## Status of implementation
CODE OF ACTION | REGIONAL ACTION | FURTHER SPECIFICATION | STATUS OF IMPLEMENTATION | CONCLUSIONS ON THE STATUS OF IMPLEMENTATION
RL1 | Prepare and agree on HELCOM guidelines on marine litter references to be included in national and local waste prevention and waste management plans, i.a. an element highlighting the impacts of marine litter. | Guidelines by 2017 | Accomplished | Germany prepared a questionnaire for HELCOM countries to compile background information for drafting HELCOM guidelines on best practice on waste management to prevent waste turn into marine litter (RL3) and probably addressing cleaning and collection systems to prevent litter from land entering the aquatic environment (RL2) and marine litter references in waste management plans (RL1). The results of the questionnaire which gathering input from Denmark, Estonia, Finland, Germany, Poland, Russia, Sweden as well as KIMO and WWF Poland, as well as five additional responses from municipalities and one from a port operator are availble (document 3-7 to PRESSURE 11-2019).Together with the OSPAR RAP ML coordinator Germany has developed a roadmap for finalization of the background document and developed ideas on the potential follow-up (Outcome of WS RAP ML 5-2020, para. 22). PRESSURE 14-2021 considered the accomplishment of actions RL1 and RL3 in the RAP ML based on the work conducted on the matter (document 3-5) and agreed that they can be considered accomplished (Outcome of PRESSURE 14-2021, para. 3.1).
RL2 | Provide HELCOM guidelines on best practice routines with regard to cleaning and collection systems to prevent litter from land entering the aquatic environment. | Guidelines by 2017 | On-going | See RL1
RL3 | Share best practice on waste management in order to identify and address loopholes that makes waste turn into marine litter, including the issue of landfills, regulations and enforcement. | _ | Accomplished | See RL1
RL4 | Improvement of stormwater management in order to prevent litter, including microlitter, to enter the marine environment from heavy weather events. | By 2018 at the latest HELCOM has compiled information to give guidance on improvements of stormwater management on a local level to prevent and reduce stormwater related waste (including micro litter) entering the marine environment, taking into consideration similar action within OSPAR. If appropriate according to findings of the activity and other relevant information, amend HELCOM Recommendation 28E/5 on municipal wastewater treatment. | On-going | *HOD 59-2020 supported endorsement of the revised HELCOM Recommendation 23/5 on storm water management for the adoption by HELCOM 42-2021 (document 6-2), pending study reservation by Germany with expected clarification by 15 January. *Swedish EPA report on the analysis of the state of knowledge and challenges on storm water *CCB “Guidance on concrete ways to reduce microplastic inputs from municipal stormwater and waste water discharges”
RL5 | Establish a dialogue and negotiate on solutions with business and industry to (i) develop design improvements that reduce the negative impacts of products entering the marine environment, and (ii) reduce over‐ packaging and promote wise packaging | Initiatives taken by the private sector. | On-going | List of principles to improve the different phases of the design process in terms of reduction/prevention of marine litter generation steamed from the HELCOM-INTERREG Workshop on Marine Litter and Ecodesign held on 15 June 2018 in Berlin (Germany) (document 4-5 to PRESSURE 9-2018). Additional discussion is foreseen in terms of resources’ availability and identification of the final product of action RL5.
RL6 | Establish an overview of the importance of the different sources of primary and secondary microplastics. Evaluate products and processes that include both primary and secondary micro plastics, such as fibres from clothing, assess if they are covered or not by legislation, and act, if appropriate, to influence the legal framework, or identify other necessary measures. | By 2017 an overview on what products and processes contribute to the input of micro plastics to the Baltic Sea, taking into account similar action within OSPAR. By 2018 existing legislation is assessed and necessary measures identified together with relevant stakeholders. | On-going | *Results of Dannish national investigations available: “Microplastics, Occurrence, effects and sources of releases to the environment in Denmark” and “Microplastic in Danish wastewater. Sources, occurrences and fate". *EU study on microplastics in cosmetics. *EU report "Intentionally added microplastics in products" by Amec Foster Wheeler Environment & Infrastructure UK (2017) *EU report "Investigating Options for Reducing Releases in the Aquatic Environment of Microplastics Emitted by Products" by EUNOMIA (2018) *Finnish Bachelor's Thesis on microplastics and harmful substances in urban runoffs and landfill leachates ‐ Possible Emission Sources to Marine Environment (2016). *Swedish investigation on sources of micro plastics. *"Technical report of microplastic pollution originating from textiles and paints/coatings" by CCB (2017) *"Review of existing policies and research related to microplastics" (2019) and "Review of existing policies and research related to microplastics - Summary for Policy Makers" (2019) * With the finalisation of the “Review of existing policies and research related to microplastics” the first part of the action (“Establish an overview of the importance of the different sources of primary and secondary microplastics”) is accomplished whereas the second part (“Evaluate products and processes that include both primary and secondary micro plastics, such as fibers from clothing, assess if they are covered or not by legislation, and act, if appropriate, to influence the legal framework, or identify other necessary measures”) is to remain in the revised RAP on ML (Outcome of PRESSURE 19-2019, para. 3.8).
RL7 | Compilation of available techniques as well as research and develop additional techniques in waste water treatment plants to prevent micro particles entering the marine environment. | By 2018 HELCOM has compiled information, and prepared a report on micro particles removal in waste water treatment plants taking into account similar action within OSPAR. If appropriate according to findings of the search and other relevant information, amend HELCOM Recommendation 28E/5 on municipal wastewater treatment. | On-going | *Danish project on evaluation of various technologies ability to retain microplastic from wastewater developing a technology to retain microplastic from wastewater (2015) *Danish partnership focusing on microplastic pollution in wastewater (2017) *Danish guide on how to handle wastewater from artificial football pitches containing car tire rubber granulates (2018) *Danish project on developing and testing a filter technology to retain microplastic (2016) *Danish project on developing a technology to retain micro rubber from car tires (2017) *PhD thesis of J. Talvitie “Wastewater treatment plants as pathways of microlitter to the aquatic environment" (2018) *Swedish sources and pathways for microplastics to the marine environment - A review of existing data *Swedish report: "Advanced wastewater treatment for separation and removal of pharmaceutical residues and other hazardous substances (Report 6803 April 2017)" which section 5 (p.29) provides an assessment of available techniques
RL8 | Assess the importance of the contribution of upstream waste flows to the marine environment and, if needed, identify suitable actions. | By 2017 an assessment of the importance of sewage related waste coming from the upstream waste flow is produced. By 2018 share assessment with River and River Basin Commissions and identify measures including the implementation of related regulations; missing elements are identified and guidelines for improvement are presented. | On-going | * "Analysis of the degree of the marine environment pollution by wastes flowing down the rivers to the sea, including sanitary waste" (2019). * "Guidance on concrete ways to reduce microplastic inputs from municipal stormwater and waste water discharges" by CCB (2017) *Based on the analysis of the degree of the marine environment pollution by wastes flowing down the rivers to the sea, including sanitary waste, PRESSURE 12-2020 agreed to focus further work on the report on the magnitude of sanitary waste in the region and suitable measures for prevention and reduction to consider revision of the scope of this action as part of the update of the RAP ML (document 7-11 and Outcome of PRESSURE 12-2020, para. 7.20-7.23).
RL9 | Compile information on the prevalence and sources of expanded polystyrene (EPS) in the marine environment, and engage with industry to make proposals for alternative solutions (e.g. use of other materials, establishment of deposits, return and restoration systems, overpackaging reduction). | By 2017 an overview of the most significant sources of EPS ending up in the marine environment is produced, in cooperation with OSPAR. Make recommendations to the Contracting Parties on voluntary agreements with the industry on changes in product design and applying best practices when handling EPS by 2019. | On-going | *Survey of polysterene foam (EPS and XPS) in the Baltic Sea" by Denmark (2019). *Catalogue of actions to prevent EPS entering the marine environment, proposed in the report above, discussed at the Forth Workshop on the Implementation of the Action Plan (WS RAP ML 4-2019). Proposed new actions (Annex 4 of the Outcome of the Workshop) to be considered at PRESURE 12-2020. *Further steps on prioritized actions addressing EPS and XPS: the first three actions (document 4-6) are suitable for a HELCOM recommendation and that the last one (on floats for flag buoys) is more appropriate to be incorporated into the revised RAP ML. Denmark to provide the first draft to PRESSURE 14-2020, if the development of the recommendation is approved by HOD 59-2020 (Outcome of PRESSUR 13-2020, para. 4.11-4.13). *HOD 59-2020 agreed to start the work on the development of a new HELCOM Recommendation on EPS and XPS (Outcome of HOD 59-2020, para. 6.29).
RL10 | Define and implement appropriate instruments and incentives to reduce the use of plastic bags, including the illustration of the associated costs and environmental impacts (e.g. establishment of levies, deposit fees, taxes or bans on plastic bags). Support regional coordination in the Baltic Sea of the implementation of the future revised Directive 94/62/EC on packaging and packaging waste to reduce the consumption of lightweight plastic carrier bags, for HELCOM Contracting Parties being EU members. | By 2018 HELCOM Contracting Parties start to coordinate and inform each other about consumption of plastic bags on an annual basis. By 2019 establish a reduction target of plastic bags, taking into account the measures which are implemented nationally. | On-going | *"Life Cycle Assessment of grocery plastic carrier bags’ in DK’s supermarkets in 2017" *Finnish Plastic Carrier Bag Agreement
RL11 | Cooperate on the establishment and/or further development of deposit refund systems for bottles, containers and cans (e.g. glass, plastics and aluminum) in the HELCOM Contracting Parties in accordance with national law as appropriate. Investigate and strive for bilateral and multilateral solutions between the countries for establishment of such systems in relation to passenger ships. | CPs informing in 2017 on the status/plans regarding the deposit refund systems, including on possible solutions regarding passenger ships. | On-going | *Estonia conducted a survey to CPs (2016). Outcome: currently functioning deposit refund systems for bottles, containers and cans (e.g. glass, plastics and aluminium) are in place in DE, DK, SE, FI, EE and LT. In PL, LV and RU the system is not in place at the moment. There is no action regarding bilateral and multilateral solutions between the countries for establishment of such systems in relation to passenger ships. *On-going work between Estonia and Latvia aiming at developing a joint packaging deposit system between these two countries.
RL12 | Encourage, based on existing labels such as the EU Ecolabel and the Nordic Ecolabel, exchange with international environmental certification schemes for information and inclusion of the management and prevention of marine litter in their lists of criteria. | By 2016 initiate an activity on what certification schemes could be addressed, which existing criteria could be promoted for potential inclusion in international certification systems together with ways and means how to help approving those. | Not initiated | _
RL13 | HELCOM Contracting Parties to seek cooperation with the River and River Basin Commissions, as appropriate, in order to include impacts of litter on the marine environment from riverine inputs, taking into account activities in the context of the implementation of the Water Framework Directive (WFD) and the Bathing Water Directive, and beyond, when applicable. This cooperation should include the exchange of experience on best practice to prevent litter entering into water systems, in line with action RL8. | HELCOM Contracting Parties will continue cooperation with River and River basin Commissions, as appropriate, in order to integrate measures addressing the reduction of littering in river basins followed up by appropriate information exchange on the implementation of measures. | Not initiated | _
RL14 | Address landfills or dumpsites including historic ones which may eventually pose a risk to the marine environment due to factors such as coastal erosion and vicinity to rivers. | By 2020 a regional‐wide map on landfills and dumpsites including historic ones which may eventually pose a risk to the marine environment is produced. | On-going | Estonia conducted a survey to CPs (2016). Feedback provided by all HELCOM members except Germany, Lithuania and Russia. The received feedback indicated that all the landfills are under control in the region and cannot be considered as sources of marine litter. The survey was relaunched in 2019 when Lithuania provided feedback. Information on the landfills is to be verified by national data reporters including re-evaluation of the risk posed by the sites together with missing landfills’ coordinates by 1 December 2019. Once the information is updated, it will be made available in the HELCOM Map and Data Service and the action will be considered accomplished (Outcome of PRESSURE 19-2019, para. 3.11-3.17)
RL15 | Establish an exchange platform for spreading experiences on good cleaning practices in beaches, including cleaning beaches actions by local communities, riverbanks, pelagic and surface sea areas, ports, marinas and inland waterways, in cooperation with relevant fora. Develop best practice on environmental friendly technologies and methods for cleaning. | Coordinate with other RSCs in order to set up an exchange platform for spreading experiences on good cleaning practices in the different marine compartments and rivers. | On-going | The International Environmental Forum “Baltic Sea Day” and exhibition “Ecology in the Big City” which annually takes place in St Petersburg (Russia) can serve as the platform to exchange good practices and techniques for cleaning beaches, riverbanks, ports, marinas and inland waterway.
RS1 | Development of best practice on the disposal of old pleasure boats (i.e. intentional disposal of the boats at the ending of their lifetime in the sea and on shore). | Best practice developed by 2018 | Accomplished | *ELB (End-of-Life boats) report that collects a best practice -model on recycling of ELB (2019). *Swedish national project on recycling of pleasure boats by Sweboat, Båtskroten Sverige AB and Stena Recycling AB (2015). *Compiled information on activities and economic incentives aimed at appropriate disposal of ELB (2019). *Danish report on recycling of fiberglass into traffic shield products (2019) *PRESSURE 19-2019 supported the development of a regional approach on ELB which would assist countries to handle the problem. Since the situation of ELB differs in the countries, the starting point to develop the regional approach would be a policy message based on the the existing material (Outcome of PRESSURE 19-2019, para. 3.27-3.29). *HOD 59-2020 approved the draft policy brief on End of life Boats (ELB) (document 6-1) as a HELCOM policy message on End of Life Boats. *PRESSURE 14-2021 considered the accomplishment of the action (document 3-3), noting that the HELCOM policy message on End of Life Boats is available in the HELCOM website and agreed that the action is accomplished (Outcome of PRESSURE 14-2021, para. 3.4-3.5).
RS2 | Develop best practice in relation to inspections for MARPOL Annex V, including harmonized management of data. Support regional coordination of IMO regulations in accordance with EU requirements for those HELCOM countries which are EU members. | Best practice developed in cooperation with Paris MoU by 2017 | Accomplished | *"Sanctions, penalties and fines issued by OSPAR and HELCOM Contracting Parties for waste disposal offences at sea" *Seminar on the prevention of and sanctions on illegal waste disposal from ships at sea to be held on 29-30 November 2018 in Berlin. *PRESSURE 14-2021 considered the accomplishment of the action based on the work conducted (document 3-6), took note that the background document was finalized in 2016 and the workshop held in 2018. The text presented in the document therefore reflects the situation at this time, in particular the discussions preceded the amendment to the Port Reception Facilities Directive, adopted in 2019 (2019/833) and replacing 2000/59/EC. The meeting took note that Denmark does not agree with all parts of the background report and the recommendations, particularly, with the conclusions regarding the efficiency of PRF related inspections conducted under the framework of PSC. The meeting agreed that the action is accomplished and further acknowledged that the legal framework has been developed since publication of the background report.
RS3 | Further work on implementation and harmonization of the no‐special‐fee system in ports of the Baltic Sea countries, addressing: * gaps in existing regulations, * enforcement and practices concerning shipping, * port reception facilities auditing to assess adequacy of garbage collection, * fair waste burden sharing between ports. | Evaluate the implementation of HELCOM Recommendation (28E‐10), starting 2016 | Not initiated | Chapter 2 of the EU *Study to support the development of measures to combat a range of marine litter sources" (2016)
RS4 | Implementation of the ISO standard (ISO 201070:2013) in relation to port reception facilities. Differentiate according to the size of the port. Promote the development of regional statistics on waste collected in ports based on existing information as far as possible. | Assess how many ports are operating according to ISO standards and to propose action as appropriate by 2017. | Not initiated | _
RS5 | Promote and disseminate best practice in relation to all relevant aspects of waste management within the fishing sector (including e.g. waste management on board, waste management at harbors and operational losses/net cuttings). | By 2018, based on the OSPAR outcome, select best practices to be disseminated in the Baltic Sea. | On-going | *"Best practice guide to reduce inputs of cuttings of nets and cord to the marine environment" (2020)
RS6 | Through a multinational project, such as the MARELITT Baltic project, together with the fishing industry and other stakeholders, develop and promote best practice in relation to ALDFG and derelict fishing gear and their removal. | Best Practice developed by 2017, the issues is promoted within HELCOM‐ EUSBSR cooperation | On-going | *Conclusions of the Marelitt Baltic project available: "Baltic Sea Blueprint" (2019) *Outcome of a regional questionnaire to compile information on national activities regarding ALDFG available (2019). *Prioritized actions to address ALDFG in the revised RAP ML agreed upon (Annex 2 of the Outcome of WS RAP ML 5-2020).
RS7 | Compile information and elaborate guidelines on best practices to reduce the input of ALDFG from commercial and recreational fishing to the Baltic Sea taking into account geographical particularities; utilize UNEP RSC report and FAO on ALDFG as a starting point and focus on regional specifics | Guidelines developed by 2017 taking into account geographical particularities. | On-going | See RS6
RS8 | Identify the options to address key waste items from the fishing and aquaculture industry, which could contribute to marine litter, including deposit schemes and extended producer responsibility. | Late 2016 assess the use of OSPAR document and in consultation with the Baltic Sea Advisory Council consider and agree on the way forward to address key waste items from the fishing and aquaculture industries. | On-going | *Chapter 4 of the EU *Study to support the development of measures to combat a range of marine litter sources" (2016) *Swedish preliminary study of lost fishing gear from a circular economic perspective.
RS9 | Investigate the use and prevalence of dolly ropes (bunches of polyethylene threads used to protect the cod end of demersal trawl nets from abrasions; synthetic fibre) in the areas of the Baltic Sea where they are used and consider the need to act. | Consider the outcome of the study on the impact of dolly ropes currently under development by the Netherlands. Baltic Sea Advisory Council is to be invited to be involved in this activity. | Accomplished | PRESSURE 12-2020 agreed that RAP ML action RS9 on dolly rope can be considered accomplished since dolly ropes are not used in the Baltic Sea (document 7-6 and Outcome of PRESSURE 12-2020, para. 7.27).
RS10 | Mapping of snagging sites or historic dumping grounds and a risk assessment for identifying where accumulation of ghost nets pose a threat to the environment and should be removed. | As part of the assessment to be developed by HELCOM SUBMERGED by 2016. Mapping by 2017. Risk assessment | On-going | *Dannish report: "Ghost nets—A pilot project on derelict fishing gear" (2017)
RS11 | Based on the risk assessment conducted in RS10 and identification of accumulation areas, initiate removal of ghost nets and their safe management on land. | The aim is to increase the removal and disposal of the nets, and that statistics are available to confirm the increasing trend. | On-going | See RS6
RS12 | Enter into the partnership with international and regional organizations (e.g. KIMO, NABU, OSPAR Commission) as well as port authorities, to encourage implementation of passive Fishing for Litter schemes, to collect litter caught in fishing nets during normal fishing activities. | Increasing trends in the number of vessels from the fishing sector involved in the schemes. | On-going | See RS7
RE1 | To prepare information sheets to assist Contracting Parties in developing material for education programs, especially for professional seafarers including fishermen, highlighting the marine litter problem and including codes of practice in cooperation with relevant organisations including IMO. | Information sheets to be prepared by 2016 | On-going | CBD open online training course on marine litter and microplastic pollution (September-November 2017)
RE2 | HELCOM website to be updated periodically based on the input from Contracting Parties on marine litter management activities. | 2015 initial information uploaded (simplified BSAP follow up system) | Not initiated | _
RE3 | Develop a communication strategy for this Regional Action Plan linked in a coherent way with national initiatives/actions. This will include linking the HELCOM website to relevant projects and initiatives. | 2016 | Not initiated | _

## Leadership by country
LEADERSHIP
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden | CCB | WWF Poland
RL1 | NC | NC | NC | NC | NC | NC | NC | NC | NC | Contribute | NC | NC
RL2 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RL3 | NC | NC | NC | NC | L | NC | NC | NC | NC | NC | NC | NC
RL4 | NC | NC | NC | NC | NC | NC | NC | NC | NC | C | C | NC
RL5 | NC | NC | NC | NC | L | NC | NC | NC | NC | NC | NC | NC
RL6 | NC | NC | NC | NC | C | NC | NC | NC | NC | NC | NC | NC
RL7 | NC | NC | NC | CL | NC | NC | NC | NC | NC | L | NC | NC
RL8 | NC | NC | NC | NC | NC | NC | NC | L | NC | NC | NC | NC
RL9 | L | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RL10 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | C | NC
RL11 | NC | L | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RL12 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RL13 | NC | NC | NC | NC | NC | NC | NC | L | NC | NC | NC | NC
RL14 | NC | L | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RL15 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RS1 | NC | NC | NC | L | NC | NC | NC | NC | NC | NC | NC | NC
RS2 | NC | NC | NC | NC | L | NC | NC | NC | NC | NC | NC | NC
RS3 | NC | NC | NC | NC | C | NC | NC | NC | NC | NC | NC | NC
RS4 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RS5 | NC | NC | NC | NC | C | NC | NC | NC | NC | L | NC | NC
RS6 | NC | NC | NC | NC | C | NC | NC | L | NC | NC | NC | L
RS7 | NC | NC | NC | NC | C | NC | NC | L | NC | NC | NC | L
RS8 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RS9 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RS10 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RS11 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
RS12 | NC | NC | NC | NC | C | NC | NC | L | NC | NC | NC | L
E1 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
E2 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC
E3 | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC | NC

## Activities by country
ACTIVITIES
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden | CCB | WWF Poland | Potential contribution from projects
RL1 | N | N | N | N | N | N | National waste management plan for 2014–2020 is aiming to reduce waste amounts, accounting system, waste handling system, to increase society consciousness and qualification of specialists etc.; National waste prevention programme for 2014-2020 period (thereinafter - Prevention programme) is also aiming to reduce impact of waste to environment and human health as above mentioned Management plan. Prevention programme includes awareness raising measures in order to reduce the amount ligtweight carrier bags as these bags are identified as one of the most polluting plastic products in the marine environment. Both legal documents are applicable for whole national territory including marine. | N | Waste management legislation has been under the reform during last few years including implementation on national project “Ecology” (2019-2024) which contains a wide range of changes in waste management on federal, regional and local levels (Outcome of PRESSURE 19-2019, para. 3.37). FSBI "State Oceanographic Institute" of Roshydromet is implementing the state project "Development of scientific methods to study the marine litter pollution" for the years 2020-2024 in order to develop recommendations for introducing the best methodologies into the Russian marine monitoring system. | There is one measure within in the existing national (Swedish) EU MSFD Programme of Measures (PoM) to include a reference to marine litter in the Swedish National Waste Plan and Waste Prevention Program. There is also one measure in the Swedish PoM about including a reference to marine litter in local waste managment plans. This PoM-measures has been included in the revised National Waste Plan and Waste Prevention Program for the years 2018-2023. However during the evaluation of the existing PoM we have realised that the reference to marine litter needs to be strengthened and clarified and that many municipalities need support in order to implement sufficient measures. | N | N | ‘Blastic project – plastic pathways from land to sea’, funded by the Central Baltic Programme (2016‐2018).
RL2 | N | N | N | N | N | N | The wastewater management regulation prohibits the disposal of waste to the aquatic environment. The Regulation establishes the mandatory use of cleaning and collection systems for suspended solids. | N | N | The government has appointed an investigation on how to implement the EU's single use plastics directive in Sweden. The proposal will be presented in the end of 2020 and is expected to include suggestions on measures to improve collection systems. The Swedish EPA and SWAM contribute to the investigation. The development project Why do people not do as they say by the Keep Sweden Tidy foundation that was funded by the Swedish EPA may contribute to improve collection systems. The Swedish EPA will also publish a report with the aim to provide an overview of existing and future techniques which can be used in industrial recycling processes to detect, quantify and/or remove substances of very high concern (SVHCs). The study is part of an ongoing dialogue between the Swedish EPA and the Swedish Chemicals Agency regarding how to increase material recycling without recirculating substances of concern. | N | N | ‘Blastic project – plastic pathways from land to sea’, funded by the Central Baltic Programme (2016‐2018).
RL3 | N | N | N | A national survey was carried out in 2017-2019 to define land and sea-based sources and pathways of macro- and microlitter, including a task to identify loopholes for waste in recycling facilities. This task includes a case study at selected waste treatment centers (former landfill sites), regional sorting stations and ecopoints for packaging collection. The aim of the work was to assess 1) the potential of different sites with varying waste management activities to generate littering and 2) whether this turns into marine litter. The results of this survey, with detailed presentation of the data collection and recommendations, will be published as a part of the overall project end report in the end of 2019, was published as a part of the overall project final report in 2020. | A close cooperation has been established with the International Waste Working Group (IWWG), which agreed to support the further implementation of the waste management actions within both, the HELCOM and the OSPAR RAP MLs. As a next step Germany plans to send out a questionnaire addressing loopholes that make waste turn into waste for land‐ based macro‐ and microplastics and best practise of primary actions in waste management by early 2018. | N | Not clear which information should be added here. Information on landfills please find below in RL 14. | N | N | Municipal waste plans and waste prevention and management: In the regulations for municipal waste plans that the municipalities are responsible of, the Swedish EPA has set requirements for the municipalities to work strategically with the littering issue. The regulations require that the waste plan must contain goals and measures to prevent and limit litter. For this, the Swedish EPA has produced guidance on the regulations Guidance for the construction industry: The Swedish EPA has identified that approximately 7-10% of the litter on the shores of the Baltic Sea (Sweden) comes from the construction and demolition sector. Through communication to the industry about the risk and simple measures that can be taken, the industry itself can contribute to reducing the risk of littering. | N | N | ‘Blastic project – plastic pathways from land to sea’, funded by the Central Baltic Programme (2016‐2018).
RL4 | N | There are ongoing national activities to improve storm-water management, particularly closing the outlets discharging directly to the sea as well as other measures to handle storm water smartly. Estonia supports further work with the revision of the Recommendation. | N | Potential contribution of research project MIF on sampling methodology (water flow volume based) and preliminary data on microlitter in stormwaters. Ongoing technological development. Pilot samples have been collected from one sampling site in 2019 and 2020. | N | N | N | N | N | The Swedish EPA is responsible for analysing the state of knowledge and challenges concerning storm water management. 2020 SEPA provide 84 million SEK for measures that reduce pollution and waterborne microplastics. The SEPA distribute grants until 2023 for measures that improve the aquatic environment. Contribution to investments to reduce emissions of microplastics and other pollutants via stormwater is part of the mission. During 2020, SEPA can also distribute grants to stormwater investigations aiming towards increased knowledge about stormwater management and for an improved water environment. Projects that receive support must contribute to one or more of the call's objectives of increased knowledge of: a) reduced spread of macro and microplastics via stormwater, b) reduced spread of other pollutants via stormwater, c) modelling of stormwater, d) performance of different stormwater facilities. Granted projects must be able to benefit municipalities and actors within the stormwater area in Sweden. More information can be found here: http://www.naturvardsverket.se/Stod-i-miljoarbetet/Bidrag/Utslapp-via-dagvatten-2020/ and here: http://www.naturvardsverket.se/Stod-i-miljoarbetet/Bidrag/Stod-till-dagvattenutredningar/ SEPA is also working together with other authorities with a Guide for nature-based solutions that is planned to be completed in 2020. | “Guidance on concrete ways to reduce microplastic inputs from municipal stormwater and waste water discharges” | N | ‘Blastic project – plastic pathways from land to sea’, funded by the Central Baltic Programme (2016‐2018). FP7 ‘Baltic Flows’ (finished in 2016). ‘IWater’ (December 2015 - May 2018) a project run by Union of Baltic Cities. 'FanpLESStic-sea project - Initiatives to remove microplastics before they enter the sea' (Jan. 2019-June 2020). *BSR WATER project platform (climate change aspects in storm-water management is one of the WPs of the project platform)
RL5 | The Danish Forum for circular plastic packaging under the Danish Plastics Federation has developed recommendations and a manual of how to change the design of packaging focussing on reuse and recycling | N | N | The challenge prize competition “Marine litter challenge” was as an innovation contest in 2018 open for all, from general public to companies and industry. It was launched to find solutions for reducing the amount of marine litter from sources as well as to develop methods for collecting ML. The contest received altogether nearly 100 different ideas. The first prize was awarded to a startup company developing new packaging materials to replace plastics in e.g. in shipping packages of online stores. In addition to that, development to replace EPS boxes in the fishing and aquaculture industry by board packaging material made of renewable wood fibre has taken place recently in Finland. The Plastics Roadmap for Finland points out the first steps towards a new, sustainable plastic economy. It includes 10 key actions, of which one is targeted to investing in and supporting in a big way alternative solutions for replacing plastics with new, bio-based materials, and also in setting up a new plastics knowledge network. https://muovitiekartta.fi/in-brief/ | * The UBA is co‐chairing the EU MSFD TG Marine Litter and was in this context also driving the process of producing a report assessing the biological and socioeconomic harm caused by marine litter which is now publically available. *Germany has set up a national Round Table on Marine Litter which is addressing overpackaging/wide packaging by looking into how existing regulations and praxis can be modified/adapted. A lot of stakeholders from business and industry are involved. Some of them are also involved in the national Round Table “Eco-Design for Plastic Packaging” which aims to develop a Guideline on the eco-design of packaging among the entire supply chain. First results expected in 2018, these will be shared within HELCOM (WS RAP ML 2-2017) *Germany currently considers how to transfer this national process to a regional level aiming to set up a dialogue together with other HELCOM CPs and head organizations of relevant industrial sectors such as the packaging industry. *Promotor of the Workshop held on 15 June 2018 in Berlin (Germany) organized by HELCOM and the INTERREG BSR project “EcoDesign Circle” | N | N | N | N | Sweden is engaged in the European Plastic Pact and the Basel convention Plastic Waste Partnership. These are two international initiatives that involve governments, industry stakeholders and organisations with the overall aim to strive for a sustainable plastic use, increase reuse and recycling, and improve plastic waste management. - In the European Plastic Pact, Sweden provide with funding, and sit in the steering group. Also, the Swedish EPA are participating in the working group for collection, sorting and recycling and the working group for responsible use of plastics. -In the Basel Partnership for plastic waste, Sweden contribute to development and implementation of workplans for all working groups. -At the national level, SEPA have the role as a coordinator for plastic issues. This include bringing together different actors along the plastic value chain, competent authorities and organisations. SEPA are therefore now setting up a “National plastic-coordination” with the aim to spread knowledge and enhance cooperation between all relevant actors working towards a sustainable plastic use. | N | N | No information reported
RL6 | Denmark has carried out two national investigations on microplastics, “Microplastics, Occurrence, effects and sources of releases to the environment in Denmark” (Environmental project No. 1793, 2015) and “Microplastic in Danish wastewater. Sources, occurrences and fate (Environmental Project No. 1906. Marts 2017) (PRESSURE 6-2017). |  | Study on microplastics in cosmetics. EU is considering follow‐up activities on microplastics. Report "Intentionally added microplastics in products" (2017). Report Investigating Options for Reducing Releases in the Aquatic Environment of Microplastics Emitted by Products (2018). | Bachelor's Thesis on microplastics and harmful substances in urban runoffs and landfill leachates ‐ Possible Emission Sources to Marine Environment (2016). Finland aims to launch a case/pilot study on microplastics in storm waters, as a part of a national research project (MIF). To support national PoM, Finland has carried out a national survey on the sources of both macro- and microlitter (plastics). The final report was published in 2020. As a part of this study a report of the amount of microplastics included in the Personal Care products on Finnish markets and entering municipal waste waters was compiled in 2017. There are also EU-wide assessments made by consulting companies, such as at least EUNOMIA (2018), Amec Foster Wheeler Environment & Infrastructure (2017). Regarding legal instruments, Finland is following the development in EU, for example the work which is presently being carried out in EU on microplastic emissions. | Germany has produced a national overview on relevant sources for Microplastics, is involved in the implementation of the respective measures of the OSPAR RAP ML including ongoing dialogues with the cosmetic and other relevant industries and has also targeted this action via a national roundtable on Marine Litter. This can be brought into the process once it gets started. Within the implementation of the OSPAR RAP ML, an Assessment Document of land-based inputs of microplastics in the marine environment is currently considered. The report describes source emissions and potential impacts of microplastics in the OSPAR area in order to facilitate prioritization of further actions to mitigate microplastic emissions to the environment. Upon finalization, it will be shared within HELCOM. The FONA-call of the Federal Ministry of Education and Research also addresses the issue of microplastic. Moving forward, microplastics will be a priority on the agenda of the Round Table of Marine Litter. |  | National project "Investigations of marine litter that causes marine environment pollution, amount, type, sources and other characteristics of litter" (will start in 2019). Project mostly oriented to sources of marine litter (wasterwater, stormwater, lagoon role) and its significance. Also methodological recommendations to monitoring strategy will be developed in order to evaluate potential marine litter sources and flows into marine area. |  | In the frame of the project MicroplAstics Research in the BaLtic marine Environment (MARBLE) (funded by the Russian Science Foundation) the research team from Laboratory for Marine Physics of the Atlantic Branch of P.P. Shirshov Institute of Oceanology of RAS collected samples of microplastic from the waters of the Baltic Sea and found that near the water surface and bottom, there are a lot of microfibers. Studies were carried out to measure the rate descent of microplastic to the bottom at the Laboratory. It is assumed that the results of the project will be used to attract public attention to the problem of microplastic pollution of the World Ocean in general and the Baltic Sea in particular. Results of this project were presented at the HELCOM SPICE workshop on microliter held on 7-8 November in Helsinki (Finland). Project EI-GEO “Environmental impact of geosynthetics in aquatic systems” (http://ei-geo.com/). Geosynthetics are widely used in hydraulic engineering in aquatic ecosystems such as in revetment measures for coastal protection or in ballast layers for wind energy plants. While providing various economic and technical benefits, the application of geosynthetics in hydraulic engineering projects has been questioned recently as these materials might degrade during their lifetime and induce a hazardous impact on the aquatic environment in a long term especially as the origin of plastic debris or as source/sink for chemicals such as plasticizers and stabilizers used in the production of geosynthetics to improve their performance. The proposed project is aimed at assessment of the application of geosynthetics in hydraulic engineering. Accelerated artificial ageing of geotextiles used in marine applications will be applied in a laboratory scale and the performance characteristics will be compared with the virgin material. Whereby, a combination of mechanical, chemical and microbiological stress will be simulated. Additionally, the leaching behavior in relation to the ongoing ageing process as well as the ecotoxicological impact of leachates in marine environment will be investigated. The laboratory tasks will be accompanied by a field case study at the Kaliningrad shore. | SEPA have carried out two government assignments about micro plastics: 2017: Identify key sources of microplastics into the ocean and suggest measures to reduce the discharge levels 2019: Measures to avoid the release of microplastics in the environment. Based on the results of the assignments the Swedish EPA recommended that the following sources should primarily be addressed in Sweden: Roads and tyres, Artificial turf pitches, Industrial production and management of primary plastic, Washing of synthetics, Boat hull paint, Littering. o The Swedish National Road and Transport Research Institute are working on a government assignment to develop the body of knowledge about the release of microplastics from road traffic. https://www.vti.se/en/research-areas/microplastics-from-road-traffic/ o The Swedish EPA will be the coordinatior for issues concerning plastic and microplastic at the national level. This includes gathering and disseminating knowledge on microplastics o The Swedish EPA are carrying out two projects on indicators related to OSPAR: Project to develop indicators for monitoring of microplastics in the marine environment, Project to measure and analyse microparticles in sediment. oThe Swedish EPA have developed two guidance documents with the aim to reduce the release ofmicroplastics: The management of artificial turfs, Measures to minimize the release of microplastics from manufacturing and handling of plastic. o In regard to procurment the Swedish EPA has formed a purchasing group for reduced environmental impact from artificial turf pitches. The Swedish Environmental Protection Agency finances the work to, through public procurement, set requirements for artificial turf so that the leakage of microplastics is reduced. oSwedish EPA distribute government funding to combat the environmental problems with microplastics. EPA has carried out a call of 25 million SEK for funding of research projects to increase the knowledge about the origin, distribution and impact of microplastics on the environment. For example investments to reduce emissions of microplastics and other pollutants via stormwater (see RL4). o The Swedish Agency for Marine and Water Management (SwAM) has financed a study on the spread of micro plastics from boat brush washers and held a seminar that discusses various measurement methods for micro particles. | Technical report of microplastic pollution originating from textiles and paints/coatings, addressing both environmental implications and available solutions published on CCB’s website. It will be used in public awareness and information work, as well as potentially – to address the industry. |  | ‘Blastic project – plastic pathways from land to sea’, funded by the Central Baltic Programme (2016‐2018). 'FanpLESStic-sea project - Initiatives to remove microplastics before they enter the sea' (Jan. 2019-June 2020).
RL7 | The Danish EPA has financially supported the following projects: *Evaluating various technologies ability to retain microplastic from wastewater (2015) *Developing a technology to retain microplastic from wastewater (2015) *Partnership focusing on microplastic pollution in wastewater (2017) *Project on developing a technology to retain microplastic from laundry wastewater at large laundries (2017) *Guide on how to handle wastewater from artificial football pitches containing car tire rubber granulates (2018) *Project on developing and testing a filter technology to retain microplastic (2016) *Project on developing a technology to retain micro rubber from car tires (2017) | N | N | Research on the role of waste water treatment plants (WWTPs) as pathways for microparticles has actively been carried out both in Sweden and Finland, and this research also includes Nordic collaboration. General conclusion is that the methods applied in conventional WWTPs remove the great majority of all microparticles from WWTP effluent waters. For example the studies carried out in the largest WWTP in Scandinavia show that conventional primary and secondary treatments can efficiently remove (> 99 %) microlitter arriving at the WWTP, and that most (98%) of the microlitter is removed already during pre-treatment. The activated sludge process further decreases the microlitter concentration. The use of different advanced final-stage treatment technologies to remove microlitter from wastewater effluents has also been investigated in Finland at different WWTPs (see PhD thesis of Julia Talvitie: “Wastewater treatment plants as pathways of microlitter to the aquatic environment"; 2018). The results showed that from the primary effluent, the membrane bioreactor removed 99.9% of microplastics during treatment. From the secondary effluent, sand filtration removed 97%, flotation technique removed 95 %, and disc filter removed 40 – 98.5% of the MPs. Biologically active filtration did not have any impact on the microplastic concentration. Thus, a selection of advanced methods already exist, and they may be applied if regarded necessary. | N |  | According to the Lithuanian Wastewater Management Regulation, in determining the conditions for discharges into the environment, it must be guided by the principle that the maximum permissible concentrations in the waste water of this Regulation and other legislation can not be exceeded; the concentration limits are specified in the "Best Available Techniques" Reference Document prepared for a specific activity, except for the exceptions provided in this Regulation. | N | N | * A SEPA report on "Wastewater treatment in Sweden 2018 ” that include information of techniques to prevent marine particles to enter the marine environment is soon to be published *Swedish and OSPAR report on BATs to reduce and prevent sewage and storm‐water related waste entering the marine environment, including micro particles. *On the basis of studies into the spread of microplastics in the environment however, WWTPs appear to be a relatively minor source of microplastics. Studies show that as much as 98 % of particles are separated from the WWTP effluent using conventional treatment steps involving sedimentation and sludge withdrawal. https://www.svensktvatten.se/contentassets/7be8e202754e4011a400bcff4ed89b1c/mikSVu-rap-8-13.pdf Questions still remain regarding the possible spread of microplastics via the use of sludge as fertilizer on farm land but at least one long-term Swedish study has shown that there were no significant measurable differences with regard to amount of microplastic found on farm land when sludge had been used as fertilizer compared to control fertilization *SEPA to identify important sources of microplastic loads to the sea, to reduce the occurrence and release of microplastics from these sources and where appropriate to propose regulatory changes to reduce these emissions. The work includes a review of BATs: "Swedish sources and pathways for microplastics to the marine environment - A review of existing data". According to SEPA, with responsibility for water treatment issues, standardised analysis methods for microplastics remain under development. This hinders implementation of standards for microplastic removal at water treatment plants. On the basis of studies into the spread of microplastics in the environment however, WWTPs appear to be a relatively minor source of microplastics, as 90 - 97% of particles appear to be separated in the WWTP. An important issue remains concerning stormwater discharges, as this can result in large quantities of microplastics being released from the sewage system (see RL4). | N | N | FanpLESStic-sea project - Initiatives to remove microplastics before they enter the sea' (Jan. 2019-June 2020).
RL8 | N | N | N | Through BLASTIC project. | N | N | N | Poland developed a questionnaire to countries, whose feedback led to the report on the "Analysis of the degree of the marine environment pollution by wastes flowing down the rivers to the sea, including sanitary waste" (2017) | N | Adressed partly by the BLASTIC project which was co-financed by SwAM. Some sanitairy items are adressed under the new EU SUP directive. | *CCB made a proposal on concrete ways to reduce microplastics in stormwater and sewage which would contribute to Actions RL4, RL7 and RL8 (WS RAP ML 1‐2016). *Simple methodology for detection of microplastic in rivers, streams and other freshwater bodies adapted from the original Swedish version and tested by CCB’s member organizations and partners in several locations in Belarus, Latvia, Lithuania, Poland and Russia (both St.Petersburg and Kaliningrad regions). After testing the methodology will be included into CCB’s River Watch public monitoring manual (also in national languages) and continued on a regular basis. The screening round is still ongoing and the results will be published in early 2018. *Odra Commission is planning to include measures related to litter in the river management plan (Outcome of PRESSURE 10-2019, para. 3.40) *Suggested to include various clean-up actions in the recommendations (Outcome of PRESSURE 10-2019, para. 3.41) | N | *BLASTIC project launched a social media campaign in four countries (Estonia, Finland, Latvia and Sweden), where also the importance of land-based sources and top items were discussed. The campaign highlighted the different sources of marine litter from urban environments and the most common litter items. These included i.e. sanitary waste from sewerage and cigarette butts through storm drains. *A new project to be launched in the transboundary basin of Nemunas supported by UNESCO which can be used for consideration of the recommended measures and that the HELCOM Workshop with river basin authorities can also be utilised for communication (Outcome of PRESSURE 10-2019, para. 3.41)
RL9 | Dannish study (January 2018 - March 2019) to gather knowledge on the prevalence and sources of EPS in the Baltic Sea, and to point out possible measures to reduce the environmental burden of EPS in the Baltic Sea. The study is involving all HELCOM parties and the results of the study will act as the knowledge and decision-making basis for the further work. The first phase of the project focuses on manufacture, use and trade and on fate and hazards of EPS in the marine environment. Next phase will be focusing on occurrence of EPS in the Baltic Sea, estimates on losses and discharges and on potential measures. Contact has been established with OSPAR project Ocean Wise on the similar OSPAR action, which will run until December 2020. | N | N | On- going development in Finland for using wood-based materials to replace EPS; has already been done to replace EPS with cardboard in boxes used in storing and transporting fish (see RL5). Also waterproof cardboard has been developed to replace EPS e.g. in coffee cups and related. | N | N | N | N | N | SEPA has recently published a report “Possibilities to reduce the climate impact by circular use of plastics in the construction sector”. The report summarises existing knowledge about the use of plastics in the construction sector. It gives an indication of its climate impact, presents concrete examples and gives recommendations for what different actors in the construction sector can do to contribute to a more sustainable use of plastics. According to the report, the construction and demolition sector is estimated to account for about 7-10 percent of the marine litter on the shores of the Baltic Sea. This is about the same proportion of marine litter that comes from the fishing sector (excluding recreational fishing). There is a risk of littering when: a) Products are used outdoors. One risk factor is when materials are unpacked from their transport packaging, as packaging materials are relatively light and in some cases brittle, which increases the risk of the plastic blowing away and littering, b) Waste is stored outdoors. If the waste is stored in containers outdoors, such as on construction sites, it is important that the container is covered or otherwise protected against weather and wind to prevent the waste from spreading to the local environment, c) Waste is transported. During transport, the risk of littering depends on how the load is covered. Nets or tarpaulins are usually used on containers during transport. The meshes on the cover nets are quite coarse, and especially EPS (styrofoam) can blow off and litter. In order to reduce litter, in addition to reducing the risks of plastic becoming litter, agreements can also be made that require cleaning of the facility, including the immediate area. The report can be found here: http://www.naturvardsverket.se/Documents/publ-filer/6900/978-91-620-6923-0.pdf?pid=26756 A further project focusing on plastic flows within the construction sector is currently running and will be finalized by end of 2020. The project, e.g., includes a literature study on how the construction sector contributes to microplastics and littering, and possible action to decrease these. SwAM has funded a report on EPS/XPS where floating docks are mentioned as a potential source to microplastics in the environment. Following measures are proposed: a ban on unprotected EPS in floating docks, information to manufacturers, retailers, consumers, regular supervision of public floating docks and aquaculture. | N | N | N
RL10 | Danish EPA report that provides a lifecycle assessment (LCA) of production, use and disposal of shopping bags available in Danish supermarkets in autumn 2017. 16 different environmental parameters have been compared, and the results are shown by how many times a given type of carrier bag should be used to be as environmentally good as a regular plastic carrier bag. | N | N | Finnish framework agreement to reduce the consumption of lightweight plastic carrier bags (Plastic Carrier Bag Agreement). National PoM (2016–2021) proposes that, with the aim to reduce the littering of the Baltic Sea, proposals for measures are to be prepared to reduce the amount of plastic litter, in particular. As means to reduce littering the focus of the measures should include the use of plastic containers and bags. Green Deal agreement of the Ministry of the Environment and Federation of Finnish Commerce on the measures to reduce the consumption of plastic carrier bags signed (2016). The agreement implements the measures the MS are required to take to reduce the consumption of plastic carrier bags under the EU Packaging Waste Directive (94/62/EC), as amended by Directive (EU) 2015/720. The purpose of the agreement is to agree on voluntary measures of the retail sector to ensure that the minimum objectives concerning the consumption of lightweight plastic carrier bags in the Packaging Waste Directive are reached in Finland. As a rule all companies in the retail sector with one or several branches in Finland may join the plastic bag agreement for the trade sector via the Society’s Commitment. The Ministry of the Environment undertakes to evaluate after three years from the date when the agreement was concluded (31 October 2016) the effectiveness of the agreed measures in terms of reducing the consumption of lightweight plastic carrier bags and preventing littering. Should the evaluation show that the measures taken have not been effective, the Ministry of the Environment will consider other potential means to reduce the consumption of lightweight plastic carrier bags. The consumption of plastic bags in Finland decreased by up to 60% (depending on the commercial chain) by the end of 2017, i.e. during the first year of the Plastic Carrier Bag Agreement. | N | N | In order to reduce ligtweight carrier plastic bags in Lithuania measures are set in: 1. The Law on Packaging and Packaging Waste, which determines ban on the distribution of lightweight plastic carrier bags at the points of sale of goods or products with the exception of very lightweight plastic carrier bags with a wall thickness below 15 microns; 2. National waste prevention programme, which includes awareness raising measures in order to reduce the amount of ligtweight carrier bags as these bags are identified as one of the most polluting plastic products in the marine environment. | N | The ban on the use of plastic dishes, plastic bags and packaging for cultural events in the Leningrad Region was enshrined in the regulatory act of the Committee on Culture of the Leningrad region. The Committee for Nature Management, Environmental Protection and Environmental Safety of St. Petersburg supported the proposal of the representatives of the NGO "Razdelny sbor" to prohibit balloons at major city holidays. | SE has recently introduced a tax on plastic bags. From 1 May 2020, those who manufacture, import or receive plastic carrier bags from another EU country must pay tax on these. The tax is 3 SEK for plastic bags thicker than 15 micrometre and 0,3 SEK for plastic bags < 15 micrometre thick and with a volume <7 litres. The Swedish EPA has also developed two guidance documents on plastic bags with the aim to support compliance to the EU regulation on plastic bags. The guidance documents are directed to manufacturers and importers of plastic bags and provide guidance on how to fulfil the requirements for reporting of plastic bags and the requirements for information to customers. As a complement to the guidance, the Swedish EPA has compiled a collection of arguments to support for example the retailers in their meeting with customers. | N | N | N
RL11 | N | Estonia conducted a survey to CPs (2016). Outcome: currently functioning deposit refund systems for bottles, containers and cans (e.g. glass, plastics and aluminium) are in place in DE, DK, SE, FI, EE and LT. In PL, LV and RU the system is not in place at the moment. There is no action regarding bilateral and multilateral solutions between the countries for establishment of such systems in relation to passenger ships. | N | Finland uses a deposit-based return system for beverage packages, which enables the efficient collection of packages for recycling. More information can be found from the website of Palpa; https://www.palpa.fi/english/ | N | N | Mandatory deposit-refund system for one-way beverage containers (glass, metal or plastic) is applied in Lithuania since 1 February 2016. According to the Law on the Packaging and Packaging Waste Management a mandatory deposit-refund system for one-way packaging (of a capacity greater than one-tenth of a litter, but less than three litters, made of glass, metal or plastic) of specified beverages is applied. Collected beverage containers (glass, metal, plastic or cardboard) are reused or recycled in accordance with the targets set in the national legislation. The fulfilment of the recovery and recycling targets are under the responsibility of the producers and importers. | Poland is analysing opportunities to integrate deposit-refund systems into national legislation and the system acting in Lithuania for almost four year has already given visible positive results for the environment (Outcome of PRESSURE 10-2019, para. 3.29) | Establishment of deposit refund systems for bottles, containers and cans (e.g. glass, plastics and aluminum) in accordance with national law is ongoing. | In Sweden in accordance with Swedish regulation SFS 2005:220, all packaging sold in Sweden that contains drinks ready for consumption must be included in an approved return system (https://pantamera.nu) in 2018-2019 SEPA financed four innovation projects with the aim to increase the reuse of take-away items through deposit systems. One project with the aim to develop a deposit system for take-away items at major events, carried out by the city of Gothenburgh. One project with the aim to develop a system for deposit of take-away items via an app, carried out by Research Institutes of Sweden (RISE). One project with the aim to develop deposit systems for take-away items, carried out by IVL Swedish Environmental Research Institute. One project with the aim to analyse current deposit systems and develop proposals on how to expand or improve current systems, or develop new ones, the project was carried out by CMA research. | N | N | Possible input: http://norden.diva‐ portal.org/smash/get/diva2:721027/FULLTEXT01.pdf
RL12 | N | N | N | N | German Ecolabel ”Blue Angel” addresses shipping (packaging) or refuse bags or carrier bags from recycled plastics, among others. | N | N | N | N | N | N | N | N
RL13 | N | N | N | Through BLASTIC project. | N | N | N | N | N | No action taken because limited resources and knowledge at the national level on how to address this issue. | N | N | BLASTIC project will explore different methods for monitoring macrolitter in rivers. The work will be carried out in collaboration with local municipalities. The project will carry out pilot monitoring on riverine litter in one case study area in Estonia, Finland, Latvia and Sweden, in 2017. The aim is to produce a guidance document based on the project´s experiences in 2018. Collaboration with the municipalities went well.
RL14 | Denmark indicated that there is no information on coordinates of the national landfills reported in the Estonian questionnaire (Outcome of PRESSURE 10-2019, para. 3.34) | Estonia conducted a survey to CPs (2016). Feedback provided by all HELCOM members except Germany, Lithuania and Russia. The received feedback indicated that all the landfills are under control in the region and cannot be considered as sources of marine litter. | N | Finland has replied to the Estonian questionnaire and in short, due to the long distance to the sea and measures taken to prevent littering, the landfills probably do not cause littering of the Baltic Sea. | N | N | All landfills in Lithuania are fulfilling the requirements set in Lanfdill directive, which is transposed into national legal acts. Old landfills in Lithuania are closed and new regional non-hazardous waste landfills meet the environmental standards set in directive 1999/31/EB on the landfill of waste, which is transposed to national legal acts. | N | N | SE has responded to the HELCOM qustionnaire on landfills. Measures to reduce environmental impact from landfill can be divided into two main strategies: * Reduce emissions from landfills in the long term through the design of landfills. * Reduce the amount and hazard of the landfilled waste. These measures include producer responsibility for certain types of waste, sorting requirements for flammable waste, a ban on the disposal of sorted flammable waste and organic waste and also taxes on waste landfilled. Sweden's laws on landfill have led to the waste concentrating on a smaller number of landfills which have a higher standard. The Landfill Regulation imposes stricter requirements than before, including on the underlying barrier of the landfills, bottom sealing, final coverage and collection of leachate. The requirements differ depending on the type of waste that is deposited and the higher the more hazardous waste that the landfill receives (https://www.naturvardsverket.se/Stod-i-miljoarbetet/Vagledningar/Avfall/Deponering-av-avfall-/) The Swedish EPA has developed guidande documents for risk classification and enforcement of closed dumpsites and landfills directed to municipalities and county administrive boards. | N | N | N
RL15 | N | N | N | N | N | N | N | N | The International Environmental Forum “Baltic Sea Day” (http://www.helcom.ru/baltic_sea_day/2020_year) and exhibition “Ecology in the Big City” which annually take place in St Petersburg can serve as the platform to exchange good practices and techniques for cleaning beaches, riverbanks, ports, marinas and inland waterway. The event might become a permanent platform for local communities to exchange the best practices and solutions. Russia invited representatives of the municipalities in the Baltic Sea region to join to the annual environmental educational action “Clean Beach ” in May 2020 organised by the initiative of St. Petersburg, Russia in cooperation with Helsinki, Turku and Tallinn and coordinated by St. Petersburg organization SC “Mineral” as an annual contribution into implementation of the RAP ML (document 3-6 of PRESSURE 8-2018). "Clean Beach" was held in 2014 for the first time, as part of the International Project "Year of the Gulf of Finland - 2014". Traditionally, the "Clean Beach" campaign is not just litter collection, but also an educational event, one of its main important tasks is to improve the environmental culture of citizens, to educate the young generation and to promote environmental volunteering. Update on the acitivity provided to PRESSURE 19-2019 including beach litter monitoring data (document 3-5). Union of Baltic cities is planning to organise webinar on " Clean beach" (preliminary date, 21 of January 2020) to engage new cities and participants. | Sweden support organisations such as Cleaning Sweden and Keep Sweden Tidy (HSR) to spread information and to undertake beach cleaning actions. The Swedish government has provided 17 million SEK for beach cleaning actions in 2018-2020. For projects that are financed trough this fund there are guidance on how to clean the beaches. For other projects concerning removal of ghost nets on the seafloor or on wrecks and financed by the Swedish Agency for Marine and Water Management there are also guidance on how it should be done in regard to the environment. But we see that this guidance need to be clarified and streghtened in relation to Swedens diversed coastline. In 2019 SEPA financed the project Winter cleaning on the west coast, carried out by the West Coast Foundation. The aim of the project was to develop knowledge to support cleaning of plastic that has leaked to the environment and reduce the spread of microplastics, and carry out winter cleaning of beaches. | N | N | BalticLitter - Litter rim of the Baltic Sea coast: monitoring, impact, and remediation, from the ERA.Net RUS Plus Call 2017 - Science & Technology (June 2018- May 2021)
RS1 | Danish report on recycling of fiberglass into traffic shield products (2019) | N | N | Finland (KAT) has produced an ELB (End-of-Life boats) report compiling best practices on recycling of ELB. A survey study was made and distributed to all HELCOM countries to receive input and complete information about the practices in each of the countries, after which the report was circulated for comments and acepted at PRESSURE 10-2019.A policy brief on the topic was prepared for PRESSURE 12-2020 and countries were invited to provide comments by May 2020. | N | N | N | N | N | *Swedish national project on recycling of pleasure boats by Sweboat, Båtskroten Sverige AB and Stena Recycling AB. *Between 2018-2020 SwAM has funded a project with the aim to increase the disposal of pleasure boats. The aim is to find innovative new solutions in the process of disposal of pleasure boats. | N | N | N
RS2 | N | N | N | N | *This action is treated together with the related actions 32, 33 and 38 of the OSPAR RAP ML. The German Federal Environment Agency commissioned a study project on the issue at stake in the second half of 2015. A detailed questionnaire was designed and sent out to both OSPAR and HELCOM via the Secretariats as well as the North Sea Network of Investigators and Prosecutors’ Heads of Delegation (NSN), covering the topics treated by the study that are difficult to research from abroad or desktop‐based: Number of controls, level of fines, structure of prosecuting and control authorities etc. Responses were received from 11 OSPAR and HELCOM members, namely Denmark, Estonia, Finland, Germany, Ireland, Latvia, Lithuania, Norway, Sweden, The Netherlands and UK. *A supporting report ‘Analysis of penalties and fines issued by OSPAR and HELCOM Contracting Parties for waste disposal offences at sea’ was delivered to WS RAP ML 2-2017, OSPAR EIHA 2017 and MARITIME 17-2017. *Seminar on the prevention of and sanctions on illegal waste disposal from ships at sea to be held on 29-30 November 2018 in Berlin. | N | N | N | N | N | N | N | N
RS3 | N | N | EU study to support the development of measures to combat a range of marine litter sources, being its chapter 2 on incentivising waste disposal at ports relevant for this action. | To support national PoM, Finland has carried out a national survey on the sources of both macro- and microlitter (plastics). The survey report will be ready by the end of 2019. As a part of this study a detailed analysis on the loopholes and obstacles for handling shipping related waste and port reception of waste was carried out (interviews and on-site observations). Results of this report will feed on actions RS3 and RS4. | To support national PoM, Finland has carried out a national survey on the sources of both macro- and microlitter (plastics). The final report was published in 2020. As a part of this study a detailed analysis on the loopholes and obstacles for handling shipping related waste and port reception of waste was carried out (interviews and on-site observations). Results of this report will feed on actions RS3 and RS4. | N | N | N | N | SE has a 100 % NSF-system, which also includes caught marine litter during normal fishing operations. RS3 is strongly interlinked with the implemenation of the new EU PRF directive. | N | N | N
RS4 | N | N | N | See action RS3 | N | N | N | N | N | N | N | N | N
RS5 | N | N | N | To support national PoM, Finland has carried out a national survey on the sources of both macro- and microlitter (plastics). The final report was published in 2020. As a part of this study a detailed analysis on litter sources in fishing and aquaculture in Finland was carried out. Information from this survey will feed on actions RS5 and RS8. | Germany is having a national roundtable where the green deal to reduce the waste from the fishing and aquaculture sector is being discussed. Whereas a recommendation on Green Deals was not passed, within OSPAR, it was agreed to continue working on this topic. | N | N | N | N | In regard to this action SwAM has funded a project on best practices for cuttings of rope, nets and cord.The project was carried out by KIMO International. Dialogue meetings were held with fishers, fishery associations and ports/harbours staff to explore current practices and ways in which these waste items can be better managed. KIMO has produced a project report, best practices guide and awareness-raising materials, which can be found here: https://www.kimointernational.org/net-cuttings/ | N | N | N
RS6 | N | N | N | N | Germany is part of the EU project MARELITT and especially involved in carrying out environmental impact assessments for retrieving operations of ALDFG. Furthermore in the framework of scientific diving operations Germany is compiling information on benthic hotspots of ghost gear in German Baltic waters and the ecological soundness of manual retrieval operations. | N | N | N | Pilot project " Ghost Nets" is supported by Nord Stream 2 AG and implemented by NGO "Baltic Fund for nature", within the project, will be find out how the abandoned networks are distributed across the Gulf of Finland and develop methodological approaches to solving the problem. The results will be presented in the frame of BSD -2020. | Sweden proposed to change the deadline to 2019 in view of the expected outcomes in the frame of the MARELITT Baltic project to be available in 2018. During the latest national removal of ALDFG in Sweden it has become clear that there are several national issues that need to be considered during the removal operations. Therefore SwAM is looking into the possiblity to develop national guidelines for examle for: removal operations within so called Natura 2000 areas, what kind of removal method is best suited in regard to the area that is to be cleaned and how to best report removal operations. | N | ‘Removal of derelict fishing gear, lost or discarded by fishermen in the Baltic Sea’, the Marelitt Baltic project: methodology for designating DFG hot spot areas under development. A map on the potential locations of underwater objects, shipwrecks and hooks to be produced. Surveys to be conducted among fishermen on the designation of the DGF. Methodology on retrieval of fishing gear has been developed. Forty ports have been visited and surveyed for waste management and processing on fishing gear. A pilot action on sampling and preparation of DFG for processing is ongoing. Proposal to create a capacity building group and invite HELCOM experts to participate. Preliminary conclusions of the project available. | N
RS7 | N | N | N | N | See action RS6 | N | N | N | N | Swedish PoM includes a measure to reduce the input of ALDFG from commercial and recreational fishing in Swedish waters. Sweden proposed to change the deadline to 2019 in view of the expected outcomes in the frame of the MARELITT Baltic project to be available in 2018. | N | N | N
RS8 | N | N | EU study to support the development of measures to combat a range of marine litter sources, being its chapter 4 on marine litter reduction actions for the fisheries and aquaculture sector relevant for this action. | See action RS5 | N | N | N | N | N | SwAM has conducted a study of lost fishing gear from a circular economic perspective. A testbed for marine waste is under development in connection to the Marine Recycling Center in Sotenäs municipality. The marine waste is mostly from the fishing industry. | N | N | N
RS9 | N | N | N | N | N | N | N | N | N | N | N | N | N
RS10 | Dannish small pilot project based on knowledge gathering for the extent of ghost nets in Danish waters, which can contribute to this action. | N | N | An EMFF funded project ‘Derelict fishing gears in the Finnish waters (KAPYYSI)’ (Nov 2018 - March 2020) aimed at shedding light on the ALDFG problem in the Northern Baltic Sea. The project was conducted by the Finnish Environment Institute (SYKE) and the Finnish Fishermen’s Association (SAKL). Final report was published in 2020. | N | N | N | N | N | SwAM has during 2020 launched a ghost net reporting tool which can be used by recreational fishers, the public and commercial fishermen. | N | See action RS6 | N
RS11 | N | N | N | See RS10 | N | N | N | N | N | In Sweden, municipalities can apply for contributions to dragging for ghost nets with safe management on land through LOVA regulation (since 2018). The Swedish Agency for Marine and Water Management sanitizes shipwrecks from hazards and when feasible also removes ghost nets at the same time. During 2020 SwAM is financing removal of ALDFG by dragging with 3,6 million SEK. Due to experiences from earlier dragging operations the focus is in the following three areas: Southern parts of the Baltic Sea, The Sound and the Swedish West Coast. | N | See action RS6 | N
RS12 | N | N | N | N | *Germany is widely applying the FFL‐scheme coordinated by Mecklenburg‐Vorpommern and the NABU. The litter generated here is assessed not only in terms of weight/amounts but also composition. Germany delivers this data to both RSCs pf relevance to our marine waters (HELCOM and OSPAR). *Together with the other leads we will aim for ongoing cooperation to encourage other parties to establish the FFL scheme as well. In OSPAR we have developed guidelines and use a joined logo (developed by KIMO), which could be used and/or developed/modified in HELCOM as well. | N | N | N | N | Sweden has 100% NSF system, also including litter caught during normal fishing activities. SE has joined the Ghost Gear initiative. | N | See action RS6 | N
RE1 | N | N | N | N | N | N | N | N | N | SE has adopted OSPARs´Recommendation 2019/01 on the reduction of marine litter through the Implementation of Sustainability Education Programmes for Fishers, which can be found here: https://www.ospar.org/work-areas/eiha/marine-litter/regional-action-plan | CBD launched an open online training course on marine litter and microplastic pollution in September 2017 and will last till 15 November. CCB contributed to the Out-to-Sea Travelling Exhibition in the Technical Museum (Tekniska Museet) of Stockholm. | N | N
RE2 | N | N | N | N | N | N | N | N | N | N | N | N | N
RE3 | N | N | N | N | N | N | N | N | N | N | N | N | N

## Additional information
CODE OF ACTION | Additional information
RL1 | *Lithuanian: a) National waste management plan for 2014-2020 can be found here: https://www.e-tar.lt/portal/lt/legalAct/TAR.9945210D6571/ZtaLvZPcai b) National waste prevention programme can be found here: https://www.e-tar.lt/portal/lt/legalAct/TAR.09C26B84F785/ejmYyEmdlI c) The Law on Packaging and Packaging Waste can be found here: https://www.e-tar.lt/portal/lt/legalAct/7a5f8dd03c5811e6bcc5c96b48152012. *Swedish revised National Waste Plan and a Waste Prevention Program for the years 2018-2023 under development can be found here: http://www.naturvardsverket.se/Miljoarbete-i-samhallet/Miljoarbete-i-Sverige/Regeringsuppdrag/Reviderad-nationell-avfallsplan/ *Additional information on the Waste Council (“Avfallsrådet”), the Swedish EPA's expert support for waste issues and issues related to sustainable management of materials in society can be found here: http://www.naturvardsverket.se/Miljoarbete-i-samhallet/Miljoarbete-i-Sverige/Uppdelat-efter-omrade/Avfall/Vem-gor-vad/Avfallsradet/ *There are two background reports under progress within Blastic project, one on marine litter sources and one on available methods to monitor marine plastic litter, as well as an identification list of marine litter sources. There will be a questionnaire for pilot municipalities to be filled in with the list of marine litter sources. Subsequently, draft measures for municipalities will be drafted. *DE is to provide updated information on their national PoMs. Propose to change deadline to 2019 in order to benefit from the guidelines produced by the Blastic project. CPs are invited to consider leadership. *Report on the results of the questionnaire on waste management in the Baltic Sea (2019) is available here: https://portal.helcom.fi/meetings/PRESSURE%2011-2019-628/MeetingDocuments/3-7%20Report%20on%20the%20results%20of%20the%20questionnaire%20on%20waste%20management%20in%20the%20Baltic%20Sea.pdf *Accomplishment of actions RL1 and RL3 in the RAP ML (2021) is available here: https://portal.helcom.fi/meetings/PRESSURE%2014-2021-853/MeetingDocuments/3-5%20Accomplishment%20of%20actions%20RL1%20and%20RL3%20in%20the%20RAP%20ML.pdf
RL2 | *LIthuanian wastewater management regulation can be found here: https://e-seimas.lrs.lt/portal/legalAct/lt/TAD/TAIS.276576 *Propose to change deadline to 2019 in order to benefit from the guidelines produced by the Blastic project and also in the view of the HOLAS II assessment. To consider ongoing work on Nordic Council of Ministries, Clean Europe Network (DE to provide contact details), and the Baltic Sea Accelerator. CPs are invited to consider leadership. *Additional information on the Swedish EPA commission (“regeringsuppdrag”) to administer calls for support for cutting-edge technologies and advanced system solutions for sustainable urban development for the years 2016-2019 can be found here: http://www.naturvardsverket.se/Miljoarbete-i-samhallet/Miljoarbete-i-Sverige/Regeringsuppdrag/Mangmiljonsatsning-pa-ny-teknik-for-hallbar-stadsutveckling/
RL3 | *Setälä, O., Suikkanen, S. (eds.): Suomen merialueen roskaantumisen lähteet. Suomen ympäristökeskuksen raportteja 9/2020. 119 pp. (report in Finnish, with an extended abstract in English). https://helda.helsinki.fi/handle/10138/313542
RL4 | *To be included in the Work Plan of PRESSURE WG. PRESSURE to provide feedback on this action. DE to contribute with information. CPs are invited to consider leadership. *Swedish EPA report on the analysis of the state of knowledge and challenges on storm water can be found here: http://www.naturvardsverket.se/Miljoarbete-i-samhallet/Miljoarbete-i-Sverige/Regeringsuppdrag/Redovisade-2017/Analysera-kunskapslaget-for-dagvattenproblematiken/ *Additional information on the Swedish EPA's provision of SEK 25 million in 2018 for measures that reduce pollution and waterborne micro plastics can be found here: http://www.naturvardsverket.se/Nyheter-och-pressmeddelanden/25-miljoner-for-att-minska-fororeningar-och-mikroplaster-i-dagvatten/ *Additional information on the FanpLESStic-sea project can be found here: http://www.helcom.fi/helcom-at-work/projects/fanpLESStic-sea *Proposal to update HELCOM Recommendation 23/5 to be discussed at PRESSURE 12-2020 contained in Annex 3 of the Outcome of the WS RAP ML 4-2019: https://portal.helcom.fi/meetings/WS%20RAP%20ML%204-2019-638/MeetingDocuments/Outcome%20WS%20RAP%20ML%204-2019.pdf
RL5 | *Finnish “Marine litter challenge” competition can be found here: http://www.meriroskahaaste.fi/en-US/. *Finnish development to replace EPS boxes in the fishing and aquaculture industry by board packaging material made of renewable wood fibre can be found here: https://kalaneuvos.fi/en/finnish-ecofishbox-environmentally-friendly-choice-for-fish-products/. *The Plastics Roadmap for Finland: https://muovitiekartta.fi/in-brief/ *Workshop held on 15 June 2018 in Berlin (Germany) organized by HELCOM and the INTERREG BSR project “EcoDesign Circle” (2016-2019, https://www.ecodesigncircle.eu/). The workshop discussed how ecodesign principles, methods, tools, approaches and circular systems can be specified and applied to contribute to the reduction of marine litter in the Baltic Sea Area and which measures and framework conditions can support it. The workshop aimed to identify design solutions optimizing the use of products at the end of their life. *Recommendations and manual of how to change the design of packaging focussing on reuse and recycling by the Danish Forum for circular plastic packaging under the Danish Plastics Federation is available here: https://plast.dk/wp-content/uploads/2018/07/Forum-for-Circular-Plastic-Packaging-recommendations-and-action.pdf and https://plast.dk/wp-content/uploads/2018/07/Design-Manual-Reuse-and-recycling-of-plastic-packaging-for-private-use.pdf
RL6 | *Danish reports available here: http://www2.mst.dk/Udgiv/publications/2015/10/978-87-93352-80-3.pdf http://www2.mst.dk/Udgiv/publications/2017/03/978-87-93529-44-1.pdf *EU report available here: http://ec.europa.eu/environment/marine/good-environmental-status/descriptor-10/pdf/MSFD Measures to Combat Marine Litter.pdf *EU report "Investigating Options for Reducing Releases in the Aquatic Environment of Microplastics Emitted by Products" by EUNOMIA available here: http://www.eunomia.co.uk/reports-tools/investigating-options-for-reducing-releases-in-the-aquatic-environment-of-microplastics-emitted-by-products/ *EU report "Intentionally added microplastics in products" by Amec Foster Wheeler Environment & Infrastructure UK Limited available here: http://ec.europa.eu/environment/chemicals/reach/pdf/39168%20Intentionally%20added%20microplastics%20-%20Final%20report%2020171020.pdf *Finnish Bachelor's thesis available here: https://www.theseus.fi/bitstream/handle/10024/114539/Kilponen_Juho.pdf?se%20quence=1 *Setälä, O., Suikkanen, S. (eds.): Suomen merialueen roskaantumisen lähteet. Suomen ympäristökeskuksen raportteja 9/2020. 119 pp. (report in Finnish, with an extended abstract in English). https://helda.helsinki.fi/handle/10138/313542 *Swedish investigation on sources of micro plastics available here: (i) https://www.naturvardsverket.se/upload/miljoarbete-i-samhallet/miljoarbete-i-sverige/regeringsuppdrag/2016/mikroplaster/swedish-sources-and-pathways-for-microplastics-to-marine environment-ivl-c183.pdf (ii) http://www.swedishepa.se/Environmental-objectives-and-cooperation/Swedish-environmental-work/Government-commissions/Reported-2017/Microplastics/ *Additional information on Swedish financing to address artificial turf pitches and micro plastic particles can be found here: (i) http://www.naturvardsverket.se/Nyheter-och-pressmeddelanden/Ny-vagledning-om-mikroplaster-fran-konstgrasplaner/ (ii) http://www.naturvardsverket.se/Miljoarbete-i-samhallet/Miljoarbete-i-Sverige/Regeringsuppdrag/Redovisade-2017/Mikroplaster--kallor-och-forslag-pa-atgarder-/Bestallargrupp-for-konstgrasplaner *Regular Swedish call for research projects related to micro plastics: http://www.swedishepa.se/Guidance/Research/For-applicants-and-reviewers/Closed-Calls1/Call-for-funding-research-in-the-area-of-Microplastics/ *Summary introduction for the plastic work done by the Swedish environmental protection agency can be found here: http://www.naturvardsverket.se/upload/miljoarbete-i-samhallet/miljoarbete-i-sverige/avfall/avfallsradet/2018/presentation-naturvardsverket-aktuellt-plastarbete.pdf *Technical report of microplastic pollution originating from textiles and paints/coatings by CCB available here: http://www.ccb.se/documents/Postkod2017/CCB_TechnicalReport_MP_textiles_paints.pdf *Norway has released a report on measures to reduce microplastics that maybe can feed in to this action: http://www.miljodirektoratet.no/no/Publikasjoner/2016/April-2016/Primary-microplastic--pollution-Measures-and-reduction-potentials-in-Norway/ *Additional information on the FanpLESStic-sea project can be found here: http://www.helcom.fi/helcom-at-work/projects/fanpLESStic-sea *“Review of existing policies and research related to microplastics” available here: https://helcom.fi/wp-content/uploads/2020/01/FanpLESStic-sea-Microplastics-Policy-and-Research-Review.pdf *“Review of existing policies and research related to microplastics - Summary for policy makers" available here:https://helcom.fi/wp-content/uploads/2020/02/fanpLESStic-microplastics-summary-report.pdf
RL7 | *Projects financially supported by the Danish EPA: a) Evaluating various technologies ability to retain microplastic from wastewater, developing a technology to retain microplastic from wastewater (2015) available here: https://www2.mst.dk/Udgiv/publikationer/2018/05/978-87-93710-29-0.pdf b) Partnership focusing on microplastic pollution in wastewater (2017), available here: https://mst.dk/media/143341/partnerskab-om-mikroplast-i-spildevand-2017.pdf c) Guide on how to handle wastewater from artificial football pitches containing car tire rubber granulates (2018) available here: https://www2.mst.dk/Udgiv/publikationer/2018/05/978-87-93710-25-2.pdf and https://www2.mst.dk/Udgiv/publikationer/2018/04/978-87-93614-99-4.pdf d) Project on developing and testing a filter technology to retain microplastic (2016) available here: https://www.teknologisk.dk/projekter/projekt-udvikling-af-teknologi-til-fjernelse-af-mikroplast-fra-regnvandsbetingede-udledninger/38290 e) Project on developing a technology to retain micro rubber from car tires (2017) available here: http://www.kruger.dk/projekter/udviklingsprojekter/mikroplast.htm *PhD thesis of J. Talvitie “Wastewater treatment plants as pathways of microlitter to the aquatic environment" (2018) available here: https://aaltodoc.aalto.fi/bitstream/handle/123456789/30720/isbn9789526079806.pdf?sequence=1&isAllowed=y *Lithuanian wastewater management regulation can be found here: https://e-seimas.lrs.lt/portal/legalAct/lt/TAD/TAIS.276576 *"Swedish sources and pathways for microplastics to the marine environment - A review of existing data" available here: https://www.naturvardsverket.se/upload/miljoarbete-i-samhallet/miljoarbete-i-sverige/regeringsuppdrag/2016/mikroplaster/swedish-sources-and-pathways-for-microplastics-to-marine%20environment-ivl-c183.pdf *Swedish report: "Advanced wastewater treatment for separation and removal of pharmaceutical residues and other hazardous substances (Report 6803 April 2017)" which section 5 (p.29) provides an assessment of available techniques, can be found here: http://www.naturvardsverket.se/Documents/publikationer6400/978-91-620-6803-5.pdf?pid=21820 *Additional information on the FanpLESStic-sea project can be found here: http://www.helcom.fi/helcom-at-work/projects/fanpLESStic-sea
RL8 | *"Analysis of the degree of the marine environment pollution by wastes flowing down the rivers to the sea, including sanitary waste" (2019) available here: https://portal.helcom.fi/meetings/PRESSURE%2010-2019-549/MeetingDocuments/3-9%20Assess%20the%20importance%20of%20the%20contribution%20of%20upstream%20waste%20flows%20to%20the%20marine%20environment_RL8.pdf *"Guidance on concrete ways to reduce microplastic inputs from municipal stormwater and waste water discharges" by CCB (2017) available here: https://www.ccb.se/documents/Postkod2017/CCB%20-%20Guidance%20on%20concrete%20ways%20to%20reduce%20microplastics%20in%20stormwater%20and%20sewage.pdf *"Analysis of the degree of the marine environment pollution by wastes flowing down the rivers to the sea, including sanitary waste – Updated report and Summary Page of action RL8" available here: https://portal.helcom.fi/meetings/PRESSURE%2012-2020-734/MeetingDocuments/7-11%20Analysis%20of%20the%20degree%20of%20the%20marine%20environment%20pollution%20by%20wastes%20flowing%20down%20the%20rivers%20to%20the%20sea.pdf
RL9 | *Survey of polysterene foam (EPS and XPS) in the Baltic Sea" by Denmark (2019) available here: http://www.helcom.fi/Lists/Publications/Survey%20of%20polystyrene%20foam%20(EPS%20and%20XPS)%20in%20the%20Baltic%20Sea.pdf *"Further steps on prioritized actions addressing expanded and extruded polystyrene (EPS and XPS)" (document 4-6 to PRESSURE 13-2020) available here: https://portal.helcom.fi/meetings/PRESSURE%2013-2020-796/MeetingDocuments/4-6%20Further%20steps%20on%20prioritized%20actions%20addressing%20expanded%20and%20extruded%20polystyrene%20(EPS%20and%20XPS).pdf
RL10 | *"Life Cycle Assessment of grocery plastic carrier bags’ in DK’s supermarkets in 2017" available here: https://www2.mst.dk/Udgiv/publications/2018/02/978-87-93614-73-4.pdf *Finnish Plastic Carrier Bag Agreement, additional information available here: http://www.ym.fi/en-us/The_environment/Waste/Green_Deal_agreements *Lithuanian: a) National waste prevention programme can be found here: https://www.e-tar.lt/portal/lt/legalAct/TAR.09C26B84F785/ejmYyEmdlI b) Law on Packaging and Packaging Waste can be found here: https://www.e-tar.lt/portal/lt/legalAct/7a5f8dd03c5811e6bcc5c96b48152012
RL11 | *Deposit-based return system for beverage packages in Finland can be found here: https://www.palpa.fi/beverage-container-recycling/deposit-refund-system/ *Lithuanian Law on Packaging and Packaging Waste can be found here: https://www.e-tar.lt/portal/lt/legalAct/TAR.9D1ADB9E1518/IvasotGiKK *Information on on-going work between Estonia and Latvia aiming at developing a joint packaging deposit system between these two countries can be found here: https://portal.helcom.fi/meetings/PRESSURE%2010-2019-549/MeetingDocuments/3-7%20Possible%20development%20of%20joint%20packaging%20deposit%20system%20between%20Estonia%20and%20Latvia,%20HELCOM%20RAP%20ML,%20RL%2011_Preliminary%20info.pdf
RL12 | _
RL13 | _
RL14 | *"Follow-up on action RL14 on landfills or dumpsites which may eventually pose a risk to the marine environment" available here: https://portal.helcom.fi/meetings/PRESSURE%2011-2019-628/MeetingDocuments/3-2%20Follow%20up%20on%20action%20RL14%20on%20landfills%20or%20dumpsites%20which%20may%20eventually%20pose%20a%20risk%20to%20the%20marine%20environment.pdf
RL15 | BalticLitter - Litter rim of the Baltic Sea coast: monitoring, impact, and remediation (June 2018- May 2021) available here: https://www.researchgate.net/project/Litter-rim-of-the-Baltic-Sea-coast-monitoring-impact-and-remediation-BalticLitter
RS1 | *ELB (End-of-Life boats) report that collects a best practice -model on recycling of ELB available here: https://portal.helcom.fi/meetings/PRESSURE%2010-2019-549/MeetingDocuments/3-6%20HELCOM%20RAP%20ML,%20RS1%20Development%20of%20best%20practice%20on%20the%20disposal%20of%20old%20pleasure%20boats.pdf *Swedish national project on recycling of pleasure boats by Sweboat, Båtskroten Sverige AB and Stena Recycling AB available here: https://portal.helcom.fi/meetings/PRESSURE%203-2015-278/MeetingDocuments/5-7%20A%20Swedish%20nationwide%20recycling%20system%20for%20end%20of%20life%20boats.pdf *Compiled information on activities and economic incentives aimed at appropriate disposal of ELB (2019) available here: https://portal.helcom.fi/meetings/PRESSURE%2011-2019-628/MeetingDocuments/3-4%20Compiled%20information%20on%20activities%20and%20economic%20incentives%20aimed%20at%20appropriate%20disposal%20of%20End%20of%20Life%20Boats.pdf *Danish report on recycling of fiberglass into traffic shield products (2019) available here: https://www2.mst.dk/Udgiv/publikationer/2016/10/978-87-93529-27-4.pdf *"Policy brief on disposal of End of Life Boats (ELB)" (2020) available here: https://portal.helcom.fi/meetings/HOD%2059-2020-784/MeetingDocuments/6-1%20Draft%20policy%20brief%20on%20disposal%20of%20End%20of%20Life%20Boats%20(ELB).pdf *Accomplishment of actions RS1 (2021) is available here: https://portal.helcom.fi/meetings/PRESSURE%2014-2021-853/MeetingDocuments/3-6%20Accomplishment%20of%20action%20RS%202%20on%20in%20the%20RAP%20ML.pdf
RS2 | *EU "Study to support the development of measures to combat a range of marine litter sources" available here: http://ec.europa.eu/environment/marine/good-environmental-status/descriptor-10/pdf/MSFD%20Measures%20to%20Combat%20Marine%20Litter.pdf *Accomplishment of action RS2 (2021) is available here: https://portal.helcom.fi/meetings/PRESSURE%2014-2021-853/MeetingDocuments/3-6%20Accomplishment%20of%20action%20RS%202%20on%20in%20the%20RAP%20ML.pdf
RS3 | *Setälä, O., Suikkanen, S. (eds.): Suomen merialueen roskaantumisen lähteet. Suomen ympäristökeskuksen raportteja 9/2020. 119 pp. (report in Finnish, with an extended abstract in English). https://helda.helsinki.fi/handle/10138/313542 *Intovuori, V.-V. 2020. Ships’ waste discharge sources and incentives for preventing waste discharges to sea. Master’s Thesis for Marine Engineering/Technology. https://www.theseus.fi/handle/10024/341085
RS4 | *Setälä, O., Suikkanen, S. (eds.): Suomen merialueen roskaantumisen lähteet. Suomen ympäristökeskuksen raportteja 9/2020. 119 pp. (report in Finnish, with an extended abstract in English). https://helda.helsinki.fi/handle/10138/313542 *Intovuori, V.-V. 2020. Ships’ waste discharge sources and incentives for preventing waste discharges to sea. Master’s Thesis for Marine Engineering/Technology. https://www.theseus.fi/handle/10024/341085
RS5 | *Setälä, O., Suikkanen, S. (eds.): Suomen merialueen roskaantumisen lähteet. Suomen ympäristökeskuksen raportteja 9/2020. 119 pp. (report in Finnish, with an extended abstract in English). https://helda.helsinki.fi/handle/10138/313542 *Seppänen, E., Lappalainen, A. 2019. Kalastus ja kalankasvatus muoviroskan lähteenä Itämerellä: RoskatPois! -hankkeen selvitys (in Finnish). Luonnonvara- ja biotalouden tutkimus 9/2019. Luonnonvarakeskus, Helsinki. 28 p. https://jukuri.luke.fi/handle/10024/543823 *"Best practice guide to reduce inputs of cuttings of nets and cord to the marine environment" (2020) available here: https://helcom.fi/wp-content/uploads/2020/10/Best-Practices-to-reduce-marine-litter-from-net-cuttings-waste.pdf
RS6 | *Conclusions of the Marelitt Baltic project, "Baltic Sea Blueprint" available here: https://portal.helcom.fi/meetings/WS%20RAP%20ML%204-2019-638/MeetingDocuments/1-3%20Baltic%20Sea%20Blueprint%20%E2%80%93%20a%20roadmap%20to%20implement%20results%20of%20MARELITT%20Baltic%20project.pdf *Outcome of a regional questionnaire to compile information on national activities regarding ALDFG available here: https://portal.helcom.fi/meetings/PRESSURE%2010-2019-549/MeetingDocuments/3-3%20Revised%20outcome%20of%20the%20regional%20questionnaire%20to%20compile%20information%20on%20national%20activities%20with%20regard%20to%20ALDFG.pdf *Prioritized actions to address ALDFG in the revised RAP ML agreed upon (Annex 2 of the Outcome of WS RAP ML 5-2020) available here: https://portal.helcom.fi/meetings/WS%20RAP%20ML%205-2020-798/MeetingDocuments/Outcome%20WS%20RAP%20ML%205-2020.pdf
RS7 | Chapter 4 of the "EU Study to support the development of measures to combat a range of marine litter sources" available here: http://ec.europa.eu/environment/marine/good-environmental-status/descriptor-10/pdf/MSFD%20Measures%20to%20Combat%20Marine%20Litter.pdf
RS8 | *Setälä, O., Suikkanen, S. (eds.): Suomen merialueen roskaantumisen lähteet. Suomen ympäristökeskuksen raportteja 9/2020. 119 pp. (report in Finnish, with an extended abstract in English). https://helda.helsinki.fi/handle/10138/313542 *Seppänen, E., Lappalainen, A. 2019. Kalastus ja kalankasvatus muoviroskan lähteenä Itämerellä: RoskatPois! -hankkeen selvitys (in Finnish). Luonnonvara- ja biotalouden tutkimus 9/2019. Luonnonvarakeskus, Helsinki. 28 p. https://jukuri.luke.fi/handle/10024/543823
RS9 | PRESSURE 12-2020 agreed that RAP ML action RS9 on dolly rope can be considered accomplished since dolly ropes are not used in the Baltic Sea (document 7-6 and Outcome of PRESSURE 12-2020, para. 7.27), available here: https://portal.helcom.fi/meetings/PRESSURE%2012-2020-734/MeetingDocuments/7-6%20RAP%20Marine%20Litter%20Action%20RS9%20on%20dolly%20rope.pdf
RS10 | Dannish report: "Ghost nets—A pilot project on derelict fishing gear" (2017) available here: http://www.aqua.dtu.dk/english/-/media/Institutter/Aqua/Publikationer/Forskningsrapporter_301_351/323-2017_Ghost-nets-A-pilot-project-on-derelict-fishing-gear.ashx *Final report of the Finnish Kapyysi project (in Finnish): http://sakl.fi/wp-content/uploads/Raportti-Kapyysi_FINAL.pdf
RS11 | *Final report of the Finnish Kapyysi project (in Finnish): http://sakl.fi/wp-content/uploads/Raportti-Kapyysi_FINAL.pdf
RS12 | _
RE1 | CBD open online training course on marine litter and microplastic pollution (September-November 2017) available here: https://ekoagora.pl/plastic-free-baltic/
RE2
RE3

## Lists of codes
Leadership status | Country | Status of implementation | Activities by country
Lead - L | Denmark | On-going | No information reported - N
Co-lead -CL | Estonia | Not initiated
Contributor -C | EU | Accomplished
Reporter - R | Finland
No contribute - NC | Germany
Latvia
Lithuania
Poland
Russia
Sweden
CCB
WWF Poland
Potential contribution from projects