## Status of implementation
CODE OF ACTION | REGIONAL ACTION | FURTHER SPECIFICATION | STATUS OF IMPLEMENTATION | DOCUMENTATION RELATED TO THE STATUS OF IMPLEMENTATION
RL1 | Share best practices and guidelines for municipalities and other responsible authorities regarding environmentally sound and effective cleaning, sorting and collection infrastructure of plastic litter on beaches and other coastal areas. |  | Not initiated
RL2 | Evaluate top findings according to the knowledge available and recommend environmentally sound alternatives to phase out top plastic and rubber litter items. |  | Not initiated
RL3 | Establish a regional pilot project in collaboration with river basin authorities to assess input of macro litter by rivers to build sound regional knowledge base. |  | Not initiated
RL4 | Reduce marine litter by sharing best practices on national return and refund deposit systems for drink packaging striving to establish such systems in all HELCOM countries and investigate possible bilateral and multilateral solutions to prevent littering and enhance recycling of drink packaging in relation to passenger ships and border shops. |  | Ongoing | Final conference of the PACKGDEPO project will take place on 20 April 2023 in Pärnu, Estonia. The results of the project are expected to provide useful input for the implementation of this action. The workshop indicated for May-June in the implementation plan of the action is planned for autumn 2023 as an online event.
RL5 | Identify environmentally open applications using plastics (e.g. agriculture foil, coastal erosion protection, etc...) which need to be addressed and recommend relevant actions. |  | Not initiated
RL6 | Based on the evaluations made in the EU and among the contracting parties of the most significant products and processes that release both primary and secondary microplastics, assess if they are covered or not by legislation, and act, if appropriate, to influence or adjust the legal framework, or identify other necessary measures to reduce emissions to the aquatic environment. |  | Not initiated
RL7 | Evaluate the possibility to introduce regional recommendations to reduce release of microplastics from WWTP utilizing the outcome of related studies. |  | Not initiated
RL8 | Development of a HELCOM guideline on establishment and operation of artificial turfs, to prevent plastic losses, taking into account the ongoing work within the EU including the proposal by ECHA. |  | Ongoing | Starting firstly by designing a survey questionnaire on artificial football fields. The action was briefly presented in the Nordic Football Association’s Infrastructure Conference 7.-9.9.2022, which Finland hosted. Present were infrastructure experts from Norway, Iceland, Sweden, Denmark, Germany and Finland. Compilation of the results from the online survey on artificial football fields has been conducted (April 2023). CCB offered to translate the questionnaire and share it with relevant football associations to get more information and responses. In Germany there are challenges with finding the appropriate contacts due to the federal arrangement and the lack of a general database on artificial football pitches. However, there is already work in progress on football pitches in relation to the environmental certification scheme Blue Angel, which may be of benefit in relation to developing measures on how to approach this topic. Finland and Germany are to liaise bilaterally in this regard. The survey did not consider the afterlife of artificial pitches, but that this may be included in future guidance documents on the matter, as replacing old pitches with new ones typically causes significant pollution.
RL9 | Investigate opportunities for substitution with subsequent phasing-out non-degradable shot wads and launch information campaigns targeted at hunters. |  | Not initiated
RL10 | Provide guidance on best-practice examples and regulatory options for municipalities in the Baltic Sea region to reduce the generation of single use plastic litter. |  | Not initiated | The focus of Germany so far was on finalizing the the Interreg-project CAPonLITTER (Capitalising good coastal practises and improving policies to prevent marine litter, CoL) and implementing a related MSFD measure. The two guidances on Best-Practice examples and regulatory options for municipalities to prevent and reduce plastic litter are now both translated and need final editing before they can be distributed to HELCOM CPs. Results of CoL will be disseminated once the project ends mid-2023.The other steps will then follow.
RL11 | Prevention and reduction of single use plastics consumption and littering at major events and promotion campaigns through the establishment of a catalog of possible measures to be utilized by the organizers and authorities. |  | Not initiated
RL12 | Phase out intentional releases of inflated balloons |  | Ongoing | KIMO International was commissioned to carry out a survey with the aim to get an overview of the problem(s) and possible solutions. The survey gave an estimate of the number of balloons released in the HELCOM area and found on the beaches. The survey listed which (type of) legislation or other approaches the contracting parties have in place and how it is enforced. Based on the results, the authors were to suggest possible ways of phasing out intentional releases of balloons. A final draft was prepared by KIMO international and is pending finalisation (April 2023). In addition to the report, KIMO international has developed communication material to raise awareness of the environmental problems linked to balloon releases. As next steps in relation to actions RL12 and RL13, initiation of drafting guidelines is foreseen.
RL13a | Consider phasing out the use of plastic components of firework and confetti outdoors - section on plastic components of firework |  | Ongoing | The first point of the roadmap for implementation of this action, the investigation for a first impression of the size of problem, has been concluded (April 2023). Work is ongoing on the second point, which is to circualte a survey to gain an overview on the issue of plastic components of firework in the HELCOM area.
RL13b | Consider phasing out the use of plastic components of firework and confetti outdoors - confetti section |  | Ongoing | KIMO International was commissioned to carry out a survey with the aim to get an overview of the problem(s) and possible solutions. The survey gave an estimate of the amount of confetti released in the HELCOM area and found on the beaches, and the environmental impact from confetti litter was described. The survey listed which (type of) legislation or other approaches the Contracting Parties have in place and how it is enforced. Based on the results, the authors were to suggest possible ways of phasing out intentional releases of confetti. A final draft was prepared by KIMO international and is pending finalisation (April 2023). In addition to the report, KIMO international has developed communication material to raise awareness of the environmental problems linked to confetti. As next steps in relation to actions RL12 and RL13, initiation of drafting guidelines is foreseen.
RS1 | Identify opportunities for developing ELB management and recycling methodologies including potential financial arrangements (e.g. producer´s responsibility, eco-fee for registered boats). |  | Not initiated | MARITIME is to contribute to the implementation of this action. There is a Finnish project on end-of-life boats, which is expected to commence soon and conclude before the end of 2023. The implementation plan of RS1 is to be reviewed in 2024, as appropriate, based on the outcome of the project.
RS2 | Encourage the development and use of buoys, floats and docks, which do not release expanded polystyrene (EPS) and other problematic materials to the marine environment with the aim to phase out the use of those containing unprotected EPS and problematic materials. |  | Not initiated
RS3 | Cooperate with maritime stakeholders to optimize onboard waste management enhancing separation, fostering recycling, and phasing out the use of single-use plastics in shipping, including in cruise operations. |  | Not initiated | MARITIME is to contribute to the implementation of this action.
RS4 | Investigate the problem with cargo losses causing plastic littering of the marine environment and, based on the findings, together with national competent authorities, consider developing a common guidelines for accident management taking into account ongoing work within the IMO and EU. |  | Not initiated | MARITIME is to contribute to the implementation of this action.
RS5 | Investigate the problem caused by spills of plastic pellets from ships and, based on the findings, consider developing common guidelines for accident management in such events. |  | Ongoing | Step 1) Assessment report on acute plastic pollution in the Nordic Countries. The report will describe preventive measures, emergency responses, experiences from clean-up operations, relevant regulation, and other legal aspects. The roles of authorities and other actors, organisation at national/regional level, and cooperation between countries. Through procurement, financed by NMR, KIMO has started with this part. MARITIME is to contribute to the implementation of this action.
RS6 | Encourage collection of ALDFG and separation of collected ALDFG from end-of-life gear with a view to establish regional targets for collection of end-of-life fishing gear. |  | Not initiated | An online workshop is to be organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12).
RS7 | Elaborate guidelines on the best practices and undertake relevant measures to reduce the input of ALDFG to the Baltic Sea from recreational fisheries with a focus on gillnets taking into account geographical particularities. |  | Not initiated | An online workshop is to be organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12).
RS8 | Evaluate the amounts and composition of lost angling gear in the Baltic Sea including fishing lures and casting weights with corresponding hooks, soft plastic baits and light components and develop appropriate measures to prevent their further loss. |  | Ongoing | 1) A study on the amounts and composition of lost fishing gear – traps, pots and handheld fishing gear including fishing lures, baits, casting weights with corresponding hooks, fishing lines and light components from recreational fishing in the Nordic countries – in order to develop appropriate measures to prevent their further loss. Finalized and will be published in the near future. 2) Depending on the results of the Nordic study, further studies of the amount of lost fishing gear must be carried out in the countries not included in the Nordic study. The procurement is complete so that the study can proceed, and it is expected to be completed in Q1 2023. The Swedish contact person for the report has changed jobs and that therefore further progress on this action is not to be expected during the next couple of months (April 2023).
RS9 | Investigate available options for fishing gear marking as a tool to prevent and reduce gear losses and produce recommendations to improve gear marking to increase the effectiveness of this tool |  | Not initiated | An online workshop is to be organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12). Developments regarding the marking of fishing gears will be discussed at IMO PPR 10 in April 2023. Gear marking is also being considered at FAO and OSPAR, and these developments are to be considered in the further work.
RS10 | Consider innovative constructive features of fishing gear as a tool to prevent and reduce gear losses and a tool to prevent and reduce lost fishing gears from ghost fishing. |  | Not initiated | An online workshop is to be organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12). Denmark is participating in a similar action in OSPAR, which implementation will commence this year.
RS11 | Continue the mapping of areas with high potential for ALDFG accumulation (hot spots) in all HELCOM countries with subsequent update of the HELCOM Map&Data service. |  | Not initiated | An online workshop is to be organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12).
RS12 | Initiate removal of ghost nets and their safe management on land applying the best practices for ALDFG removal in national or international campaigns. |  | Not initiated | An online workshop is to be organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12).
RS13 | HELCOM to join the Global Ghost Gear Initiative (GGGI) which is the world’s largest cross-sectoral alliance committed to driving solutions to the problem of ALDFG worldwide. |  | Not initiated | The Secretariat is to initiate the implementation of this action RS13 (April 2023).
RS14 | Engage fishermen (both recreational and commercial) and general public to report on lost and observed ghost fishing gear utilizing related reporting tools (e.g. Swedish example of GhostGuard app or German Geistertaucher). |  | Ongoing | Accomplished: • WWF GhostDiver App online and ready to compile different data sources connected to verified ghost gear positions • In the BMUV founded program until March 2023: For Germany, Poland, Estonia = 320 potential ghost gear positions, of which 105 positions are already verified by divers and 98 net findings are already retrieved in several programs (executed e.g. by the Federal State Mecklenburg-Vorpommern). Ongoing (numbering related to the steps foreseen in the implementation plan): 2 Connection to Sweden, Estonia and Poland exist; 4 Reach out to Norwegian Experts 5.1 WWF Workshop in Poland; 5.2 UBA Workshop in Germany scheduled for May 15th, 2023;
RS15 | Consider the development of HELCOM Recommendation and guidelines on the reduction of marine litter through the implementation of Sustainability Education Programmes for Fishers taking into account results of the ongoing work on the revision of IMO STCW-F. |  | Not initiated

## Leadership by country
LEADERSHIP
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden | CCB | WWF Poland
RL1
RL2
RL3
RL4 |  | Lead
RL5
RL6
RL7
RL8 |  |  |  | Lead | [5 empty] | Co-lead
RL9 | Lead
RL10 |  | Co-lead |  |  | Lead
RL11 | Lead | Co-lead
RL12 | Lead | [8 empty] | Co-lead
RL13 |  |  |  |  | Lead the section on plastic components of firework |  |  |  |  | Lead the confetti section
RS1
RS2 | Lead
RS3 |  |  |  | Lead
RS4
RS5 | [9 empty] | Lead
RS6
RS7
RS8 |  |  |  |  | Considering co-leading |  |  |  |  | Lead
RS9
RS10
RS11
RS12
RS13
RS14 |  |  |  |  | Lead
RS15

## Additional information
CODE OF ACTION | ADDITIONAL INFORMATION
RL1
RL3
RL4 | PACKGDEPO project - Bottles reject borders!: https://milttonevents.smai.ly/browser/-8rCD8Bg2w1rY87HfES--UaWiZE8ZRZ5cMEzw4dntsGr68vTvlDsK5eGmEEvo2M0sMNArbl7kTSSbJxnOFz9j6pGFFthwslip1W7X1hR_C_VnGqG4IVhcuplPWIZSJ68QvwdNZsIhDQRKiW_Ccgdug,,/
RL5
RL6
RL7 | CCB launched a series of activities on addressing the microfiber pollution from textiles and solutions on the whole life cycle of textile. Keep Fibers Zipped campaign aimed at developing a trend to reduce microplastic pollution from textiles with the help of existing consumer and production, technological and behavioral solutions was launched. Main activity of the campaign is the development of the report and a case study of available solutions in the Baltic Sea region and the world related to microfiber pollution from textile. The draft report is ready with contribution of experts from CCB MOs and partner organizations. It consists of cases of solutions in the BSR and world on different stages of microfibers leakage and covers different actors (regulation, waste water treatment plants, circularity for textiles, production of the cloths and fabrics, devices for catching microfibers and behavioural practices for the consumers). Release of the report is planned in second quarter of 2023.
RL8
RL9
RL10
RL11
RL12
RL13
RL14
RS1
RS2
RS3
RS4
RS5
RS6
RS7
RS8
RS9
RS10
RS11
RS12
RS13
RS14 | Re:Fish project working on recreational fishing gear under the leadership of Sweden: https://centralbaltic.eu/news/31-regular-projects-approved-for-funding/
RS15