## Sheet1
Approved via correspondence in September 2023 by the Heads of Delegations of the EU and the Contracting Parties to HELCOM that are also Member States of the EU
No | Type of action | BSAP Action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline] | Comments
Theme: Baltic Sea biodiversity and ecosystem
Topic: Red List
1 | Joint | B22 | Update the HELCOM Red List Assessments by 2024, including identifying the main individual and cumulative pressures and underlying human activities affecting the red listed species. | RED LIST II | WG BioDiv | EG MaMa JWG Bird; EG Benthic; [EG Coastal Fish] |  | To be implemented under the RED LIST II project (2022-2024). | By end of 2024 Red list assessment and supporting information (data, species information sheets etc) is published and publicly available.
2 | Joint | B28 | Update the HELCOM Red List Assessments by 2024, including identifying the main individual and cumulative pressures and underlying human activities affecting the red listed biotopes and habitats | RED LIST II | WG BioDiv | EG Benthic |  | To be implemented under the RED LIST II project (2022-2024). | By end of 2024 Red list assessment and supporting information (data, species information sheets etc) is published and publicly available.
Topic: Habitats and Biotopes
3 | Joint | B31 | Identify by 2022 data needs for spatial pressure and impact assessment of human activities, including cumulative impacts, and implement by 2024 at latest methods for mapping and assessment of adverse effects on the ecosystem of human activities in the Baltic Sea region. | HOLAS 3 | WG BioDiv | - | ReMap project | Implementation started under HOLAS 3. Spring 2023: WG to consider list of existing component, activity and pressures layers and provide initial input. Autumn 2023: Data and infrastructure needs to be reviewed as part of the review of HOLAS 3. 2024: Long-term dataflows and infrastructure established with CPs. | Data needs for spatial pressure and impact assessment of human activities, including cumulative impacts, are identified by 2022. Data needs for spatial pressure and impact assessment of human activities, including cumulative impacts, are addressed and long term dataflow plans have been established by 2024. Latest improved methods for mapping and assessment of adverse effects on the ecosystem of human activities in the Baltic Sea region are implemented and results made publicly available by 2029.
4 | Joint | B32 | Update the HELCOM Underwater biotope and habitat (HUB) classification where gaps have been identified by 2024, and by 2025 develop a fully functioning translation matrix between HUB, Marine Strategy Framework Directive (MSFD) broad habitat types, Habitats Directive habitats and the European Nature Information System (EUNIS), in co-operation with the European Marine Observation and Data network (EMODnet). | RED LIST II, PROTECT BALTIC | WG BioDiv | - | TG SEABED | 2022-2024: Resources for updating the HUB classification have been secured under the RED LIST II project and initial communication with the consultant established. Work on the translation matrix is included under the PROTECT BALTIC project and, will be ready by end of 2025. | By 2024 gap analysis for HELCOM HUB-classification scheme has been performed. By 2024 HELCOM HUB-classification is updated, where gaps have been identified. By 2025 a fully functioning translation matrix between HUB, MSFD broad habitat types, HD habitats and EUNIS is developed
Topic: Enabling ecosystem based management
5 | Joint | B33 | By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). | WG GEAR | WG GEAR | WG BioDiv, WG Sea-based activities, WG Source to Sea |  | 2023-2024: Support the review and gap analysis following HOLAS 3, looking at both the policy and the technical aspects of the inclusion, and assessment, of biodiversity and ecosystems, as well as the working structure and process. Based on this review, identify and prioritize work to be done with respect to biodiversity and ecosystems under the preparatory phase for HOLAS 4 and prepare corresponding workplans to target the gaps and ensure work progresses. Spring 2023: plan for the review process presented and considered. Information harvesting started from existing sources. Post HOLAS 3-survey drafting started. Autumn 2023: post HOLAS 3-survey made available, information harvesting and catergorazing finalised from existing sources. Spring 2024: survey results analysed and merged with exisiting information, Workshops arranged to review material and provide policy prioritisation and technical review and prepare topical workplans for furhter development, which togeter form the roadmap. 2023-2024: ensure that there are Expert Groups established to support the indicator and assessment methodology development for those topics where no such support currently exists. Spring 2023: overview of linkages between biodiversity topics and EGs presented and considered. | By 2024 a Roadmap for how to fill gaps for both ecosystem components and pressures is developed. By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available
6 | Joint | B34 | Develop core indicators, and threshold values to evaluate the status of food webs by 2026, where applicable, and implement a holistic assessment of food webs no later than 2030. | [EG Foodweb] | WG BioDiv | - | Upcoming EU Foodweb group? | 2023/2024: review and gap analysis following HOLAS 3 and development of a workplan for the development work towards HOLAS 4, to be reviewed and approved by WG. | By 2026 a minimum of one indicator has been established with an agreed threshold value to evaluate the status of food web in a holistic way. By 2030 a holistic assessment of food webs is available. | This work has been started in HOLAS 3, however it seems likely that rather than indicators a more useful approach long term will be a foodweb assessment methodology. It would be relevant to formalize the EG FOODWEB to ensure long term support for the development and assessment
7 | Joint | B35 | By 2024 operationalize a set of indicators for the assessment of fish population health, including size and age distribution, where applicable, and, by 2029, for any remaining relevant species. | [Sweden] [EG Coastal fish] | WG BioDiv WG | WG GEAR, WG Fish | S40 (WG Fish), S48 (WG Fish), possible ongoing work within ICES? | 2023/2024: Invite FISH Pro to perform a review and gap analysis following HOLAS 3, and development of a workplan for the development work towards HOLAS 4. To be reviewed and approved by WG. 2023/2024: secure agreement amongst CPs on how to address commercial fish. 2024-: implement workplans (if possible with the support of external funding). | By 2024 indicators for the assessment of fish population health are available, including indicators for size and age distribution. By 2029 health, size and distributional indicators are available for all relevant species | This work started under HELCOM BLUES project and HOLAS 3.
8 | National/Joint | B15 | […] regularly assess the state of the coastal fish community through selected coastal fish species and groups, including threatened species, by at latest 2023.[…] | [Sweden], [EG Coastal fish] | WG BioDiv | WG Fish | - | Coordinated assessment methods are being progressed under FISH Pro as part of the work for HOLAS3 and the coastal fish assessments. | By 2023 assessment, presenting information in a format that contributes to the effective implementation of measures is ready and publicly available. (Joint supporting action). Interval for the next assessment is agreed by 2023. (Joint supporting action Where ecologically relevant, data and assessment of coastal fish is available by 2023 for the full distribution of the species, at a resolution suitable for management and the implementation of measures. (Joint supporting action. By 2027 appropriate management measures have been implemented with the ambition to maintain or improve the status of coastal fish species. (National measure)
9 | Joint | S67 | Define the characteristics of benthic habitats, develop core indicators and undertake an integrated assessment of the status of benthic habitats, including their structure, function, […] leading to the identification of measures to reduce adverse effects where needed. Work should be done in close cooperation with work undertaken by Contracting Parties in other relevant fora, taking into account activities in EU Technical Group on seabed habitats and sea-floor integrity (TG Seabed), and considering the ICES advice on a sea-floor assessment process. | Indicator leads | WG BioDiv | WG Sea-based pressures, EG Benthic, EG Dreds | EU TG Seabed, ICES | 2023/2024: review and gap analysis following HOLAS 3, specifically with regards to structure and function of seabed habitats, and elaboration of a workplan for the development work towards HOLAS 4. 2024/2025: elaborate proposed measures for reducing adverse impact on the structure and function of seabed habitats, towards the MM planned for 2026. | By 2023 characteristics of benthic habitats have been defined. By end of 2023 HELCOM indicators evaluating the status, structure, function and distribution of benthic habitats has been developed and operationalized. By 2023 HELCOM indicator evaluating the extent of loss of benthic habitats has been developed and operationalized. By end of 2023 assessment of benthic habitats has been undertaken. By end of 2025, where needed measures to reduce adverse effects have been identified. Relevant new measures adopted by Ministerial Meeting in 2026 | This work is ongoing under HOLAS 3. The work on indicators and assessment of distribution and extent of loss and disturbance is primarily done under WG SEABED. EG DREDS to follow up and to provide comments during the process when needed.
10 | NA |  | Collate available information on and define “favourable conservation status” (e.g. threshold value) for harbour porpoise, considering also IUCN red-list criteria. | Harbour porpoise team under EG MaMa | WG BioDiv |  | ASCOBANS Jastarnia Group | 2023/2024: review and gap analysis following HOLAS 3, and elaboration of a workplan for the development work towards HOLAS 4. 2024: Definition of favorable conservation status established. To be linked to ongoing work under the ASCOBANS Jastarnia Group 2024/2027: Harbour porpoise team and indicator leads executing workplan, with guidance from BIODIV. | By end of 2024 favorable conservation status agreed. By 2027 threshold values and operational indicators established for all populations. | Work started in 2019 under EG MaMa, and initial values proposed under the HOLAS 3 process in 2022.
11 | Joint | B10 | Include information on functional and life history traits for the species in the HELCOM Biodiversity Database, by 2024. | PROTECT BALTIC | WG BioDiv | - |  | 2023-2028: PROTECT BALTIC will progress the work, in close cooperation with the lead (collecting trait information and updating the Biodiversity database)] | By end of 2024 trait information has been added for the species listed in the HELCOM Biodiversity database, wherever possible.
Theme: Protection
Topic: Spatial protection measures
12 | National/Joint | B1 | By 2030 at the latest, establish a resilient, regionally coherent, effectively and equitably managed, ecologically representative and well-connected system of HELCOM marine protected areas (MPAs), supported by those other spatial conservation measures, under alternative regimes for marine protection, which can contribute to the coherence of the network. Where scientifically justified, special attention should be given to offshore areas beyond territorial waters. The network of marine protected areas will: - cover at least 30% of the marine area of the Baltic Sea, of which at least 1/3 will be strictly protected. Other Effective Area-based Conservation Measures (OECMs) could be counted towards the 30% targets only if they, as a minimum, comply with the OECM criteria agreed by the Convention on Biological Diversity (CBD). - where scientifically justified, consider including no-use zones within marine protected areas, which can also serve as scientific reference areas. - expand conservation efforts to actively include areas of particular importance for biodiversity and ecosystem resilience, including important ecosystem elements such as species or areas recognized to be ecologically significant based on function for the ecosystem/provisioning of ecosystem services and broad habitat types, but which may not necessarily be rare or threatened. | Finland/PROTECT BALTIC | WG BioDiv | - | HT13 (HELCOM-VASAB MSP WG), HT14 (HELCOM-VASAB MSP WG), CBD targets, EU Biodiversity Strategy, upcoming Nature Restoration Law. | 2023-2028: PROTECT BALTIC will progress the task using the project as a platform, but in close cooperation with BIODIV WG. 2023: start work on establishing a regional MPA framework by establishing an agreed process, followed by scoping goals. 2024: Negotiate and establish regional conservation objectives and targets. | By the end of 2030 the HELCOM MPA network is resilient. By the end of 2030 the HELCOM MPA network is regionally coherent. By end of 2030 the HELCOM MPA network is effectively and equitably managed. By end of 2030 the HELCOM MPA network, together with OECMs complying with the CBD criteria, covers at least 30% of the marine area of the Baltic Sea. At least 1/3 of the area covered by the HELCOM MPA network is strictly protected. (Joint measure) (2030) Conservation efforts target and include areas of particular importance for biodiversity and ecosystem resilience, irrespective of threat status, as outlined in the action. (National measure) (2030)
13 | NA |  | Review, and possibly revise, the HELCOM Recommendation 35/1 | Finland, supported by Sweden | WG BioDiv | - | PROTECT BALTIC | 2023: submit the proposal to open the Recommendation for approval to HoDs. | By 2028 reviewed and possibly updated Recommendation adopted.
2024/2027: [in close cooperation with PROTECT BALTIC] elaborate the needed revisions, reporting requirements, structures intervals etc.
2027: Submit the updated Recommendation to HOD for approval.
2028: Adoption of new Recommendation at HELCOM
14 | National/Joint | B2 | [By 2022 come to a common understanding of the Other Effective Area-based Conservation Measures (OECMs) criteria and their use in HELCOM, based on definitions agreed in the Convention on Biological Diversity (CBD) and the EU], and define how OECMs can support the coherence of the Baltic Sea marine protected area (MPA) network. [By 2025 identification of OECMs in the Baltic Sea region.] | PROTECT BALTIC for how OECMs can support the MPA network | WG BioDiv | HELCOM-VASA MSP WG | - | 2023-2028: PROTECT BALTIC will progress work on the second half of the action (defining how OECMs can support the coherence of the Baltic Sea marine protected area (MPA) network) | Common understanding to be approved by IC HOD 2-2022 and adopted by HELCOM in 2023. (Joint) | Started in February 2022. 2022: Refine the common understanding, cross reference with information from the EU. Autumn 2022: Outline and include in the common understanding initial guidance on how OECMs can/should contribute to securing the conservation objectives of MPAs. IC STATE & CONSERVATION 2-2022 considered the further developed common understanding and decision support tree for identifying measures with the potential to function as OECMs and recommend submission to HODs. Submitted for adoption to HELCOM in 2023.
By 2025 OECMs have been identified for the Baltic Sea region. (National)
15 | NA |  | Update the national information in the MPA database. | PROTECT BALTIC/CPs | WG BioDiv | - | - | 2023-2028: PROTECT BALTIC will improve database functionality and reporting, preparing reporting manuals, collating MPA specific information, translating it and populating the database. | By 2024 updated national information on MPAs included in the database and available for use.
[8 empty] | 2024: CPs to review and update national information in the MPA database. | By 2028 new MPA database with improved functionality ready and publicly available
16 | NA |  | Update and expand the MPA database. Produce guidance for using and updating the MPA Database. | PROTECT BALTIC | WG BioDiv | - | - | 2023-2028: PROTECT BALTIC will updated the database platform and the functionality of the data base, draft a manual for its use and collate and populate the database with updated MPA information. | By 2028 improved functionality and accessibility of MPA information for region.
By 028 facilitate reporting to the database.
17 | National/Joint | B6 | The coherence of the marine protected area (MPA) network will be periodically assessed at least every ten years, with the next such assessment to be carried out by 2025. By 2027 the results from the coherence assessment are to be used to take appropriate actions to ensure conservation and resilience of biodiversity, and to identify possible spatial conservation expansion needs to improve coherence. | PROTECT BALTIC/Sweden | WG BioDiv |  | - | 2023-2028: PROTECT BALTIC will be improving and implementing the assessment of MPA coherence and guidance on the expansion of spatial conservation. | The assessment of coherence of HELCOM MPAs is completed by 2025. (Joint supporting action)
[8 empty] | Autumn 2023: scope the need for improving the assessment methodology, as well as establish data requirements. | Possible spatial conservation expansion to improve coherence are identified by 2027. (National measure)
[8 empty] | 2024: Methodology development, publication of data call, data collation. | The HELCOM MPA network is fully coherent including with respect to adequacy, connectivity (incl. migration), replication and representativity, taking into account the changing climate, in 2030. (Joint measures)
2025: run assessment, analysis of results and finalizing report.
2027-2030: Once the assessment is available the WG is to share information on how CPs are taking action to improve coherence.
18 | NA |  | Concretize how the MPA network are and/or could contribute to mitigating the effects of climate change. | PROTECT BALTIC | WG BioDiv | - | climate change fact sheet (EN Clime), ecosystem service work (EG ESA, HOLAS) | 2023-2028: PROTECT BALTIC will work with ecosystem service provisioning, species distribution under various climate scenarios, resilience proxies. | By 2028 present clear indication of the current and future potential of MPAs to contribution to mitigation of the effects of climate change (type and magnitude of contribution).
19 | NA |  | Improve the understanding of the role of MPAs for ecosystem services, in order to enhance cost-effectiveness of MPAs management and yield the greatest environmental benefits. | PROTECT BALTIC | WG BioDiv | - | MSP4BIO, BLUE4All | 2023-2028: PROTECT BALTIC and BLUE4All will progress the work on ecosystem service provisioning, distribution and valuation. | By 2028 provide clear indication of current and future potential of MPAs to contribution to provisioning of ecosystem service (type and magnitude of contribution), as well as the value associated with the services.
Topic: Management of spatial protection
20 | National/Joint | B3 | By 2030 strengthen the management of the Baltic Sea marine protected area (MPA) network by introducing key elements into management efforts, including but not limited to those highlighted here, to increase effectiveness of protection, including by providing support to Baltic Sea MPA managers through capacity building e.g., through annual workshops. By 2023 update, and by 2025, apply HELCOM MPA management guidelines with focus on: | PROTECT BALTIC/Germany | WG BioDiv | - | S64 (WG Sea-based pressures) S42 (WG Fish), S47 (WG Fish), S54 (WG Fish), S57 (WG Seabased) | [2023-2028: If the PROTECT BALTIC project is funded this work will be progressed using the project as a platform, but in close cooperation with BIODIV WG. Due to a necessary change in the timeline for the work under the PROTECT BALTIC project the target year for updated Management Guidelines will not be met, however work will be underway.] | 2023 workshop for MPA managers carried out, contributing to building capacity.
|  |  | a) Assessments and evaluation methodology and structures for management effectiveness; |  |  |  |  | Autumn 2022: find a host and begin the planning of the 2023 MPA managers network capacity building WS. | 2024 workshop for MPA managers carried out, contributing to building capacity.
|  |  | b) Setting quantitative conservation objectives; |  |  |  |  | Autumn 2023: find a host and begin the planning of the 2024 MPA managers network capacity building WS. | By 2023 the HELCOM Guidelines for MPA Management are updated.
|  |  | c) Effective conservation measures that reduce pressures; | [5 empty] | By 2025 the HELCOM MPA Management Guidelines are applied.
|  |  | d) Establishment of indicators to monitor management performance and status of conservation features; | [5 empty] | By 2030 improved key elements are introduced into MPA management to increase the effectiveness of protection.
e) Establishment of a common monitoring strategy and evaluation of conservation features and pressures;
f) Adaptive management.
21 | NA |  | Establish coordination mechanisms for management of pressures and impacts on MPAs, in particular for adjacent transnational MPAs |  | WG BioDiv | - | PROTECT BALTIC | Spring 2024: Working group to scope needs and requirements for a coordination mechanism and prepare a proposal. | By end of 2024: Clear next steps agreed and included in next WP update. | Use the document submitted to IC S&C 2-2022 as a starting point to identify where/for what Contracting Parties adjacent transnational MPAs are relevant. In the absence of PROTECT BALTIC the use of the SPIA tool can be explored.
[8 empty] | Autumn 2024: include an agreed way forward in the Work plan updated. | By 2027: Transnational coordination mechanism established
2023-2028 PROTECT BALTIC project will produce regional overviews of the spatial distribution of pressures and impacts inside and outside of MPAs, as well as divide pressures into direct and indirect, directing how to these should be handled, as well as provide impact analysis for the various ecosystem components existing in and/or included in the conservation objectives of the MPAs (both adjacent transnational ones and others)
22 | NA |  | Increase capacity for developing multi-management plans for marine protected areas. | PROTECT BALTIC | WG BioDiv | - | - | Autumn 2024: Arrange a MPA managers capacity building WS on the process, experiences and best practices of developing multi-management plans. | By end of 2024: Based on a targeted workshop for the MPA managers network, increased familiarity with the development and establishment process.
[8 empty] | 2023-2028 PROTECT BALTIC: Include guidance on developing multi management plans in the update of the HELCOM MPA management manual | By end of 2024: Based on a targeted workshop for the MPA managers network, established connections between managers and experienced practitioners.
By end of 2028: Chapter on multi management plans in the update of the HELCOM MPA management manual.
23 | NA |  | Collate and provide information on how to consider nature conservation needs, ecologically significant areas (also outside the protected areas) and ecosystem function in Maritime Spatial Planning and vice versa. |  | WG BioDiv | HELCOM-VASAB MSP WG | MSP4BIO, eMSP | 2023: Scoping workshop jointly with MSP practitioners to identify a common language and shared objectives as well as concrete areas and formats of cooperation (MSP4BIO and eMSP). | By end of 2023: an initial scoping WS on future work and common language has been arranged.
2023-2028: PROTECT BALTIC will prepare biodiversity distribution maps, ecosystem service distribution maps, connectivity analyses etc which are of high relevance for MSP.
Topic: Conservation of species
24 | Joint | B24 | Develop tools for, and regularly assess, the effectiveness of other conservation measures for species, besides marine protected areas (MPAs), the first assessment to be done by 2025 as well as assess effect on species through risk- and status assessments by 2029. |  | WG BioDiv | JWG Bird, EG MaMa, [EG Coastal Fish] | - | Autumn 2023: Dedicated session to identify what other conservation measures are available. Using the Habitats Directive list of conservation measures, removing the spatial measures, as a basis. | By end of 2023: Overview of available other conservation measures prepared.
[8 empty] | 2024: Explore how to best combine the assessment of effectiveness of other conservation measures with MPAs and develop methodology/tools. | By 2025: tools for assessment of effectiveness of conservation measures for species, other than MPAs, have been developed.
[8 empty] | 2025: run the assessment and prepare report. | By 2025: the first assessment of effectiveness of other conservation measures for species, besides MPAs, is ready and publicly available.
By 2029: the effect of conservation measures for species, other than MPAs, on species has been evaluated through risk- and status assessments.
25 | National/Joint | S52 | Define necessary complementary measures by 2024 in relevant [environmental] policy areas to improve the size/age structure for fish stocks, including cod. |  | WG Fish | WG BioDiv | ICES, BaltFISH, BSAC | In 2023: Define what species are to be targeted, jointly with FISH WG (2023). | By end of 2024: Complementary measures are defined and can be implemented, in order to improve size/age structure, to reach healthy fish stocks. | FISH 14-2022: A lead is needed to further the fisheries part of this action. It is proposed that both FISH and STATE&CONSERVATION oversee this action, as the complementary measures to be defined are expected to stem from the areas of responsibility of both groups. DK comment following FISH 14-2022: Work on regionally important species is best carried out by ICES.
2024: Identify a selection of effective and efficient measures (i.e. best practices) for improving status of fish stocks. Where relevant these should eventually be included in the HELCOM Restoration Action Plan.
Topic: Protection of birds
26 | Joint | B11 | Maintain an updated map of the sensitivity of birds to threats such as wind energy facilities, wave energy installations, shipping and fisheries. Complete, as a first step, the mapping of migration routes, staging, moulting and breeding areas based on existing data by 2022. By 2025 further develop these maps by incorporating new data, post-production investigation information and addressing the subject of cumulative effects from these activities in space and time. | [Germany], EG Birdmove | WG BioDiv | HELCOM-VASAB MSP WG |  | 2022 onwards: Information on wind energy facilities, wave energy installations, shipping and fisheries will be collated under various HELCOM projects, including HOLAS and work to update BASEMAPS. | By 2023 there are publicly available bird maps that include staging areas, migration routes and where possible migration densities, sensitivity, as well as overlap with possible threats exists, including information on confidence and uncertainty.
[8 empty] | 2023: EG BIRD MOVE to review of pressures list (as included in the action), addition of any other relevant pressures. EG BIRD MOVE to produce initial prioritization of species most sensitive to the identified pressures and expert based sensitivity scoring across species and pressures and submit to WG BioDiv for review. | Bird sensitivity maps are regularly updated in line with the action, the first update to be ready by 2025.
2023: EG BIRD MOVE to collate relevant information such as timing/drivers of migration, flight altitude and determinants, breeding and feeding behaviour etc for the relevant species, and submit to WG BioDiv for review.
Autumn 2023: Jointly with EG BIRD MOVE, prepare data call on collating spatial information on migration routes, staging, moulting and breeding areas based on existing data
Autumn 2023: Nationally coordinate the data delivery for the data call on collating spatial information on migration routes, staging, moulting and breeding areas based on existing data, results to be processed under EG BIRDMOVE.
Topic: Protection of mammals
27 | National/Joint | B8 | By 2022 at the latest, specify knowledge gaps on all threats to the Baltic Proper harbour porpoise population, and by 2023 for the western Baltic population, including by-catch and areas of high by-catch risk, underwater noise, contaminants and prey depletion. Knowledge gaps related to areas of high by-catch risk are to be addressed and by 2028 at the latest additional areas of high by-catch risk for both Baltic Sea populations are to be determined. To strengthen Baltic harbour porpoise population, by 2025 identify possible mitigation measures for threats other than by-catch and implement such measures as they become available. | Poland, [WWF] [Sweden] | WG BioDiv | EG MaMa, EG Noise, EG Haz (biological effects), WG Fish | S43 (WG Fish), S44 (WG Fish), S45 (WG Fish), S46 (WG Fish), S47 (WG Fish), S48 (WG Fish), ASCOBANS Jastarnia Group | Early 2023: Leads to prepare initial list of gaps. HOLAS 3 can contribute with information on knowledge gaps for harbour porpoise assessment (in indicator reports and thematic assessment). | By 2023 knowledge gaps on all threats to the Baltic Proper harbour porpoise population have been specified and listed. | Priority (no direct support for implementation identified). Could be supported by a SAMBAH project (or similar).
[8 empty] | Spring 2023: Invite CPs and EG MaMa harbour porpoise team to provide knowledge gaps to the spring meeting of BIODIV. Invite ASCOBANS/Jastarnia group to provide input to the same meeting. | By 2023 knowledge gaps on all threats to the western Baltic population have been specified and listed.
By 2025 possible mitigation measures are identified and implemented as they become available. (National measure)
By 2028 knowledge gaps related to areas of high by-catch risk are addressed.
By 2028 year, at the latest, additional areas of high by-catch risk for both Baltic Sea populations have been determined.
Topic: Protection of habitats and biotopes
28 | Joint | B25 | Map ecosystem services and the present and potential spatial distribution of key ecosystem components, including habitat forming species such as bladder wrack, eelgrass, blue mussel and stoneworts Baltic-wide, by 2025. | PROTECT BALTIC/EG ESA | WG BioDiv | WG GEAR, EG ESA, EG Benthic | Possibly MSP4BIO and BLUE4ALL | 2023-2028: PROTECT BALTIC project, will develop a multi-use methodology for identification, mapping and quantification of ecosystem services Exploration of ecosystem component quality and location for upscaling of ecosystem services and spatial overlaps of ecosystem services and human activities | By 2025 a regional list of ecosystem services connected to key ecosystem components as well as spatial distribution of these ecosystem services is publicly available.
By 2025 regional maps presenting current and potential distribution of key ecosystem components are prepared and publicly available.
29 | National/Joint | B26 | Protect key ecosystem components including habitat forming species by 2030, by: - assessing the state of, and threats to these key ecosystem components by 2023 |  | WG BioDiv | WG Sea-based pressures, EN Clime, HOLAS | PROTECT BALTIC, B22, B28, B31, B32, S68, B10 | 2023: key ecosystem components and threats assessed under HOLAS 3. | By 2023 an assessment, is ready and publicly available.
[8 empty] | 2025: complement currently prioritized conservation features with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services. | By 2025 currently prioritized conservation features have been complemented with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services.
[8 empty] | 2023-2028: PROTECT BALTIC functions as the platform for identifying key representative ecosystem components based on function for the ecosystem/provisioning of ecosystem services. | By 2030 effective measures are in place to mitigate threats and pressures, to improve the status of the identified key ecosystem components. (National measure)
30 | National/Joint | B9 | By 2024 assess the status of the Haploops species and the biotopes, as well as key threats and, if relevant based on the assessment, by 2026 develop a joint conservation plan for Haploops species including jointly agreed measures to improve the status of the species and biotopes, to be implemented by 2028. | Denmark | WG BioDiv | - | - | 2022-2024: The status will be assessed as part of the Red List II project. | By 2024, updated assessment of the status of the species and the biotope, as well as key threats is ready and publicly available. (Joint supporting action)
[8 empty] | 2025-2026: Based on the results of the assessment and the identified pressures in the Species Information Sheet, the relevant CPs work together using HELCOM as a platform, to identify and agree on measures and develop a joint conservation plan for the species. | By 2026, if and where relevant, based on the status assessment, development of a joint conservation plan to improve the status of haploops species and biotopes, including jointly agreed measures, has been completed. (Joint supporting action)
[8 empty] | 2027-2028: national implementation of measures and conservation plan. | By 2028, if and where relevant, based on the status assessment, development of a joint conservation plan to improve the status of haploops species and biotopes, including jointly agreed measures, has been adopted. (Joint supporting action)
If and where relevant, joint conservation plan to improve the status of haploops species and biotopes, including jointly agreed measures, has been implemented. (National measure)
31 | Joint | B29 | By 2025 develop, and by 2027 implement, and ensure compliance with, ecologically relevant conservation plans or other relevant programmes or measures, limiting direct and indirect pressures stemming from human activities for threatened and declining biotopes and habitats. |  | WG BioDiv | - | PROTECT BALTIC, B22, B28, B31, B32, S68, B10 | 2024: Prepare a list of what habitats/biotopes on the Red List are relevant for what CP. | By end of 2024 an overview list of what Red Listed habitats/biotopes are relevant for each CP has been produced.
[8 empty] | 2025: Based on the results of the assessment and the identified pressures in the Habitat Information Sheet, the relevant CPs work to identify and agree on measures and develop conservation plans for the relevant habitat/biotope. Conservation plans and measures can also be prepared jointly by several CPs. WG BioDiv to track progress. | By 2025 conservation plans or environmental measures are developed and ready to be implemented. (National supporting action)
[8 empty] | 2026-2027: national implementation of measures and conservation plan. WG BioDiv to track progress. | By 2027 conservation plans or other relevant programmes or measures are implemented. (National measure)
Negative status trends are turned, in the long-term securing favourable status of the relevant habitats and biotopes. (National measure)
2025-2030: Track status to support adaptive management and transboundary initiatives
32 | Joint | B30 | Develop tools for, and regularly assess, the effectiveness of other conservation measures for habitats and biotopes, besides marine protected areas (MPAs), the first assessment to be done by 2025 as well as assess effect on biotopes and habitats through risk- and status assessments by 2029. |  | WG BioDiv | - | - | Autumn 2023: Dedicated session to identify what other conservation measures are available. Using the Habitats Directive list of conservation measures, removing the spatial measures, as a basis. | By end of 2023: Overview of available other conservation measures prepared.
[8 empty] | 2024: Explore how to best combine the assessment of effectiveness of other conservation measures with MPAs and develop methodology/tools. | By 2025 tools for assessment of effectiveness of conservation measures for habitats and biotopes, other than MPAs, have been developed.
[8 empty] | 2025: run the assessment and prepare report. | By 2025 the first assessment of effectiveness of other conservation measures for habitats and biotopes, besides MPAs, is ready and publicly available.
By 2029 the effect of conservation measures for habitats and biotopes, other than MPAs, on species has been evaluated through risk- and status assessments.
Theme: Restoration
33 | National/Joint | B26 | […] -[protect key ecosystem components, including habitat forming species by] identifying suitable measures and types of habitats, biotopes and key ecosystem components for passive or active restoration by 2025 and implementing programmes for restoration as outlined in the HELCOM Restoration Action plan by 2030. | PROTECT BALTIC | WG BioDiv | - | implementation of the EU restoration law and the UN Decade of Ecosystem Restoration | 2023-2028: PROTECT BALTIC will work on the identification and agreement of a list of key ecosystem components, identification of possible measures, measures effectiveness analysis and, development of the Restoration Action Plan and toolbox, in close collaboration with WG BioDiv | By 2023 currently prioritized conservation features have been complemented with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services. (Joint supporting action)
By 2023 an assessment, is ready and publicly available. (Joint supporting action)
By 2030 effective measures are in place to mitigate threats and pressures, to improve the status of the identified key ecosystem components. (National measure)
34 | National/Joint | B27 | By 2025 develop and by 2026 start implementing a HELCOM Action Plan for habitat and biotope restoration, including qualitative and quantitative regional targets, a prioritized list of actions, and an associated implementation toolbox outlining best practices and methods for restoration in the Baltic Sea region. | PROTECT BALTIC/Sweden | WG BioDiv | - | S52 (WG Fish). This work will be closely tied to the EU regulation on restoration. | From 2022 onwards: at regular intervals identify and share information on methods and national work on ecosystem restoration in the Baltic Sea, | By 2025 qualitative and quantitative regional targets for habitat and biotope restoration have been established. (Joint supporting action) | Denmark can possibly support the work and next steps.
[8 empty] | From 2023 onwards: share information on development of indicators to track progress of restoration efforts and their effect | By 2025 a prioritized list of restoration actions has been developed and is publicly available. (Joint supporting action)
[8 empty] | 2024: use the discussions in the WG to identify regional priorities, taking into account possible measures outlined in the Red List recommendation and Red List Species and Habitat Information Sheets. | By 2025 a HELCOM Action Plan for habitat and biotope restoration has been developed and is publicly available. (Joint supporting action)
[8 empty] | 2024: explore the need/possibility of a HELCOM Recommendation on restoration, to support the Action Plan. | By 2025 an implementation toolbox outlining best practices and methods for restoration has been developed to support the implementation of the HELCOM Action Plan for habitat and biotope restoration (Joint supporting action)
[8 empty] | 2023-2028: PROTECT BALTIC will function as the platform for discussions, arranging dedicated sessions/WSs as needed and preparing input material, as well as the draft plan | By 2026 the implementation of the HELCOM Action Plan has commenced. (National measure)
35 | NA |  | To discuss and share experiences on the national work on the proposed EU Restoration Law |  | WG BioDiv | - | EU Restoration Law | From 2022 onwards: the BIODIV WG to be used as a platform for regional coordination of national restoration efforts, by helping to ensure that efforts are ecologically relevant, synergistic and that actions in one area do not jeopardize the possibility of success, nor effectiveness of, restoration efforts elsewhere. | A regional platform for transboundary cooperation with regards to restoration activities.
By 2024 identification of HELCOMs role with regards to the EU restoration law.
36 | National/Joint | B18 | Restore functional populations of Baltic sturgeon by 2029 implementing the HELCOM Baltic Sea Sturgeon Action Plan. | EG Stur | WG BioDiv | WG Fish, EG Fish-M | activities related to the European Sturgeon Action Plan | The next steps are included in the Action Plan, in 2023 invite EG STUR to plan the more detailed timeline for the implementation of the action at its next meeting. | Consistent ex-situ conservation programme is implemented, taking advantage of the specimens already secured. (National measure) | For FISH WG: Finalizing the Recommendation on large river restoration. Activate cooperation with BALTFISH to come up with joint recommendations for modified fishing gear and for monitoring by-catch.
Adoption of the Recommendation on large river restoration.
In situ conservation programme is implemented and enforced, preventing further loss of the remaining specimens. (National measure)
A strategic long-term monitoring programme for population development and habitat use, to support adaptive management, is in place in all relevant countries. (National supporting action)
A dedicated programme on habitat protection and rehabilitation has been developed, in order to ensure that spawning and nursery sites meet the needs of the species and are accessible for the respective life cycle stages. (Joint supporting action)
A dedicated programme on habitat protection and rehabilitation, ensuring that spawning and nursery sites meet the needs of the species and are accessible for the respective life cycle stages, has been implemented where relevant. (National measure)
Successful, self-sustaining, re-introduced population of Baltic sturgeon is in its potential spawning rivers and in key areas of its former natural range. (National measure)
Theme: Climate change
37 | Joint | HT1 | Using the HELCOM/Baltic Earth Joint Expert Network on Climate Change as a platform and through committed implementation of the HELCOM Science Agenda, improve the access of policy-makers to scientific information on the impacts of climate change together with multiple other pressures on the Baltic Sea marine environment through periodic updates of the HELCOM Climate Change Fact Sheet, and incorporate the possible effect of climate change into the holistic assessment of status as well as effectiveness of measures by 2030 at latest. | EN Clime | WG GEAR | WG BioDiv, WG Landbased, WG Sea-based pressures, WG Fish, EG MaMa, EG Benthic, EG Phyto, EG Zoo, JWG Bird, [EG Coastal Fish] | BEAR development under BALTIC EARTH | 2023-2024: identify possible additional parameters related to biodiversity and ecosystems, for future inclusion in the CCFS. | By end of 2024: plan for inclusion of climate change information in HOLAS 4.
[8 empty] | 2023-2024: Review of HOLAS 3 and scoping and planning the HOLAS 4 preparatory work, including how to further improve integration of climate change in the status assessment for biodiversity and ecosystems. | By 2025, possible inclusion of additional biodiversity parameters into the updated CCFS
2025: support the preparation of possible additional parameters, using the established CCFS procedure.
38 | Joint | HT5 | Develop a strategic approach to ocean acidification for the Baltic Sea with first steps addressing the knowledge gaps by 2025. |  | WG GEAR | WG BioDiv, EN Clime | Indicator development for acidification under HELCOM. ECOSTAT acidification processes, EEA acidification indicator work. OSPAR ICG on Acidification and the Ocean Acidification Alliance. | Autumn 2023: Scoping WS on acidification in the Baltic Sea, knowledge gaps and needs, including session on biological and ecosystem effects. | By end of 2023 knowledge gaps in relation to ocean acidification in the Baltic Sea have been identified.
By end of 2025 identified knowledge gaps in relation to ocean acidification in the Baltic Sea have been addressed.
By 2030 a strategic approach to ocean acidification for the Baltic Sea has been developed and adopted.
Theme: Monitoring
39 | Joint | HT6 | Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements. | CP leads as identified under GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDiv, WG Source to sea; WG Sea-based pressures; EG Haz; EG Eutro; EG MaMa; EG ML; EG Noise; EG Phyto; EG Zoo; JWG Bird, EG Benthic | PROTECT BALTIC, MSDF Art.11 | By 2024 perform a gap analysis of the current Monitoring Manual and monitoring programmes with respect to biodiversity and protection and agree how the gaps can best be addressed as part of the next update. | Updated monitoring programmes are available every six years in line with what is specified in the action.
Autumn 2024-2026: Begin the process to update the biodiversity related monitoring programmes to ensure the review and update is finalized and the updated monitoring manual and programmes are published in early 2026, in good time before the national Art.11 reporting concludes.
[2023-2028: PROTECT BALTIC will review monitoring methods for monitoring of pressures and biodiversity in MPAs, but which are possibly also relevant for monitoring overall and could be used to support the review of the monitoring programmes].
40 | NA |  | Contribute to and guide the development of biodiversity and ecosystem related regional monitoring guidelines. | On a need basis. | WG BioDiv | - | - | [2023-2028: PROTECT BALTIC will review monitoring methods for monitoring of pressures and biodiversity in MPAs, but which are possibly also relevant for monitoring overall and could be used to support the review/development of monitoring guidelines]. | New monitoring guidelines for biodiversity and protection available when relevant.
41 | Joint | HT11 | Develop quality standards for seafloor habitat mapping and derived products by 2024. | needed | WG BioDiv | EG Benthic | EMODnet EUSeamap, PROTECT BALTIC | Spring 2024: WS on habitat mapping and derived products. The WS to scope national work on quality standards, including for substrate identification and data reporting and the possibility to use this to develop regional standards, or, in the absence of national standards, outline a plan for future work. | By end of 2024 standards for quality of seafloor habitat mapping have been developed and agreed
Spring 2024: WG to review plan, identify lead(s) for drafting.
Autumn 2024: WG to review the draft standards and provide guidance and input.
Spring 2025: Approve the finalized standards for layout and publication.
2023-2028: PROTECT BALTIC will develop modelling approaches for modelling benthic habitats and biotopes, as well as produce maps. As part of this work it is likely that the project will produce information on quality requirements for both data and products, which can be included in the work on establishing standards.
42 | National/Joint | HT10 | Target the gaps identified in the HELCOM monitoring programmes of biotopes, habitats, including key habitats and key habitats forming species by 2024 and operationalize continual Baltic-wide monitoring of those biotopes and habitats by 2030. |  | WG BioDiv | EG Benthic | MSDF Art.11 | Spring 2023: Utilize the gap analysis prepared under the SEAM and FUMARI project, as well as any relevant information identified under the scoping of gaps in at sea monitoring, to collate an overview of existing gaps. Review the overview to identify national gaps, as well as any overlooked species/habitat/biotope specific gaps. | By 2023 a full gap analysis is made for monitoring programmes of biotopes and habitats.
[8 empty] | Autumn 2023: Identify possible solutions to the gaps | By 2024 gaps for monitoring programmes of biotopes and habitats are addressed and updated monitoring programmes and guidelines prepared.
[8 empty] | 2024: Agree on methodology, data formats, target components, frequency etc. | By 2030 continual Baltic-wide monitoring of biotopes and habitats is operationalized. (National)
43 | National/Joint | B15 | Develop and coordinate monitoring and assessment methods, where ecologically relevant, for specified representative coastal fish species, populations and communities, by 2023. […] | [EG Coastal fish] | WG BioDiv | WG Fish | S53 (WG Fish) | 2023: assessment produced for coastal fish as part of HOLAS 3. | By 2025 monitoring guidelines are available which cover all the representative species.
[8 empty] | 2023: [EG Coastal fish] to review the assessment methodology for coastal fish and report proposed improvements to WG. | By 2027 further refined assessment methodology available for assessment of representative coastal fish.
Spring 2024: [EG Coastal fish] to review the list of selected representative coastal fish species and propose which species to include for future assessment. WG to review and approval.
Autumn 2024: [EG Coastal fish] to perform gap analysis of monitoring methods for the selected representative coastal fish species and report to WG, which, if needed, prioritizes amongst gaps.
2025: [EG Coastal fish] to develop HELCOM monitoring guidelines for the representative species, WG to approve, with the ultimate aim of securing comparable data and results
2024-2026: [EG Coastal fish] to further develop assessment methods for assessment of coastal fish species towards HOLAS
44 | NA |  | Establish persistent regular data flows and data management for all biodiversity and ecosystem data needed for HELCOM assessment and tracking purposes. |  | WG BioDiv | EG MaMa, JWG Bird, EG Birdmove, [EG Coastal Fish], EG Zoo, EG Phyto, EG Benthic | - | From 2023 onwards: Using the review of the HOLAS 3 (2023), RED LIST (2023) and PROTECT BALTIC (2025) data reporting and processes as a basis, identify gaps in dataflows and infrastructure. | Lower resource requirements long term due to automatised data reporting.
[8 empty] | Analyze the underlying causes and identify solutions. | Improved access to data and information across the region.
[8 empty] | Implement solutions to secure improved, consistent dataflows. | Enabling automatising assessment procedure.
45 | S38 | S38 | Undertake monitoring and pollution risk assessment regarding species and habitats in the Baltic Region by 2026. | EG WILDLIFE | WG Response | WG GEAR;WG BioDiv; EG BirdMove; EG MaMa; JWG BIRD | Other groups to report barriers to WG GEAR. | An analysis of data stemming from existing monitoring to determine vulnerable species, vulnerable areas, vulnerable times of the year is conducted. | An analysis of data stemming from existing monitoring to determine vulnerable species, vulnerable areas, vulnerable times of the year is conducted.
[7 empty] | Need to interpret the action jointly to come up with a cross-topical plan for how to address this action, what is already available and where further HELCOM work can add value. | Results are presented in a format which fulfils the needs of an operational manager, e.g. seasonal maps with risk indications, scale indications. etc. | Results are presented in a format which fulfils the needs of an operational manager, e.g. seasonal maps with risk indications, scale indications. etc.
[8 empty] | A risk analysis as to how response activities could also impact certain species and habitats in areas, seasons, or certain circumstances is conducted. | A risk analysis as to how response activities could also impact certain species and habitats in areas, seasons, or certain circumstances is conducted.
Theme: General/recurring tasks
46 | NA |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group | relevant country leading the Recommendation. | WG BioDiv | - | - | Persistent agenda item on the WG’s agenda, with the intention that implementation is supported, a lead is available for each Recommendation, reporting intervals and formats are established and that reporting follows a rolling system where implementation of Recommendations are regularly tracked and reviewed. | Plan for the implementation, reporting and possible revision of the Recommendation at each meeting.
47 | NA |  | Regularly review Baltic Sea Environment Factsheets (BSEFs) relevant to the groups remit and approve any new BSEFs for publication. | relevant country leading the Recommendation. | WG BioDiv | - | - | Persistent agenda item on the WG’s agenda, with the intention to ensure information presented is current and relevant and that any emerging topics are covered. | Up-to-date BSEFs available on the HELCOM website.
Topic: Planning future work
48 | NA |  | Plan for the implementation of actions with later target years (cf. Appendix 1) | relevant country leading the Recommendation. | WG BioDiv | - | - | In the 2024 autumn meeting of the WG, review the workplan, include actions with target years in the next 2 year work period and elaborate associated tasks and next steps. | Up-to-date Workplan available to guide the work of the group
Topic: Cooperation with other international organizations and institutions and processes
49 | NA |  | Identify and engage in relevant current and emerging international initiatives and processes on regional, interregional, EU and global level. | - | WG BioDiv | - | Biodiversity related SDGs, CBD, UNEP, UN Decade of Ocean Science, UN Decade of Ecosystem Restoration, EU Green Deal, EU Biodiversity Strategy, EU MSFD, EU HBD, EU Restoration Law, RSC initiatives, CMS. | At each meeting share information on current and emerging international initiatives and processes of relevance for the WG. | Improved visibility, impact and uptake of HELCOM work outside of the immediate Baltic Sea region. (continuous)
[8 empty] | Scope the possible contribution and benefit for HELCOM and engage accordingly. | HELCOM work is current, fit-for-purpose and can support CPs in their efforts to implement other international commitments.
50 | NA |  | Map the BSAP actions against the CBD global biodiversity targets |  | WG BioDiv | - | CBD global biodiversity targets. | Once the targets are available the Secretariat will prepare an initial mapping, to be reviewed in the next WG meeting and, once approved, shared with GEAR to support horizontal coordination. | Improved overview of, and possibility to report on, how CPs work in HELCOM concretely contributes to reaching the global targets.