## Sheet1
Approved via correspondence in September 2023 by the Heads of Delegations of the EU and the Contracting Parties to HELCOM that are also Member States of the EU
No | BSAP action | Type of action | Task | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
Theme: General/recurring tasks
Topic: Cooperation with other international organizations, institutions and processes
1 | S41 | Joint | Further elaborate cooperation between the Baltic Sea Fisheries Forum (BALTFISH) and relevant HELCOM working groups by 2023 to facilitate a wide range of actions to achieve good environmental status. | Secretariat to lead, taking into account decisions/instructions by WG Fish meetings. | WG Fish |  |  | Continuously sharing relevant meeting agendas and outcomes with BALTFISH and attending relevant meetings. Consider possibilities of organizing joint workshops or meetings, involving also BSAC, to address specific topics, with the aim to find solutions to meet relevant objectives. Consider further structuring and formalization of the cooperation and coordination. Eight out of HELCOM’s ten Contracting Parties are also members of BALTFISH, although the responsible authorities might differ in some cases. Coordination between HELCOM and BALTFISH does not remove the need for Contracting Parties to coordinate at the national level. | A more structured or formalized cooperation and coordination between HELCOM and BALTFISH is elaborated. Such cooperation and coordination is carried out through practical means such as sharing meeting agendas, and feeding in to the appropriate processes between organizations.
Topic: Recommendations
2 |  |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group. | To be determined case by case | WG Fish |  |  | The Secretariat to submit a compilation of Recommendations related to the WG Fish to initiate the discussion in 2023. When revising individual Recommendations, lead countries should be identified on a case by case basis. | HELCOM Recommendations of relevance for the group are up to date, implemented and reported on a regular basis.
Theme: Spatial conservation measures
Topic: Spatial conservation management
3 | B5 | National/Joint | Develop, implement and share information on effective management measures, including measures to ensure compliance/control measures, to reduce the impact of fisheries inside marine protected areas (MPAs) in order to contribute to achieve their conservation objectives. | Lead needed | WG Fish | WG BioDiv | S43 | Contracting Parties to share information on management measures proven to be effective. The Secretariat to set up a document on the Meeting Portal in order to collect information from Contracting Parties on effective fisheries management measures. The role of WG BioDiv in contributing to this action needs to be determined. Contracting Parties develop operational and technical bycatch reduction measures such as set net closures and ADDs in MPAs. Implement nationally in MPAs in coastal waters. Contracting Parties to initiate the Article 11 process/ BALTFISH Joint Recommendation process for MPAs in their EEZs. The development of management measures and their implementation within the EEZs will require cooperation with BALTFISH, as well as the Scheveningen Group for Kattegat. Measures are already in place in some MPAs, information sharing is taking place, as well as the development of regional procedures. 2023-2028: If the PROTECT BALTIC project is funded work on the HELCOM MPA database will be progressed using the project as a platform (improve database functionality and reporting, preparing reporting manuals, collating MPA specific information, translating it and populating the database). There is a link with the EU Biodiversity Strategy, the implementation of which also contributes to this action. | Management measures for fisheries inside MPAs, contributing to the area’s conservation objectives, are more widely in place. (National measure) Fisheries measures are documented in the HELCOM MPA Database. (Joint supporting action)
Topic: Conservation of fish
4 | B15 | National/Joint | Develop and coordinate monitoring and assessment methods, where ecologically relevant, for specified representative coastal fish species, populations and communities, by 2023. | FISH-PRO III [Sweden] | WG BioDiv | WG Fish | S53 | 2023: assessment produced for coastal fish as part of HOLAS 3. Spring 2024: FISH-PRO to review the list of selected representative coastal fish species and propose which species to include for future assessment. WG to review and approval. Autumn 2024: FISH-PRO to perform gap analysis of monitoring methods for the selected representative coastal fish species and report to WG, which, if needed, prioritizes amongst gaps. 2025: FISH-PRO to develop HELCOM monitoring guidelines for the representative species, WG to approve, with the ultimate aim of securing comparable data and results 2024-2026: FISH-PRO to further develop assessment methods for assessment of coastal fish species towards HOLAS | By 2025 monitoring guidelines are available which cover all the representative species. By 2027 further refined assessment methodology available for assessment of representative coastal fish.
5 | B15 | National/Joint | […] regularly assess the state of the coastal fish community through selected coastal fish species and groups, including threatened species, by at latest 2023. | FISH-PRO III [Sweden] | WG BioDiv | WG Fish |  | Coordinated assessment methods are being progressed under FISH Pro as part of the work for HOLAS 3 and the coastal fish assessments. | By 2023 assessment, presenting information in a format that contributes to the effective implementation of measures is ready and publicly available. (Joint supporting action). Interval for the next assessment is agreed by 2023. (Joint supporting action. Where ecologically relevant, data and assessment of coastal fish is available by 2023 for the full distribution of the species, at a resolution suitable for management and the implementation of measures. (Joint supporting action. By 2027 appropriate management measures have been implemented with the ambition to maintain or improve the status of coastal fish species. (National measure)
6 | B17 | National/Joint | With the aim to protect and restore eel population, determine which measures set out in the Convention on the Conservation of Migratory Species of Wild Animals (CMS), EU Eel Regulation and other relevant instruments would benefit from regional cooperation on a Baltic-wide level. Finalize by 2024 and implement by 2025 a Baltic coordinated programme of such measures. | Fish-M | WG Fish |  | BSAC meetings and activities | Fish-M to plan the implementation of the action taking into account developments within BALTFISH, EU, EU member states and other relevant bodies. BALTFISH has taken initiative on eel and there might be attempts for coordinated action. The BSAC has issued advice on eel on the 5 May 2022. The recommendations outline concrete proposals for improving the situation from the regional view of the Baltic Sea that could be taken on board when drafting the coordinated programme of protective measures. Actions needed in all sea basins including the Mediterranean and the Black Sea (NB: the Eel Regulation (EU) 1100/2007 does not apply to the Black Sea and its river system according to Commission Decision 2008/292/EC). Important to take into account all anthropogenic effects. All anthropogenic mortalities, all life stages of eel and all habitats should be taken into account, not only fisheries. But do not wait until all effects are identified. BALTFISH has taken initiative on eel and there might be attempts for coordinated action. The BSAC has issued advice on eel on the 5 May 2022. The recommendations outline concrete proposals for improving the situation from the regional view of the Baltic Sea that could be taken on board when drafting the coordinated programme of protective measures. Actions needed in all sea basins including the Mediterranean and the Black Sea (NB: the Eel Regulation (EU) 1100/2007 does not apply to the Black Sea and its river system according to Commission Decision 2008/292/EC). Important to take into account all anthropogenic effects. All anthropogenic mortalities, all life stages of eel and all habitats should be taken into account, not only fisheries. But do not wait until all effects are identified. | A coordinated programme of protective measures ensuring successful eel migrations, aligned with CMS, the EU Eel Regulation and other relevant instruments is in place by 2024 (Joint supporting action) and being implemented by 2025 (National measure).
7 | B18 | National/Joint | Restore functional populations of Baltic sturgeon by 2029 implementing the HELCOM Baltic Sea Sturgeon Action Plan. | EG Stur, supported by Fish-M | WG BioDiv | WG Fish | activities related to the European Sturgeon Action Plan | HELCOM should activate cooperation with BALTFISH to come up with joint recommendations for modified fishing gear and for monitoring by-catch. Finalizing the Recommendation on large river restoration. The next steps are included in the European Sturgeon Action Plan, in 2023 invite EG STUR to plan the more detailed timeline for the implementation of the action at its next meeting. For WG Fish: Finalizing the draft Recommendation on large river restoration for sturgeon. | Consistent ex-situ conservation programme is implemented, taking advantage of the specimens already secured. (National measure). Adoption of the Recommendation on large river restoration. In situ conservation programme is implemented and enforced, preventing further loss of the remaining specimens. (National measure) A strategic long-term monitoring programme for population development and habitat use, to support adaptive management, is in place in all relevant countries. (National supporting action) A dedicated programme on habitat protection and rehabilitation has been developed, in order to ensure that spawning and nursery sites meet the needs of the species and are accessible for the respective life cycle stages. (Joint supporting action) A dedicated programme on habitat protection and rehabilitation, ensuring that spawning and nursery sites meet the needs of the species and are accessible for the respective life cycle stages, has been implemented where relevant. (National measure) Successful, self-sustaining, re-introduced population of Baltic sturgeon is in its potential spawning rivers and in key areas of its former natural range. (National measure)
Theme: Enabling ecosystem-based management
Topic: Indicators
8 | B35 | Joint | By 2024 operationalize a set of indicators for the assessment of fish population health, including size and age distribution, where applicable, and, by 2029, for any remaining relevant species. | [FISH-PRO III] [Sweden] | WG BioDiv | GEAR WG, WG Fish | S40, S48, possible ongoing work within ICES | This work is ongoing under the HELCOM BLUES project towards HOLAS 3. 2023/2024: Invite FISH-PRO to perform a review and gap analysis following HOLAS 3 and development of a workplan for the development work towards HOLAS 4. To be reviewed and approved by WG BioDiv. 2023/2024: secure agreement amongst Contracting Parties on how to address commercial fish. 2024: implement workplans (if possible with the support of external funding). | By 2024 indicators for the assessment of fish population health are available, including indicators for size and age distribution. By 2029 health, size and distributional indicators are available for all relevant species.
9 |  | Joint | Review and contribute to the development and assessment of HELCOM indicators related to fish, cumulative impacts on fish, fisheries impact on food webs, incidental bycatches and fisheries impacts on benthic biotopes |  | WG Fish |  | GEAR, WG BioDiv, EG Fishdata, FISH-PRO III, HELCOM Indicator Workshops, HOLAS 3, HOD. ICES Fisheries Overviews | Communicate with relevant HELCOM Groups and projects regarding planning of development and assessment of indicators on fish (including threatened species), impacts on fish and fisheries impacts on foodwebs – and how WG Fish can contribute. EG Fishdata to consider in follow up of Roadmap with the aim of implementing data collection and contribute to the needs identified in line with ecosystem-based management. Important to coordinate with ICES Work. | Contribution to keeping the HELCOM indicator catalogue up to date.
Theme: Fisheries management
10 | S40 | Joint | Identify by 2024 fish species for which there is a need for better data for identified purposes, such as setting threshold levels. Utilize dedicated programmes and projects to facilitate recording and reporting of data for these species by 2025 to support the identification and implementation of measures to achieve good environmental status. | EG Fishdata | WG Fish |  | B35, BSAC meetings and activities | For the first part of the action WG Fish should request support from FISHPRO, COMFISH or other relevant projects in identifying the need for data on commercial and non-commercial fish species with a view on food webs and other ecosystem aspects. EG Fishdata should be reactivated to bring forward the implementation of the second part of the action. BSAC could be consulted for the first part of the action (identification of fish species where there is need for better data) which is a recurring point in the BSAC recommendations. Important that the work is coordinated with BSAC and other regional bodies. Important that the work is also coordinated with ICES and its relevant working groups. The action is not related specifically to by-catch, but to improved data on fish species for which there is insufficient data in general. Some issues could be improved after the revision and subsequent implementation of the control regulation. HELCOM work on commercial fisheries to be considered and contribute. It should be clarified how detailed and for which purpose the data is collected. | By 2024 fish species for which there is a need for better data for identified purposes have been identified. By 2025 programmes or projects are in place to facilitate recording and reporting of data from commercial and recreational fishermen on catch of non-target fish species.
11 | S42 | Joint | Update and harmonize by 2024 the 2016 BALTFIMPA decision-support tool approach with ongoing initiatives e.g. in the International Council for the Exploration of the Sea (ICES) on a seafloor assessment framework for the Baltic Sea. This tool should also provide options on how to reduce the possible negative impact of fisheries on conservation values in the most cost-effective way, including in marine protected areas (MPAs). | Lead needed. | WG Fish |  | B5 | ICES to be invited to have a look at the BALTFIMPA tool and propose possible updates needed. A lead country or project would be useful in order to update the BALTFIMPA tool. | BALTFIMPA decision support tool is updated.
12 |  | National/Joint | Assess how far countries have come in implementing fisheries management measures in MPAs, how such measures are linked to other processes such as MSP, HOLAS, MSFD implementation and how information on impacts of fishing gear is used for management. |  | WG Fish |  | WG BioDiv, MPA TG, PROTECT BALTIC project | Questionnaire on alternative fishing gears (HELCOM Meeting portal workspace). ICES 2015 advice on pressure from fishing activity in MPAs Dedicated session to be convened. Contracting Parties to report on development and implementation of fisheries management measures in MPAs. | Assessment of fisheries management measures in MPAs complete.
Topic: By-catch
13 | S43 | Joint | Reduce the negative impacts of fishing activities on the marine ecosystem and to this end, support the development of fisheries management including technical measures to minimize unwanted by-catch of fish, birds and marine mammals and achieve the close to zero target for by-catch rates of relevant species by 2024, especially the Baltic proper population of harbour porpoise by 2022. | Lead needed | WG Fish |  | B8, BSAC meetings and activities | Contracting Parties to follow and contribute, as appropriate, to the discussions within BALTFISH regarding fisheries management measures to support this action. Consider what HELCOM could contribute with through e.g. EG MaMa or other relevant Expert Groups with regard to the implementation of this action. Fisheries management measures are developed by Contracting Parties and activities are also ongoing on the matter within BALTFISH. Germany and Poland to submit document to WG Fish in 2023, containing a proposal for the development of a by-catch mitigation toolbox. Consider possibilities of setting up a by-catch mitigation toolbox on a workspace on the HELCOM Meeting Portal. Contracting Parties and observers would subsequently be invited to contribute by filling in information on effective fisheries management measures, including technical and operational measures. From 1 June 2022 (Reg. 2022/303) an EU Delegated Regulation on full/seasonal closures in some MPAs contributes to achieving the goal of this action. EG MaMa, JWG Bird EG Stur should be involved in the implementation of this action. The following proposed measures could be considered in the development of a selection of measures: - Efforts should be made in Contracting Parties to undertake the following concrete actions: - Time/area closures in high-risk areas already identified (e.g., Femern Belt) - Set net closures in MPAs important for porpoises and birds where by-catch has been identified as a problem. - Follow discussions within BALTFISH regarding fisheries management measures - Excluder grids or exits in pontoon traps and fyke nets (not within HELCOM remit). The European Commission encourages EU Member States to use EMFAF to support the use of alternative fishing gear. The BSAC has been advising on the use of alternative fishing gears reducing by-catches for a number of years. BSAC is also ready to comment further on possible measures on harbour porpoise and by-catch in general. | The action is of an ongoing nature and will be followed up by assessment of by-catch within regional assessments.
Topic: Protection of mammals
14 | B8 | National/Joint | By 2022 at the latest, specify knowledge gaps on all threats to the Baltic Proper harbour porpoise population, and by 2023 for the western Baltic population, including by-catch and areas of high by-catch risk, underwater noise, contaminants and prey depletion. Knowledge gaps related to areas of high by-catch risk are to be addressed and by 2028 at the latest additional areas of high by-catch risk for both Baltic Sea populations are to be determined. To strengthen Baltic harbour porpoise population, by 2025 identify possible mitigation measures for threats other than by-catch and implement such measures as they become available. | Co-Lead: Poland, WWF Poland [Sweden] | WG BioDiv | EG MaMa, EG Noise, EG Haz (biological effects), WG Fish | S43 (WG Fish), S44 (WG Fish), S45 (WG Fish), S46 (WG Fish), S47 (WG Fish), S48 (WG Fish), ASCOBANS Jastarnia Group | Early 2023: Leads to prepare initial list of gaps. HOLAS 3 can contribute with information on knowledge gaps for harbour porpoise assessment (in indicator reports and thematic assessment). Spring 2023: Invite Contracting Parties and EG MaMa harbour porpoise team to provide knowledge gaps to the spring meeting of WG BioDiv. Invite ASCOBANS/Jastarnia group to provide input to the same meeting. Priority (no direct support for implementation identified). Could be supported by a SAMBAH project (or similar). | By 2023 knowledge gaps on all threats to the Baltic Proper harbour porpoise population have been specified and listed. By 2023 knowledge gaps on all threats to the western Baltic population have been specified and listed. By 2025 possible mitigation measures are identified and implemented as they become available. (National measure) By 2028 knowledge gaps related to areas of high by-catch risk are addressed. By 2028 year, at the latest, additional areas of high by-catch risk for both Baltic Sea populations have been determined.
15 | S46 | Joint | Promote effective mitigation measures to minimize by-catch of harbour porpoises in the Baltic Sea area inter alia via cooperation with the Baltic Sea Fisheries Forum (BALTFISH), and evaluate and promote adjusted measures as needed by 2025. | needed | WG Fish |  | B8, Ongoing discussions within BALTFISH on this topic | Denmark, Germany and Poland to share information with WG Fish on possible studies on porpoise occurrence in German/Polish/Danish MPA cluster[1] using C-PODs, developing additional appropriate measures and promoting them. To consider if mitigation measures in place in the German/Polish/Danish MPA cluster are sufficient, and if necessary, consider whether additional voluntary measures are needed. In coordination with Navies, Contracting Parties to investigate the possibility of using pingers on the national level. Contracting Parties to consider taking the lead for implementation of this action and inform the WG Fish in 2023. Cooperation with EG MaMa and the ASCOBANS/JASTARNIA group would be beneficial, in particular with regard to studying the occurrence of harbour porpoise. | Effective mitigation measures to reduce by-catch of harbour porpoise in the Baltic Sea have been promoted inter alia in cooperation with BALTFISH.
16 | S47 | National/Joint | Continually test, promote and introduce new technical and operational by-catch mitigation measures such as alternative and seal safe gears in cooperation with competent authorities with the aim to, as appropriate, replace fishing gear proven to be problematic with respect to by-catch, with evaluation of measures every five years starting in 2023, and regularly update the HELCOM questionnaire on trials of alternative fishing gears and fishing techniques. | Co-leads: Poland and Denmark: Poland to lead work related to the questionnaire. | WG Fish |  | B5, B8, S43 | DK to fill in HELCOM questionnaire with results of their tests at DTU Aqua. Contracting Parties to encourage co-operation between science and fishers sharing best practices. Initiating projects, field tests etc. Alternatives for flatfish set nets sought Investigate the possibility to add information to questionnaire from EU Regulation 2019/1241 (if any) to the HELCOM questionnaire. | Ongoing tests of new technical and operational by-catch mitigation measures are evaluated every five years, starting in 2023. (Joint). New efficient alternative fishing gear have been developed and are used as appropriate. (National) HELCOM questionnaire on trials of alternative fishing gears and techniques updated regularly, at least every two years, starting in 2022 making also use, as applicable, of information collected through the reporting requirements of Regulation EU 2019/1241. (Joint)
17 | S48 | Joint | Develop and implement an effective data collection for more reliable data on incidental by-caught birds and mammals and fishing effort consistent and fully in line with the data needs identified by the International Council for the Exploration of the Sea (ICES). Relevant sources of data are e.g. EU basic control Regulation and additional national or regional coordinated data collection programmes or projects for filling data-gaps outlined in the HELCOM Roadmap on fisheries data. |  | WG Fish | EG Fishdata | B8, B35 | In the short term: taking into account the revised EU Control Regulation: a) Contracting Parties to exchange information on how to collect effort data for small vessels and bycatch data. b) On the basis of the exchanged information Contracting Parties should identify ways how to collect the needed data in a cost-effective way making use of identified synergies to the extent possible c) Contracting Parties to initiate (national/joint) projects to collect bycatch data on the basis of the EU MAP d) Contracting Parties to incentivise fishermen’s participation in REM studies The overall responsibility of implementing this action is with WG Fish and EG Fishdata could be tasked to deal with this action. Cooperation with regional coordination groups needed. There is a legal obligation for EU Member States with regard to collection of bycatch data. The EU Control Regulation is currently being reviewed, the outcome of which will need to be taken into account in implementing the part of the action which deals with effort data recording and reporting. | An effective system is in place for data collection of by-catch of birds, mammals, and fishing effort, taking into account data needs identified by ICES and data gaps outlined in the HELCOM Roadmap on fisheries data, as well as the logbook requirements in the EU Control Regulation.
18 | S49 | National/Joint | Maintain, develop and extend regulatory or voluntary schemes to protect key seabird areas and seasons by establishing appropriate fisheries measures in line with conservation objectives and to monitor incidental catches of seabirds by 2025. Extend and develop outreach programmes for the fisheries sector concerning their possible impacts on seabird populations. | Contracting Parties | WG Fish |  | JWGBird, TG MPA | 1. Outreach Contracting Parties to initiate outreach projects. 2. Monitoring/data collection: a) Contracting Parties to exchange information on how to collect effort data for small vessels and bycatch data. b) On the basis of the exchanged information Contracting Parties should identify ways how to collect the needed data in a cost-effective way making use of identified synergies to the extent possible. c) Contracting Parties to initiate (national/joint) projects to collect bycatch data on the basis of the EU MAP d) Contracting Parties to incentivise fishermen’s participation in REM studies 3. Consider management measures: The HELCOM BLUES project is developing risk maps, which are expected to be useful for this action. JWG BIRD should be involved in the implementation of this action. Contracting Parties to consider which relevant additional management measures are needed, and if appropriate initiate process for management measures within MPAs. | Regulatory or voluntary schemes are in place and being implemented, as appropriate, to protect key seabird areas and seasons by establishing appropriate fisheries measures in line with conservation objectives. (Joint and national)
Topic: Fish stock management
19 | S50 | National/Joint | Competent authorities to jointly further develop protective measures for Baltic Sea salmon to support the development of a new regional salmon management plan, and nationally establish salmon management plans by 2023, where appropriate. These management plans should be implemented by 2025 to achieve the set targets, including but not limited to smolt production, genetic diversity and distribution throughout the river habitat. In addition, nationally ensure that granting permits for activities in and near rivers does not compromise the ability to reach set river specific fish population targets. | Fish-M | WG Fish |  | B16, BSAC meetings and activities | A meeting of Fish-M should be organized during 2023 in order to consider the need of further development of protective measures for Baltic Sea salmon. A lead is needed for the joint part of this action to develop protective measures. The ICES WG on Baltic salmon and sea trout should be invited to provide input to the work on implementing this action. The European Commission has requested ICES to evaluate the existing Baltic Sea main basin salmon river list, with results expected at the earliest in 2023 or 2024. BALTFISH has agreed to continue the work on developing a regional salmon management plan, being aware that there is currently no related proposal from the European Commission. The BSAC fully supports cooperation between HELCOM BALTFISH and BSAC in the work of developing a long term management plan. | Protective measures for Baltic Sea salmon to support the development of a new regional salmon management plan have been further developed by 2023. (Joint) Long-term national management plans for salmon stocks are in place by 2023 and being implemented by 2025 and at least 10 threatened salmon rivers have active conservation. (National) National procedures are in place to ensure that granting permits for activities in and near rivers does not compromise the ability to reach set river specific fish population targets. (National)
20 | S52 | National/Joint | Define necessary complementary measures by 2024 in relevant policy (fisheries, environment etc.) areas to improve the size/age structure for fish stocks, including cod. | Lead needed | WG Fish | WG BioDiv | ICES, BALTFISH, BSAC | In 2023: Define and justify which fish species are to be targeted, jointly between WG Fish and WG BioDiv (2023). ICES Advice on lists of Commercial Fish and Shellfish species for reporting of MSFD D3 published on 19​ October 2022 is available and will be useful in the context of this action, when defining and justifying which species should be targeted. 2024: Identify a selection of effective and efficient measures (i.e. best practices) for improving status of fish stocks. Where relevant these should eventually be included in the HELCOM Restoration Action Plan. A lead is needed to further the fisheries part of this action. It is proposed that both FISH and WG BioDiv oversee this action, as the complementary measures to be defined are expected to stem from the areas of responsibility of both groups. | By end of 2024: Complementary measures are defined and can be implemented, in order to improve size/age structure, to reach healthy fish stocks.
21 | S54 | National/Joint | Share information among Contracting Parties, the Baltic Sea Fisheries Forum (BALTFISH) and Baltic Sea Advisory Council (BSAC) on non-lethal mitigation measures or other ways to manage seals-fisheries interactions and implement those measures by 2025, as appropriate. | Lead needed | WG Fish | EG Noise | B5 | A lead is needed to create toolbox or other means of sharing information. Involvement by BALTFISH, BSAC and EG MaMa useful in implementing the action. | HELCOM-BALTFISH toolbox, or other means of sharing information on non-lethal mitigation measures or ways to manage seals-fisheries interactions are in place (Joint supporting action) and such measures are being implemented, as appropriate. (National measure) . Overview of actions that are suitable within the existing legal framework.
Theme: Underwater noise
22 | S61 | Joint | Develop and implement guidelines for the design and use of acoustic deterrent devices to avoid detrimental impacts on the environment from underwater noise by 2024. | EG NOISE | WG Fish | EG MaMa | Other stakeholders such as ADD manufacturers | EG Noise should lead the development of Guidelines, especially related to ADDs used for other purposes than fisheries. To support this work, Contracting Parties should share possible information with meetings of the WG Fish on the purpose (e.g., offshore construction, aquaculture, fishing), and frequency of occurrence as well as evaluation of ADD use, types of devices used in different sectors as well as on finished, planned or foreseeable projects using ADDs, if available. Information should also be provided on whether the use of ADDs requires permits in the respective Contracting Parties. EG Noise. EU Member States have committed to provide information on impulsive underwater noise to an ICES registry. Unless permits to use ADDs are needed, information on their use may be scarce. However, if projects, studies etc. on the matter have been conducted, the outcomes of such should be shared as this information could be useful in developing guidelines. | Guidelines for the design and use of acoustic deterrent devices are in place and implemented in all Contracting Parties.
Theme: Sustainable aquaculture
23 |  | Joint | Develop and agree on BAT/BEP for Sustainable aquaculture and follow up as appropriate. | CG Aquaculture | WG Fish |  |  | BAT/BEP for sustainable aquaculture approved by 2023. Reporting format developed by 2024. Review and update Recommendation 37/3, as necessary. | BAT/BEP descriptions for sustainable aquaculture in the Baltic Sea by 2023. Reporting format for demonstrating compliance with Recommendation 37/3 developed. Recommendation 37/3 reviewed and updated, as necessary.
Other tasks
24 |  |  | Evaluation and reporting on implementation of BSAP actions under the responsibility of the working group. |  | WG Fish |  |  | WG Fish to review and update its workplan during 2024, for approval by HOD in December 2024. The review should include an evaluation to enable horizontal tracking of progress, identifying and tackling barriers to implementation as well as possible synergies or areas of cooperation with other working groups. | Updated workplan for 2025-2026. Identification of barriers to implementation as well as possible synergies or areas of cooperation with other working groups.
[1] DE/DK/PL MPA cluster consists of the Danish MPA area: “Adler Grund and Rønne Banke” (DK00VA261), German MPAs areas: “Adlergrund” (DE1251301), “Westliche Rönnebank” (DE1249301), “Pommersche Bucht mit Oderbank” (DE1652301), “Greifswalder Boddenrandschwelle und Teile der Pommerschen Bucht” (DE1749302), “Pommersche Bucht” (DE1552401) and Polish MPAs areas: “Ostoja na Zatoce Pomorskiej” (PLH990002), “Wolin i Uznam” (PLH320019).