## Sheet1
Approved via correspondence in September 2023 by the Heads of Delegations of the EU and the Contracting Parties to HELCOM that are also Member States of the EU
No | type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
General/recurring tasks
1 |  |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group |  | WG Sea-based pressures |  |  | Initiate the discussion in 2023 | Plan on how to address the implementation, reporting and revision of the Recommendations by the end of 2024
Marine litter
2 |  |  | Coordinate the implementation of the HELCOM Regional Action Plan on Marine Litter | EG Marine Litter | WG Sea-based pressures |  | The actions in the Action Plan have individual leads, implementation plans and follow-up | The first workshop to be organized on 17 April 2023 back-to-back with the WG Sea-based Pressures meeting | Organization of biannual coordinating workshops
Tasks stemming from the 2021 BSAP, where HL codes refer to BSAP action coding
3 |  | HL31 | Improve the evidence base on the impact of marine litter on the Baltic Sea region in order to develop and agree on new measures by 2025. (Joint) | Lead needed | WG Sea-based pressures | EG Marine litter |  | The contents of the Alfred-Wegener-Institute database, “litterbase”, have been utilized as starting point to compile publications on the impact of marine litter to biota in the Baltic Sea. From the almost 2000 publications contained in the database, only 21 referred to the Baltic Sea. The list has been considered and there is a need to further complement it with support provided by Germany. Then, to evaluate the possibility of identifying measures to address specific litter items which are not already covered by individual actions in the RAP ML. IC WS RAP ML 2-2023 recommended that the focus should be on measures already agreed as part of the RAP ML and BSAP. The Session, however, noted that the further development of biota indicators would be useful. | The evidence base has been improved by addressing identified knowledge gaps and the information has been published by 2025.
4 |  | HL32 | Agree on core indicators and harmonised monitoring methods to evaluate quantities, composition, distribution and sources (including riverine input), of marine litter, including microlitter, by 2022, where applicable and for the rest no later than 2026. Work should be done in close coordination with work undertaken by Contracting Parties in other relevant fora, such as the Technical Group on marine litter under the Marine Strategy Framework Directive. (Joint) | Lead needed | WG Sea-based pressures | EG Marine litter |  | There is still no information on whether the project application “Filling gaps in marine litter monitoring in the Baltic Sea” (LITTERGAPS) re-submitted to the Interreg Baltic Sea call on 13 March 2023 has been granted. However, if granted, the project will contribute to further advance on seafloor, pellets on beaches, riverine macro and microlitter monitoring, as well as on microlitter ingestion by mussels. To follow up on the work of (i) the EU TG on updating the Guidance for Marine Litter Monitoring, which is envisaged to address the following matrices: beach/coastline litter, floating Litter, seafloor litter, microlitter, ingestion and entanglement; a complete version of the whole draft is envisaged in June 2023; (ii) OSPAR action “Action A.3.1 (S4.07.01) Monitor, prevent and reduce riverine inputs of macro litter to the marine environment and share knowledge on micro litter monitoring in rivers.” in the second Action Plan on Marine Litter. | Fully developed core indicators are available by 2026. Harmonised monitoring methods are agreed through the development and approval of regional monitoring guidelines by 2026.
Underwater noise
5 |  |  | Coordinate the implementation of the HELCOM Regional Action Plan on Underwater Noise | EG Noise | WG Sea-based pressures |  | The actions in the action plan have individual leads, implementation plans and follow-up | The first workshop to be organized in October 2023 back-to-back with the WG Sea-based Pressures meeting. When implementing the RAP Noise, it is recommended to make use of the analysis of the possible overlap between the RAP Noise and actions on noise in the BSAP (document 6-2). | Organization of biannual coordinating workshops
Tasks stemming from the 2021 BSAP, where S codes refer to BSAP action coding
6 |  | S55 | Identify at the latest by 2025, as well as regularly update every two years, mitigation measures according to Best Environmental Practice and Best Available Technique for continuous underwater noise in the Baltic Sea and implement thereafter in line with recommendations and regulations of the international Maritime Organization (IMO). (Joint) | Lead needed | WG Maritime | WG Sea based pressures, EG Noise |  | Action related to action 19[1] in the RAP Noise. The revision of the IMO Guidelines is currently ongoing (2022-2023). The IMO Sub-Committee on Ship Design and Construction (SDC) in January 2023 agreed the revised guidelines, for submission to the upcoming Marine Environment Protection Committee (MEPC 80) on 3-7 July 2023 for approval. The correspondence group led by Canada on the matter has been re-stablished. HELCOM countries contribution to the process would ensure alignment A53with HELCOM work. Denmark, EC and Finland are part of the group. The Secretariat has also re-joined the correspondence group as observer to be able to follow up the process and inform WG Sea-based pressures accordingly. Next steps proposed: follow up on the implementation of this action. Additional information is available in the Maritime workplan 2022-2023. | BAT and BEP are identified and implemented at the latest by 2025.
7 |  | S57 | Start working as soon as possible towards regionally coordinated actions on underwater noise, aiming in the long term towards addressing adverse effects of underwater noise on marine species identified as sensitive to noise, whilst safeguarding the potential of the Baltic Sea for sustainable human activities by: a) Supporting a swift implementation of the Regional Action Plan on Underwater Noise b) Initiating and supporting pilot projects to study efficacy of vessel slow down, rerouting and other operational measures, on noise emissions and responses of target species by the end of 2026. Results are to be communicated to the International Maritime Organization (IMO) for follow-up and further action. c) By 2027 Mapping the contribution of recreational craft to the noise in the marine environment; supporting studies on efficiency of mitigation measures, such as speed limitations and time-area restrictions; and studies on impact from echo sounders and fish-finders. Based on available evidence and new results, developing guidelines for implementing regulation to reduce impact on sensitive species. Simultaneously, establishing a discussion with the industry and relevant international standardization bodies and aiming at developing industry or/and application standards for underwater noise emissions of engines with respect to recreational craft, echo-sounders and fish finders, which can be utilized in national regulation of activities in marine protected areas (MPAs) and other noise sensitive areas in the Baltic Sea. (National/joint)) | Lead needed. Could be several lead countries for various elements of implementation (e.g. point b and c). Denmark [and Germany] to take partial lead of S57 part b). | WG Maritime | WG Sea based pressures; EG Noise |  | Next steps proposed: Re. a): actions in the RAP Noise to be prioritized as well as a short list of actions to be addressed in the first place have been identified. Follow up on information on the status of the implementation of the RAP Noise to be provided on regularly basis to WG Sea-based pressures. Re. b) and c) follow up on the implementation of this action. Additional information is available in the Maritime workplan 2022-2023. | Implementation of the Regional Action Plan on Underwater Noise. (Joint and national). In the Baltic Sea region, at least one pilot project has been initiated by the end of 2026 to study efficacy of vessel slow down, rerouting and other operational measures, on noise emissions and responses of target species. Results of such studies have been communicated to the IMO. (Joint measure) Information on the contribution of recreational craft (including the use of echo sounders and fish finders) to underwater noise in the marine environment is available. Discussions with the industry and relevant standardization bodies have been established, aiming at developing industry and/or application standards for underwater noise emissions of engines with respect to recreational craft, echo-sounders and fish finders, which can be utilized for national regulation of activities in marine protected areas (MPAs) and other noise sensitive areas in the Baltic Sea. (Joint supporting action)
8 |  | S58 | Study by 2026 the impacts of continuous underwater noise from the installation, operation and decommissioning of offshore windfarms on marine biota, including cumulative effects of multiple windfarms. Based on the results, take relevant action, if necessary, in developing appropriate mitigation measures for the continuous underwater noise generated by offshore wind farms by 2029. (Joint) | Lead needed, SE and CCB to support | WG Sea-based pressures | HELCOM-VASAB MSP; EG Noise; EG MaMA |  | To prepare a HELCOM project proposal on impacts of continuous underwater noise from offshore windfarms. Identify a call where such a project proposal could be submitted to and if not identified during the upcoming years, HELCOM countries to fund that project jointly so that results can be available in 2026. | By 2026 study on the impacts of continuous underwater noise from offshore windfarms, including cumulative effects of multiple windfarms, is conducted. If appropriate, by 2029 relevant action is taken to develop appropriate mitigation measures
9 |  | S60 | Identify at the latest by 2023, as well as regularly update every two years, mitigation measures according to Best Environmental Practice and Best Available Technique for impulsive underwater noise in the Baltic Sea and implement thereafter without delay. (Joint) | Lead needed, EE, SE and CCB to support. | WG Sea-based pressures | EG Noise |  | Action connected with action 6[2] in the RAP Noise, implementation process is to be led and/or actively promoted by Germany. | BAT/BEP guidelines for impulsive noise sources are updated.
10 |  | S62 | Develop and implement threshold values and assessment methods for adverse effect of impulsive and ambient noise for marine life, in cooperation with OSPAR, the EU and other relevant expert groups, by 2023 at latest for marine mammals and by 2026 for other relevant species groups. (Joint) | Lead needed, SE to support the second part of the action related to other relevant species groups. EE to support. | WG Sea-based pressures | EG Noise |  | Related to action 5[3] and 18[4] of the RAP Noise. HELCOM pre-core indicator report on impulsive noise and on continuous noise, as well as on the noise section of the HELCOM Thematic assessment of hazardous substances, marine litter, underwater noise and non-indigenous species 2016-2021 are available. However, additional funding is needed to advance on the development of the pre[1]core indicators to core-indicators as well as on the second part of the action related to other relevant species groups. EU TG Noise will partially support HELCOM in this task. | By 2023 threshold values and assessment methods for adverse effect of impulsive and ambient noise for marine mammals have been developed and implemented. By 2026 threshold values and assessment methods for adverse effect of impulsive and ambient noise for other relevant species groups have been developed and implemented.
Seabed loss and disturbance
11 |  |  | Compile data on dredging/depositing operations at sea reported at intervals specified in the Guidelines for Management of Dredged Material at Sea. Support the consolidated reporting to the London Convention and its 1996 Protocol utilizing the reported data on handling of dredged material at sea. | EG DREDS | WG Sea-based pressures |  |  |  | BSEFS on dredging and depositing operations at sea are published at intervals specified in the Guidelines for Management of Dredged Material at Sea, and the information is used for annual consolidated reporting to London convention/London Protocol on behalf of Contracting Parties.
Tasks steaming from the 2021 BSAP, where S, B and HT codes refer to BSAP action coding
12 |  | S65 | By 2026 implement a common approach to address and where possible minimize the loss of and disturbance to seabed habitats caused by human activities. (National/joint) | Lead needed | WG Sea-based pressures | EG Benthic; EG DreDS |  |  | A common approach to addressing loss and disturbance to seabed habitats has been developed and regionally agreed. (Joint supporting action). A common approach to addressing loss and disturbance to seabed habitats has been implemented. (National measure)
13 |  | S66 | Regularly update and improve the HELCOM Recommendation and Guideline for handling dredged material at sea using the best available knowledge to minimize environmental impact of these activities further developing Best Environmental Practice (BEP) and Best Available Technique (BAT) for dredging and depositing operations. (Joint) | EG DreDS | WG Sea-based pressures |  |  | Draft revised Guidelines under development by EG DREDS. Draft revised Guidelines to be considered by WG Sea-based pressures in autumn 2023, with a view to their finalization and approval. IC PRESSURE 1-2022 invited Contracting Parties to consider if additional nominations are needed to broaden the EG DREDS expertise related to BSAP implementation. | HELCOM Recommendation and Guidelines for management of dredged material at sea are improved and maintained up to date. BAT/BEP to minimize environmental impact of dredging/depositing operations is developed.
14 |  | S67 | Define the characteristics of benthic habitats, develop core indicators and undertake an integrated assessment of […] distribution and extent of loss, no later than 2023, leading to the identification of measures to reduce adverse effects where needed. Work should be done in close cooperation with work undertaken by Contracting Parties in other relevant fora, taking into account activities in EU Technical Group on seabed habitats and sea-floor integrity (TG Seabed), and considering the ICES advice on a sea-floor assessment process. (Joint) | Indicator leads | WG BioDiv | WG Sea-based pressures, EG Benthic; EG DreDS |  | This work is ongoing under HOLAS 3. 2023/2024: review and gap analysis following HOLAS 3, specifically with regards to distribution and extent of loss and disturbance of seabed habitats, and elaboration of a workplan for the development work towards HOLAS 4. EG DREDS to follow up and to provide comments during the process when needed. "2024/2025: elaborate proposed measures for reducing loss and disturbance of seabed habitats, towards the MM planned for 2026. The work on indicators and assessment of the benthic habitats structure and function is primarily done under WG BioDiv. " | By end of 2023 HELCOM indicators evaluating the distribution and extend of loss and disturbance have been developed and operationalized. By end of 2023 assessment of benthic habitats has been undertaken. By end of 2025, where needed, measures to reduce adverse effects have been identified. Relevant new measures adopted by Ministerial Meeting in 2026
15 |  | S68 | Develop a map service for lost and disturbed habitats under HELCOM Map and Data Service by 2024. (Joint) | Secretariat to maintain map service | WG Sea-based pressures |  | DG MARE ReMap project, TG SEABED, PERMAGOV project | 2023: Scope the needs for the map service. Scope technical possibilities and limitations, including the possibility of using the SPIA tool to do this. Explore the possibly to utilize the work under the ReMap and PERMAGOV projects for direct development/alternative external funding. . Action partially covered by the Horizon project PROTECT which HELCOM is partner to. 2024: Execute development. | By end of 2024 a map service illustrating lost and disturbed habitats has been developed under HELCOM Map and Data Service.
16 |  | B26 | Protect key ecosystem components including habitat forming species by 2030, by: - assessing the state of, and threats to these key ecosystem components by 2023 - implement effective and relevant threat mitigation measures based on the threat and state assessments, including restricting human activities associated with causing physical loss or disturbance, by 2030 - identifying suitable measures and types of habitats, biotopes and key ecosystem components for passive or active restoration by 2025 and implementing programmes for restoration as outlined in the HELCOM Restoration Action plan by 2030. | HOLAS | WG BioDiv; WG Sea-based pressures (on mitigation measures) | WG Sea-based pressures |  | Regularly exchange information on the national progress and share best practices to implement effective and relevant threat mitigation measures, including restricting human activities associated with causing physical loss or disturbance, by 2030. | By 2023 currently prioritized conservation features have been complemented with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services. (Joint supporting action). By 2023 an assessment, is ready and publicly available. (Joint supporting action) By 2030 effective measures are in place to mitigate threats and pressures, to improve the status of the identified key ecosystem components. (National measure) By 2025 suitable areas for restoration of the key system components, including habitat forming species, have been identified. (Joint supporting action)
Munitions, wrecks and hazardous submerged objects
17 |  | S34 | Develop Best Environmental Practice (BEP) for comprehensive risk assessment of munitions, wrecks and hazardous submerged objects by 2025 and implement the Best Available Techniques (BAT) for environmentally sound and safe management by 2028. (Joint) | Germany is considering the possibility of being a lead for the implementation of this action. Poland is willing to support the implementation of this action but further national consultations are needed.Responsible: WG Sea-based pressures | EG Submerged | WG Sea-based pressures |  | EG SUBMERGED to consider information regarding existing resources (decision support systems, risk assessments, data, data needs etc.) which could be used as a basis for the implementation of this action. This could include resources from the DAIMON project, upcoming projects and national risk assessments such as VRAKA (Sweden). WG Sea-based pressures to follow progress and provide input as appropriate. EG SUBMERGED 3-2023 noted that the task is a priority for the expert group and that a HORIZON Europe call is currently out and could provide input in relation to this task. | By 2025 BEP/BAT and control of threats posed by munitions, wrecks and other hazardous submerged objects in the Baltic Sea are in place and by 2028 are being implemented for environmentally sound and safe management.
18 |  | S35 | Maintain the HELCOM thematic assessment on hazardous submerged objects as a living document, including munitions and wrecks and regularly update the information in the HELCOM Map and Data Service by 2024. (Joint) | Finland is considering taking the lead on the wrecks part of the Submerged Assessment. Sweden is willing to provide text and comments to the wrecks part. | EG Submerged | WG Sea-based pressures |  | Follow up on and keep the Submerged Assessment up to date. Finland and other Contracting Parties to provide material to EG SUBMERGED for draft Submerged Assessment related to wrecks. New data regarding mines in the Baltic Sea to be approved for approval to include in the MADS during 2023. | Up to date HELCOM Submerged Assessment is published. Updated information in the HELCOM Map and Data Service is published.
Hot spots
19 |  | HT24 | Consider designating HELCOM hot spots by 2025 on the basis of identified additional sources of major negative impact on the Baltic marine ecosystem, starting with the development of specifying criteria for the designation and deletion of the hot spots by 2023, and based on those criteria, initiate and undertake targeted measures with the aim of eliminating where possible such new hot spots. (National/joint) | Germany (nutrients) | WG Source to sea; WG Sea-based pressures |  |  | To clarify ambition level and definitions within a HELCOM Workshop in spring 2023 (IC WS HOT SPOTS 1-2023). Ad hoc drafting group to be established after the workshop to make a proposal in autumn 2023. | HELCOM criteria for designation and deletion of hot spots is established by 2023. (Joint supporting action). New hot spots are designated by 2025. (Joint/National supporting action) Targeted measures are initiated to eliminate, where possible, the newly designated hot spots. (National measure)
Monitoring
20 |  | HT6 | Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements. | CP leads as identified under WG GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDiv; WG Source to sea; WG Sea-based pressures; EG Haz; EG Eutro; EG MaMa; EG Marine Litter; EG Noise; PEG; EG Zoo; JWG Bird |  | By 2024 perform a gap analysis of the current Monitoring Manual and monitoring programmes with respect to pressures originating at sea and agree how the gaps can best be addressed as part of the next update. Being the process to update the sea-based pressures related monitoring programmes in autumn 2024 to ensure the review and update is finalized and the updated monitoring manual and programmes are published in early 2026, in good time before the national Art.11 reporting concludes. | Updated monitoring programmes are available every six years in line with what is specified in the action.
21 |  |  | Contribute to and guide the development of sea-based pressures related regional monitoring guidelines. | Lead needed | WG Sea-based pressures |  |  | Review relevant monitoring guidelines related to sea-based pressures. Draft new monitoring guidelines as may be needed based on updates to the HELCOM monitoring programmes. | Up to date monitoring guidelines in place.
22 |  |  | Establish persistent regular data flows and data management for all sea based pressures data needed for HELCOM assessment and tracking purposes. | Lead needed | WG Sea-based pressures |  |  | Using the review of the HOLAS 3 (2023), data reporting and processes as a basis, identify gaps in dataflows and infrastructure. Analyze the underlying causes and identify solutions. Implement solutions to secure improved, consistent dataflows. | Lower resource requirements long term due to automatised data reporting. Improved access to data and information across the region. Enabling automatising assessment procedure.
Indicators
23 |  | B33 | By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). | Secretariat | WG GEAR | WG BioDiv; WG Source to sea; WG Sea-based pressures |  | 2023-2024: Support the review and gap analysis following HOLAS 3, looking at both the policy and the technical aspects of the inclusion, and assessment, of pressures from litter, disturbance and loss of the seabed, submerged hazardous objects, non-indigenous species and level of impulsive and continuous underwater noise, as well as the working structure and process. Based on this review, identify and prioritize work to be done with respect of sea-based pressures under the preparatory phase for HOLAS 4 and prepare and implement corresponding workplans to target the gaps and ensure work progresses. | By 2024 a Roadmap for how to fill gaps for both ecosystem components and pressures is developed. By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available
Other tasks
24 |  |  | Plan for the implementation of BSAP actions with later target years |  | WG Sea-based pressures |  |  | In the 2024 autumn meeting of the WG, review the workplan, include actions with target years in the next 2 year work period and elaborate associated tasks and next steps. | Up-to-date workplan available to guide the work of the group.
25 |  |  | Evaluation and reporting on implementation of BSAP actions under the responsibility of the working group. |  | WG Sea-based pressures |  |  | WG Sea-based pressures to review and update its workplan during 2024, for approval by HOD in December 2024. The review should include an evaluation to enable horizontal tracking of progress, identifying and tackling barriers to implementation as well as possible synergies or areas of cooperation with other working groups. A common template developed by WG GEAR should be used for reporting of progress and identifying actions where further support is needed. | Updated workplan for 2025-2026. Identification of barriers to implementation as well as possible synergies or areas of cooperation with other working groups.
[1] “Expand and improve the existing and potential operational and technical measures to reduce the impact of continuous noise to form a basis for common guidelines on management. Suitable technical measures to reduce input of continuous noise should be identified (BAT/BEP), based on a scientific justification, and taking into account socioeconomic impact.”
[2] “Identify Best Available Technologies (BAT) related to the abatement of impulsive noise. Among these collect existing national regulations and guidelines aimed to reduce the impact of underwater impulsive noise on the ecosystems of the Baltic Sea and related observations in order to form relevant HELCOM guidelines.”
[3] ”Develop and implement one or more HELCOM impact indicators for impulsive noise”
[4] “Develop and implement one or more HELCOM impact indicators for continuous low-frequency noise.”