## Sheet1
Approved via correspondence in September 2023 by the Heads of Delegations of the EU and the Contracting Parties to HELCOM that are also Member States of the EU
No | Type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
General/recurring tasks
1 |  |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group | Co-lead: The relevant expert groups under WG Source to sea | WG Source to sea |  | BSAP action HL4 led by Finland | Initiate the discussion in 2023. Agree on reporting format for Recommendation 41/3 by end of 2023. Report on the implementation of Recommendation 41/3 on the Use of National Manure Standards in 2024 | Plan on how to address the implementation, reporting and revision of the Recommendations by the end of 2024
Agriculture
2 |  |  | Discuss and share knowledge on the climate change impact on agricultural practices in the Baltic Sea, mitigation and adaptation measures |  | WG Source to sea |  |  | Sharing information on national activities and projects in the WG Source to sea meetings | Collecting the information on climate change and agriculture shared in group meetings in a dedicated workspace. The group has contributed to relevant processes in HELCOM.
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
3 |  | E8 | E8 – Develop by 2025 and apply by 2027 the best practices to improve soil structure and aggregate stability on clay soils to reduce phosphorus losses from agricultural lands, for example by using soil structure lime or gypsum. (National/joint) | Lead: needed | WG Source to sea |  |  | As a first step, collect material on best practices to improve soil structure and aggregate stability on clay soils to reduce phosphorus losses in autumn 2023. Support from the material in the policy brief on rural water management. Half-day workshop in spring 2023 to support the implementation of action E8. | By 2025 best practices to improve soil structure and aggregate stability on clay soils to reduce phosphorus losses from agricultural lands are compiled in a regional document. (Joint). By 2027 the best practices are applied nationally in areas where the measures are applicable e.g. with the help of support schemes, regulation or guidelines. (National)
4 |  | E11 | E11 - Improve knowledge exchange by establishing dialogue between farmers, authorities and decision makers. (National/joint) | CCB supported by Chair and Secretariat | WG Source to sea |  | EUSBRS PA Nutri and PA Bioeconomy, WWF Baltic Farmer of the Year Award | The implementation of the BSAP actions regarding agriculture could be the topic of the first regional forum. Impact of climate change on farmers could also be considered as a topic for a regional forum. | Regular Baltic Sea regional forum to exchange knowledge between farmers, authorities and decision makers is organized. (Joint). Ways or means for regular exchange of knowledge nationally are ensured. (National)
5 |  | E13 | E13 - Develop by 2025 recommendations for Best Available Technology (BAT)/Best Environmental Practice (BEP) to reduce ammonia and greenhouse gas emissions from livestock housing, manure storage and spreading. (Joint) | Regional project or drafting group | WG Source to sea |  | Actions E13-E14 are closely connected and are also linked to action E20, to follow the EU Industrial Emissions Directive revision | Further developed concept to be considered in spring 2023. Regional project or drafting group to contribute to the drafting. | Regional document on BAT/BEP to reduce ammonia and greenhouse gas emissions from livestock housing, manure storage and spreading is developed.
6 |  | E14 | E14 - Develop by 2025 recommendations for manure management specifically for horses, sheep, goats, and fur farming. (Joint) | Regional project or drafting group | WG Source to sea |  | Actions E13-E14 are closely connected and are also linked to action E20 | Further developed concept to be considered in spring 2023. Regional project or drafting group to contribute to the drafting. | Regional document such as Recommendation or guideline for manure management specifically for horses, sheep, goats, and fur farming is developed.
7 |  | E18 | E18 – Investigate opportunities for taxation of mineral fertiliser and/or taxation of nitrogen surplus and/or payments for agri-environment measures by 2024 and implement them building on the experiences available in various countries. (National/joint) | Secretariat | WG Source to sea |  | CAP strategic plans | Further development of the first draft of the report and collection of possible additional material. | By 2024 a HELCOM report on experiences in the Baltic Sea region countries and the effects of financial instruments such as taxation of mineral fertiliser and/or taxation of nitrogen surplus and/or payments for agri-environment measures to enhance nutrient recycling and reduce nutrient losses is published. (Joint). Suitable measures are implemented nationally building on the experiences available in various countries. (National)
8 |  | E20 | E20 - Revise by 2023 the HELCOM Recommendation 24/3 on “Measures aimed at the reduction of emissions and discharges from agriculture” ensuring reduction of agricultural ammonia emissions and considering relevant Best Available Technology (BAT) and Best Environmental Practice (BEP). (Joint) | Drafting group | WG Source to sea |  | BSAP actions E13 and E14 are closely connected | Drafting group to develop the first full draft in spring 2023. Finalizing the revision of the Recommendation in autumn 2023. | Revised HELCOM Recommendation 24/3 on “Measures aimed at the reduction of emissions and discharges from agriculture” is adopted, ensuring reduction of agricultural ammonia emissions and considering relevant BAT and BEP.
Pollution Load Compilations (PLCs)
9 |  |  | Annual compilation of airborne inputs of hazardous substances to the Baltic Sea | PLC-8 project | WG Source to sea | PLC-Air Centre EMEP; EG RedCore |  | PLC-8 project to produce annual report and Baltic Sea Environment Fact Sheet. Consider inclusion of new and/or rotation of already covered substances in accordance with the HELCOM priorities and data availability. | Baltic Sea Environment Fact Sheet (BSEFS) on selected inputs of hazardous substances are published annually.
10 |  |  | Regular update of the HELCOM information resources to collect, store and provide access to the data on input of nutrients and selected hazardous substances into the Baltic Sea including reporting web applications and relevant HELCOM GIS map services. | BNI (Database Host) | EG RedCore | PLC Data Manager; Secretariat |  |  | Continuous with annual update checks with the PLC-8 project Implementation Group
11 |  |  | Thematic report assessing the sources of nutrient input to the Baltic Sea based on 2021 data | PLC-8 project | WG Source to sea | EG RedCore |  | Part of the PLC-8 project plan (task 17) with timetable | Thematic report is published as BSEP
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
12 |  | E1 | E1 - Submit an account listing, as detailed as possible, the planned and implemented measures in different sectors and catchments alongside an estimation of their effectiveness to HELCOM by 2023 in order to demonstrate whether national net nutrient input ceilings can be achieved with these measures. (National/joint) | PLC-8 project | WG Source to sea | EG RedCore |  | PLC-8 project and EG RedCore to set the requirements for submission of lists of measures and available knowledge on costs and effects. Countries to submit the relevant data and information in spring 2023. PLC-8 project to draft the thematic report. | Lists of measures and available knowledge on costs and effects is submitted by each Contracting Party. (National). PLC-8 thematic report on effectiveness of measures to reduce nutrient inputs is published. (Joint)
13 |  | E2 | E2 - Assess progress towards maximum aIlowable inputs annually and national input ceilings every second year, to follow up implementation of regional and national targets for inputs of nutrients. (Joint) | PLC-8 project | WG Source to sea | EG RedCore; BNI |  | PLC-8 project to produce the assessments. Annual assessment: progress towards MAI by December 2023 and 2024. Biannual assessment: Progress towards NIC by December 2024. | Annual core indicator on progress toward MAI including assessment data is published. Policy message on progress towards NIC including technical annexes and assessment data is published every second year.
14 |  | E3 | E3 - Provide timely sufficient and consistent data on nutrient loads to the Baltic Sea, ensuring reliability of the follow-up system, by maintaining and enhancing monitoring programmes and networks striving for harmonized methods to estimate nutrient inputs, including from unmonitored areas. (National/joint) | Lead: PLC-8 project | WG Source to sea | EG RedCore, EMEP MSC-W, BNI, PLC data manager |  | Countries to submit the annual data according to the schedule set in the PLC-Water Guidelines. EMEP MSC-W to provide the data on airborne deposition of nitrogen on the Baltic Sea sub-basins and provide the draft BSEFS for approval by WG Source to sea. The PLC-8 project to draft the annual waterborne BSEFS and WG Source to sea to approve. | The PLC database is updated annually. (National/joint). Baltic Sea Environmental Fact Sheet (BSEFS) on waterborne nutrient inputs and annual BSEFS on atmospheric nitrogen inputs are published annually. (Joint)
15 |  | E4 | E4 – Strengthen cooperation with river basin management authorities of non-HELCOM countries through official agreements addressing transboundary waterborne nutrient inputs from non-Contracting Parties. (National/joint) | Lead: needed | Responsible WG Source to sea |  |  | Workshop/expert meeting to be organized [in 2024] to prepare for agreeing on the cooperation. | Agreements addressing transboundary waterborne nutrient inputs from non-Contracting Parties are adopted. (National). Common workshops/expert meetings are arranged and all levels of river management are included in this cooperation (National/joint)
Wastewater treatment
16 |  |  | Review and possible revision of HELCOM Recommendation 38/1 | Lead: needed | WG Source to sea |  |  | Review to begin after the EU Sewage Sludge Directive update process is completed in 2023. Consider the reporting format with the possible revision process of the Recommendation 38/1. Contracting Parties to submit their EU sewage sludge reporting documents also to the Secretariat in 2023. | HELCOM Recommendation 38/1 reviewed, and if deemed necessary, revised.
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
17 |  | E23 | E23 – Strengthen the HELCOM Recommendation 28E/5 on municipal wastewater treatment by 2027. (Joint) | Co-leads: Germany | WG Source to sea (nutrients, hazardous substances), WG Sea-based pressures (litter) |  |  | One of the most important nutrient actions to reduce also e.g. microlitter and hazardous substances but needs a lot of expertise. Ambition level to be set early in the process. The EU UWWTD revision process to be taken into account. To establish a drafting group in spring 2023 | Revised or new Recommendation with stricter requirements is adopted.
18 |  | E26 | E26 – Cooperate with relevant Policy Areas of the EU Strategy for the Baltic Sea Region (EUSBSR) regarding e.g. wastewater treatment plants (under “save the sea” objective of the EUSBSR) as well as other regional policies to engage a wider network of stakeholders into cooperation to achieve the BSAP targets. (Joint) | Secretariat | WG Source to sea |  |  | Continuous work as an observer of the PA Nutri Steering Group. Continuous work with CP representatives in the PA Nutri Steering Group | HELCOM participates in the Policy Areas’ steering committees. The Policy Area coordinators participate in HELCOM meetings and outcomes of projects and processes supported by Policy Areas are considered at relevant HELCOM Working Group meetings.
19 |  | E28 | E28 – Build a knowledge base to target the reduction of phosphorus in detergents for industrial & institutional use. By 2025, develop and publish a HELCOM progress report about best available techniques, alternative builders, especially on their use, environmental effects and effectiveness. (Joint) | Co-lead: Germany | WG Source to sea |  |  | Germany to contribute with BAT study. Synchronising with EU processes needed. Important to engage the industry in the studies. | HELCOM report on best available techniques (BAT), alternative builders, especially on their use, environmental effects and effectiveness to target the reduction of phosphorus in detergents for industrial & institutional use.
Nutrient recycling
20 |  | (E30) | Coordinate the implementation of the Baltic Sea Regional Nutrient Recycling Strategy |  | WG Source to sea |  |  | Related BSAP actions have individual target years and criteria, but not all the sub-objectives or possible measures in the Strategy are included in the BSAP. Regular discussions at the WG Source to sea meetings to coordinate the implementation with possible workshops back-to-back with WG Source to sea meetings. | The strategy has been implemented by 2027.
21 |  |  | Develop guidelines/ recommendation on nutrient accounting at farm level | Drrafting gorup | WG Source to sea |  | BSAP action E31 | Finalizing the drafting of the guidelines by the end of 2023. Decide whether the guidelines will be implemented via Recommendation. The task supports the implementation of BSAP action E31. | Guidelines or Recommendation on nutrient accounting at farm level are adopted in spring 2024.
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
22 |  | E32 | E32 – Enhance the use of recycled nutrients in agriculture making use of best available technologies and fertilize according to crop needs. (National/joint) | Lead: needed | WG Source to sea |  | BSAP action E33 | Interreg Baltic Sea Region core project funding is applied in spring 2023. Joint regional project to possibly support the evaluation of substitution of mineral fertilizers by recycled nutrients. | Support schemes and advice are in place to enhance the use of recycled nutrients in agriculture making use of best available technologies and fertilizing according to crop needs. (National). Evaluation of substitution of mineral fertilizers by recycled nutrients is carried out. (Joint)
23 |  | E33 | E33 – Develop by 2027 safety requirements for recycled fertilizer products and minimise the occurrence of harmful compounds in these products to comply with the requirements. (National/joint) | Lead: needed | WG Source to sea |  | LEX4BIO project, BSAP action E32 | Interreg Baltic Sea Region core project funding is applied in spring 2023. Joint regional project to possibly support the development of the safety requirement. | Regional document on the safety requirements for recycled fertilizer products is developed. (Joint). Compliance with the requirements is ensured nationally. (National)
24 |  | E36 | E36 – Enhance cooperation and share experiences between sectors and actors to create a holistic view on sustainable food systems including nutrient recycling across sectors. (National/joint) | Lead: needed | WG Source to sea |  |  | Interreg Baltic Sea Region core project funding is applied in spring 2023. Joint regional project to possibly support organization of events. | Identification of sectors and organizations that should be part of the national discussion on nutrient recycling. (National). Baltic Sea regional and national conferences, webinars, visits, collaboration with researchers etc. are organized to share experiences and exchange knowledge between sectors and actors. (National and joint)
Possible point sources of nutrients
25 |  |  | Developing the monitoring and management of phosphogypsum stacks | EG RedCore | WG Source to sea |  |  | To establish a technical advisory group including the fertilizer industry for starting the drafting process on the revision of the HELCOM Recommendation 17/6, taking into account the available model documents from other regions | Report and possible update of the Recommendation 17/6 on phosphogypsum management
Tasks stemming from the 2021 BSAP, where HT, HL and B codes refer to BSAP action coding
Hot spots
26 |  | HT24 | HT24 – Consider designating HELCOM hot spots by 2025 on the basis of identified additional sources of major negative impact on the Baltic marine ecosystem, starting with the development of specifying criteria for the designation and deletion of the hot spots by 2023, and based on those criteria, initiate and undertake targeted measures with the aim of eliminating where possible such new hot spots. (National/joint) | Germany (nutrients) | WG Source to sea; WG Sea-based pressures |  |  | To clarify ambition level and definitions within a HELCOM Workshop in spring 2023. Ad hoc drafting group to be established after the workshop to make a proposal in autumn 2023. | HELCOM criteria for designation and deletion of hot spots is established by 2023. (Joint supporting action). New hot spots are designated by 2025. (Joint/National supporting action) Targeted measures are initiated to eliminate, where possible, the newly designated hot spots. (National measure)
27 |  | HT26 | HT26 – Enhance cooperation with non-HELCOM countries in removing existing hot spots and designate new hot spots applying HELCOM criteria and facilitate undertaking all possible measures to eliminate them. (Joint) | Lead: needed | WG Source to sea |  |  | EUSBSR PA Nutri has proposed cooperation and organizes a facilitating event in 2023. | Elimination of the remaining hot spots in non-HELCOM countries identified by the Baltic Sea Joint Comprehensive Environmental Action Programme. Designation of new hot spots in non-HELCOM countries and their possible deletion from the hot spot list.
Hazardous substances
28 |  | HL1 | HL1 - Develop a regional strategic approach and, on the basis of that approach, an action plan for HELCOM work on hazardous substances by 2024. (Joint) | EG HAZ Strategic/holistic sub-team, Secretariat (HAPhazard project) | WG Source to sea | EG HAZ |  | The development of the strategic approach and action plan to progress according to the detailed plan prepared by the project and EG HAZ Strategic/holistic sub-team. WG Source to sea to guide the work. | Regional strategic approach on hazardous substances is developed. Regional action plan on hazardous substances is adopted.
29 |  | HL3 | HL3 - Submit to HELCOM by 2023 an account listing, as detailed as possible, the planned and implemented measures to reduce releases of hazardous substances in the environment, including available knowledge on their effects. (National/joint) | EG HAZ measures sub-team | WG Source to sea | EG HAZ |  | Countries to submit the information based on the instructions by EG HAZ. EG HAZ/project to conduct the analysis | Lists of measures and available knowledge on costs and effects is reported to HELCOM. (National). An analysis of the reported information is published by HELCOM. (Joint)
30 |  | HL7 | HL7 - Launch educational and information campaigns by 2025 to raise public awareness regarding responsible handling of hazardous substances in household chemicals and articles to prevent their release into the environment. (National/joint) | EG HAZ measures sub-team | WG Source to sea | EG HAZ | BSAP actions HL5 and HL25 | EG HAZ to agree on the focus (substances and target audience) also noting the results from the PreEMPT project, the NonHazCity project materials as well as other relevant national materials that could be utilized. EG HAZ to make the first draft of the guidelines/ recommendations, WG Source to sea to provide guidance. | Regional guidelines/ recommendations for general public and visual outreach material encouraging environmentally responsible selection of products and handling of chemicals in households are published. (Joint). National or local education and outreach campaigns for general public encouraging environmentally responsible selection of products and handling of chemicals in households are arranged based on the guidelines/ recommendations. (National) Reporting can be partly done jointly with action HL5 and HL25.
31 |  | HL8 | HL8 - Introduce requirements regarding content of chemicals of high regional environmental concern in public procurement procedures by 2025 and provide support for follow-up. (National/joint) | EG HAZ measures sub-team | WG Source to sea | EG HAZ | BSAP actions HL5 and HL10 | EG HAZ to agree on the focus noting the results and experiences of the NonHazCity project and the work on HELCOM list of priority substances (HL10). EG HAZ to make the first draft of the guidelines/ recommendations, WG Source to sea to provide guidance. | Regional guidelines/ recommendations for green procurement procedures are published. (Joint). National or local guidelines/ recommendations for green procurement procedures are issued, if needed. (National) Reporting can be partly done jointly with action HL5.
32 |  | HL9 | HL9 - Establish procedures by 2025 to utilize information obtained under various policies and policy frameworks addressing the use of chemicals (e.g. Stockholm Convention, SAICM successor, REACH Regulation, Water Framework Directive, Industrial Emissions Directive etc) to prioritize measures targeting regional contaminants and to identify emerging pollutants of high concern. (Joint) | EG HAZ strategic/holistic sub-team, HAPhazard project | WG Source to sea | EG HAZ | BSAP action HL1 | HAPhazard project and EG HAZ to make the analysis. The aim is to avoid doubling the work of other international conventions and find the linkage to HELCOM work to be able to prioritize the HELCOM measures. | Analysis of measures implemented under other policies, including their effectiveness is conducted. Summary of international work and identified measures on contaminants of emerging concern, e.g screening campaigns, is presented every two years for Pressure Working Group and for other relevant HELCOM bodies for planning and prioritizing further the HELCOM work on hazardous substances.
33 |  | HL10 | HL10 - Establish a mechanism for managing the HELCOM list of priority substances starting from 2025 and respond to screening and assessment results pointing out regional challenges for the Baltic Sea environment and contaminants of emerging concern. (Joint) | Co-leads: Denmark, [Sweden], [Germany] EG HAZ priority substances, screening and substances of emerging concern sub-team, HapHazard project | WG Source to sea | EG HAZ | BSAP action HL1 | The work is done in close cooperation with OSPAR. As a first step, HAPhazard project and EG HAZ to look into the current priority substances (Rec 31E/1), indicators and monitoring, OSPAR lists and those under MSFD and WFD, the proposals in the background document for the strategic approach as well as screening results. | A group working in collaboration with relevant other actors (e.g. global treaties, OSPAR, EU NORMAN network) aiming to further risk-based prioritisation tools for the needs of Regional Seas Conventions is formally established. A prioritisation mechanism, which is used for continuous update of the priority list based on reported data and prioritisation criteria is in place.
34 |  | HL11 | HL11 - Organize continuous follow-up of the work on hazardous substances under various global and EU policies as well as in Regional Sea Conventions (RSCs) starting from 2024, and actively influence these processes by promoting international actions identified as necessary to improve the environmental status with respect to hazardous substances in the Baltic Sea. (Joint) | EG HAZ strategic/holistic sub-team | WG Source to sea | EG HAZ | BSAP action HL1 | Summaries from the relevant UN/EU meetings are included as an agenda item for EG HAZ meetings every second year and from there reported to WG Source to sea starting from 2024. | Joint HELCOM initiatives are proposed to relevant global or upstream Conventions to reduce inputs of hazardous substances to the HELCOM Convention area.
35 |  | HL12 | HL12 - HELCOM participation starting from 2023 as member in Strategic Approach to International Chemicals Management High Ambition Alliance (SAICM HAA) to support international cooperation on global chemical challenges that influence the state of the Baltic Sea. Identification of global challenges that are of importance for the Baltic Sea that HELCOM will put on the SAICM HAA agenda. (Joint) | Lead: Secretariat | WG Source to sea | EG HAZ |  | To work together with OSPAR to identify important topics for the SAICM HAA agenda with regard to the marine environment. WG Source to sea to develop a list of topics of importance starting from 2023. Chair of WG Source to sea or Secretariat to take part in SAICM HAA meetings. | Membership in SAICM HAA.
36 |  | HL22 | HL22 - Improve knowledge base on occurrence of pharmaceutical substances in the environment, their persistence and harmful effects and ensure availability of this information for broad expert community by 2025. (Joint) | Sweden, EG HAZ pharmaceuticals sub-team | WG Source to sea | EG HAZ | BSAP actions HL23, HL24 | Sweden and EG HAZ pharmaceuticals sub-team to make a proposal on building the knowledge base | Information for a broad expert community about available information sources (e.g. Background document /internet platform/ database that compiles available information sources) is published.
37 |  | HL23 | HL23 - Identify priority pharmaceuticals by 2024 utilising the best available knowledge on their releases into the aquatic environment, environmental effects and available data on their use in the region, for efficient risk reduction and for subsequent integration of these substances to HELCOM assessments, as indicators of the state of the Baltic Sea and environmental pressure. (Joint) | EG HAZ pharmaceuticals sub-team | WG Source to sea | EG HAZ | BSAP actions HL22, HL24, HL1, HL10 | EG Haz sub-team on pharmaceuticals to plan and launch a data call on pharmaceuticals in summer 2023. First the priority pharmaceuticals could be identified by 2024 and then look into efficient risk reduction. Related to HL22 and HL10. | By 2024 priority pharmaceuticals for the Baltic Sea region are identified. Available information about effects, releases, uses and efficient risk reduction is compiled. Priority pharmaceuticals are utilized for the assessment of the Baltic Sea state, including as indicators.
38 |  | HL24 | HL24 - Develop guidance for the environmental monitoring and analysis of pharmaceuticals identified as indicators of the state of the Baltic Sea by 2025.(Joint) | Lead country needed, EG HAZ pharmaceuticals sub-team | WG Source to sea | EG HAZ | BSAP actions HL22, HL23 | Closely linked to improving the knowledge base and identifying priority pharmaceuticals. | Guidance for environmental monitoring and analysis is published.
39 |  | HL28 | HL28 - Address substances of emerging concern by commencing recurrent screening campaigns starting from 2021 including broad analytical techniques such as suspect screening and non-target screening methods. (Joint) | PreEMPT project, EG HAZ priority substances, substances of emerging concern and screening sub-team | WG Source to sea | EG HAZ | BSAP actions HL1, HL10 | Step 1 – review PreEMPT data. Also bring in data from other sources such as CP samples sent under OSPAR CONNECT etc. Step 2 - Review other screening data (pathways, WWTPs, mammals, eagle etc) to get overview. Step 3 – evaluate matrix type, spatial spread, other technical requirements for better future assessments. Step 4 – propose follow up actions, technical aspects and also regularity. Step - 5 how to implement. | The HELCOM hazardous substances screening project is implemented.
Monitoring
40 |  | HT6 | HT6 - Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements. | CP leads as identified under WG GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDIv; WG Source to sea; WG Sea-based pressures; EG HAZ; EG Eutro; EG MaMa; EG Marine Litter; EG Noise; PEG; EG ZOO; JWG BIRD; EG RedCore |  | By 2024 perform a gap analysis of the current Monitoring Manual and monitoring programmes with respect to pressures originating from land and agree how the gaps can best be addressed as part of the next update. Begin the process to update the nutrient and hazardous substances pressures related monitoring programmes in autumn 2024 to ensure the review and update is finalized and the updated monitoring manual and programmes are published in early 2026, in good time before the national Art.11 reporting concludes. EG HAZ to make proposals on how to update the monitoring manual regarding hazardous substances. | Updated monitoring programmes are available every six years in line with what is specified in the action.
41 |  |  | Contribute to and guide the development of regional monitoring guidelines for pressures from input of nutrients and hazardous substances. | Lead: needed | WG Source to sea
42 |  |  | Establish persistent regular data flows and data management for nutrients and hazardous substances data needed for HELCOM assessment and tracking purposes. | Lead: needed | WG Source to sea |  |  | Using the review of the HOLAS 3 (2023), data reporting and processes as a basis, identify gaps in dataflows and infrastructure. Analyze the underlying causes and identify solutions. Implement solutions to secure improved, consistent dataflows. | Lower resource requirements long term due to automatised data reporting. Improved access to data and information across the region. Enabling automatising assessment procedure.
Indicators
43 |  | B33 | B33 – By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). | Secretariat | WG GEAR | WG BioDiv; WG Source to sea; WG Sea-based pressures |  | 2023-2024: Support the review and gap analysis following HOLAS 3, looking at both the policy and the technical aspects of the inclusion, and assessment, of pressures from nutrients and hazardous substances, as well as the working structure and process. Based on this review, identify and prioritize work to be done with respect of pressures from nutrients and hazardous substances under the preparatory phase for HOLAS 4 and prepare and implement corresponding workplans to target the gaps and ensure work progresses. | By 2024 a Roadmap for how to fill gaps for both ecosystem components and pressures from nutrients and hazardous substances is developed. By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available
Other tasks
44 |  |  | Plan for the implementation of actions with later target years | Lead: needed | WG Source to sea |  |  | Initiate the discussion by the planning of the next workplan or earlier as needed | Plan on how to address the BSAP actions with later target years by the end of 2024
45 |  |  | Evaluation and reporting on implementation of BSAP actions under the responsibility of the working group. |  | WG Source to sea |  |  | WG Source to sea to review and update its workplan during 2024, for approval by HOD in December 2024. The review should include an evaluation to enable horizontal tracking of progress, identifying and tackling barriers to implementation as well as possible synergies or areas of cooperation with other working groups. A common template developed by WG GEAR should be used for reporting of progress and identifying actions where further support is needed. | Updated workplan for 2025-2026. Identification of barriers to implementation as well as possible synergies or areas of cooperation with other working groups.