## Status of implementation
CODE OF ACTION | REGIONAL ACTION | FURTHER SPECIFICATION | STATUS OF IMPLEMENTATION | MILESTONES | AREAS WHICH WILL REQUIRE MORE RESOURCES | DOCUMENTATION RELATED TO THE STATUS OF IMPLEMENTATION
1 | Improve the quality of data submitted to the HELCOM impulsive noise registry by updating and improving the common HELCOM guidelines for monitoring impulsive noise events in the Baltic Sea. | Based on the reporting to the registry already available. Main aim of action is to increase the completeness, spatio-temporal resolution and quality of submissions to the registry. | Action related to action S63 in the BSAP.
2 | Improve assessment of impact of impulsive noise by identifying important habitats and biologically sensitive areas and periods in the Baltic Sea region, where the introduction of high-energy impulsive noise is likely to have negative impact. | Based on HELCOM identified noise sensitive marine animal species (HELCOM 2019), which are to be delineated based on biological data and science-based criteria and in cooperation with other HELCOM working and expert groups (such as EG-MAMA)
3 | Establish common methodology for the assessment of negative impact from impulsive noise | Development and description of best practice for assessing potential injury and behavioural disturbance (habitat loss) in relation to for example environmental impact assessments (EIAs) and strategic impact assessments (SIAs). | Denmark and Germany are planning to initiate national and/or bilateral research projects to support the implementation of the action. These national projects will be closely coordinated to create synergies between expert capacities and effectively work towards a common methodology for the assessment of negative impact from impulsive noise for the HELCOM area.
4 | Further develop the HELCOM impulsive noise pre-core indicator towards an operational core indicator | This includes development of methods to assess environmental status based on the indicator as well as definition of thresholds and targets.
5 | Develop and implement one or more HELCOM impact indicators for impulsive noise | Based on the current pressure indicator, but with the inclusion of information about distribution of sensitive species and habitats. This work is a continuation of the work described in the noise sensitivity report (HELCOM 2019) and should preferably be along the same lines as the impact indicator currently under development in OSPAR and in accordance with the recommendations by EU TG-NOISE. | Action related to action S62 in the BSAP.
6 | Identify Best Available Technologies (BAT) related to the abatement of impulsive noise. Among these collect existing national regulations and guidelines aimed to reduce the impact of underwater impulsive noise on the ecosystems of the Baltic Sea and related observations in order to form relevant HELCOM guidelines. | Including noise abatement systems and alternative installation methods for offshore wind farms, spatio-temporal exclusion of UXO clearing and alternatives to detonation, commercial sonars and test/training/exercise of military sonars, alternative seismic sources, and sub-bottom profilers. | Action related to action S60 in the BSAP. Germany invited CPs to share national lists of BAT and BEP practices by IC PRESSURE 2-2022 and IC SEA-BASED PRESSURES 1-2023. Further, Germany compiled available input on national BAT/BEP practices for impulsive underwater noise in relation to pile driving activities for IC SEA-BASED PRESSURES 1-2023. Information on national BAT/BEP practices for impulsive noise generating activities, including other impulsive noise sources, are invited to be shared by CPs in response to a questionnaire regarding BAT and BEP for the abatement of impulsive noise which is being finalised. | Draft HELCOM BAT/BEP guidelines available by mid-2023.
7 | Increase the use of Best Environmental Practice (BEP) and Best Available Technology (BAT) in mitigation of impact from impulsive noise by establishing common HELCOM best practice guidelines in methods for mitigation of impact from impulsive noise | Implementation of the knowledge gained from action 6. | Germany has initiated a national research project to support the implementation of the HELCOM RAP on Underwater Noise, including this action. This action will be based on progress achieved in Action 6.
8 | Improve regional and cross-border coordination of the spatio-temporal planning and permitting by establishing a common reporting system for planned activities likely to produce impulsive noise. | This constitutes an extension of the impulsive noise registry to include future activities that are currently only recorded after they occurred.
9 | Improve protection of areas, which have already been defined as important or critical habitat for noise sensitive species, by obligating the adoption of adequate operational and technical noise mitigation measures. | HELCOM (2019) already identified a number of important areas which are important for noise sensitive species (such as the core habitat of the critically endangered harbour porpoise population of the Baltic proper or spawning areas of fishes using sound for communication). If the area is already protected as an MPA, this can be included as part of the management. This does not imply that measures (such as those identified in action 6) are not required in other areas not specifically protected.
10 | Reduce injury and behavioural disturbance from impulsive noise by establishing common HELCOM criteria for injury and disturbance, as well as common exposure limits. | These criteria and exposure limits are not identical to the GES-thresholds to be established under point 4, but are operational criteria that can be applied to individual activities generating impulsive noise. | Denmark and Germany are planning to initiate national and/or bilateral research projects to support the implementation of this action. These national projects will be closely coordinated to create synergies between expert capacities and effectively work towards common criteria and exposure limits for the HELCOM area.
11 | Improving accessibility and sharing of monitoring data by operationalisation of the common database for monitoring data on continuous underwater noise | As decided by HOD 55-2019 and implemented by database hosted by ICES. | Maritime Working Group to be informed on developments related to this action. A4 of the HELCOM BLUES project is organising an online workshop on 17 November 2022 on calibration Action related to action S63 in the BSAP.
12 | Development of common guidelines for reporting of continuous noise levels in the Baltic Sea. | Linked to and in progress in connection to establishment of common database hosted by ICES. | Action related to action S63 in the BSAP.
13 | Increase regional coordination and management of continuous noise sources by establishing a common framework for modelling past, present and future noise levels in the Baltic. | Continuation of the Soundscape planning tool developed under the BIAS project, as decided by HOD 55-2019. Such modelling is based on AIS and other relevant information about sources, such as source levels and frequency spectra. Includes developing methods to include noise from leisure boats without AIS transmitters as well as natural ambient noise. | To consider reports on underwater noise emissions from Baltic Sea shipping regularly submitted to meetings of the Maritime Working Group.
14 | Improve assessment of impact of continuous noise by identifying important habitats and biologically sensitive areas and periods in the Baltic Sea region, vulnerable to elevated levels of continuous noise. | Some information available (HELCOM 2019). To be amended based on biological data and science-based criteria and in cooperation with other HELCOM working and expert groups (such as EG-MAMA).
15 | Establishment of a common methodology for assessment of impact of activities generating continuous noise. | Applies to for example shipping, offshore wind farms, offshore installations, construction works (other than pile driving and similar impulsive sources) and offshore infrastructure, etc. | Maritime Working Group to be involved and informed of activities related to this action. Action related to action S58 in the BSAP.
16 | Further develop the HELCOM continuous low-frequency noise pre-core indicator towards an operational core indicator. | This includes development of methods to assess environmental status based on the indicator (action 15) as well as definition of thresholds and targets.
17 | Increase the knowledge and encourage data sharing on impact of noise by supporting research on sources and effects of continuous noise on marine biota. | Impact studies as detailed in the HELCOM science agenda. Encourage exchange of statistical information about continuous low frequency sources, including frequencies’ spectrum characteristics. | Denmark contributes to this task through the support of a specific research project on re-routing in Kattegat (TANGO). The project is performed in collaboration with Estonia and Sweden, and investigates how splitting a big shipping route (T) into two smaller affects surrounding noise levels and harbor porpoise activity. The presentations and findings of the Informal consultation workshop on underwater noise by shipping organised online by BSH and CCB on 8-9 Septemper 2022 (https://www.ccb.se/event/2022-workshop-underwater-noise-shipping) are relevant for this action. Maritime Working Group to be involved and informed on activities related to this action. Action related to action S57b) in the BSAP.
18 | Develop and implement one or more HELCOM impact indicators for continuous low-frequency noise. | Based on the current pressure indicator (action 16), but with the inclusion of information about distribution of sensitive species and habitats (action 14). | Action related to action S62 in the BSAP.
19 | Expand and improve the existing and potential operational and technical measures to reduce the impact of continuous noise to form a basis for common guidelines on management. Suitable technical measures to reduce input of continuous noise should be identified (BAT/BEP), based on a scientific justification, and taking into account socioeconomic impacts | Collection of experience from HELCOM members and abroad and collection of new information through research and development, as detailed in the HELCOM science agenda | Germany has initiated a national research project to support the implementation of regional strategies and regional action plans in OSPAR and HELCOM (e.g. BSAP and HELCOM RAP on Underwater Noise), including a work package on shipping noise mitigation measures, that compiles and evaluates different possible measures for the reduction of ship-based continuous noise. Sweden is considering a research proposal to be carried out next year on mainly operational mitigation measures; synergies with the German research project will be sought. Both Denmark and Germany are involved in the EU project SATURN which is very much related to this action. A correspondence group in IMO, under the leadership of Canada, is working on the revision of the voluntary Guidelines for the reduction of underwater noise from commercial shipping to address adverse impacts on marine life (MEPC.1/Circ.833). HELCOM countries, in addition to the EC, involved in the Correspondence Group are Denmark, Finland, Germany and Sweden. The correspondence group aims at submitting a report of the work conducted to the upcoming Sub-Committee on Ship Design and Construction session (SDC 9), which is scheduled on 23-27 January 2023. Action related to action S55 in the BSAP. | To make an inventory of measures, from operational to technical measures (e.g. ship design) |  | Side event organised by OceanCare, Coalition Clean Baltic (CCB) and BUND Friends of the Earth Germany in Ocean Conference 2022 “Reduce Ocean Noise and save our ocean”. https://www.ccb.se/event/2022-un-ocean-conference-side-event-noise-reduction
20 | Reduction of elevated continuous noise levels in noise sensitive and biologically important areas in the Baltic Sea by adoption of guidelines on management, based on the “HELCOM input to the establishment of environmental targets for underwater noise” (2018). The environmental targets for underwater noise should take into account the target values set by TG Noise at EU level | Implementation of knowledge gained under action 19. | Maritime Working Group to be involved and informed on activities related to this action. Possible input from CCB in connection with a pilot project on mitigation measures.
21 | Inciting national and voluntary actions with respect to raising awareness of ship and boat operators and cooperation with shipping companies and boat owners on speed management for their vessels including different aspects of adjusting and planning for vessel speed and engine load optimised for the reduction of underwater noise. | This can include installing monitoring systems at strategic locations (for example at outer approaches to ports) with real-time feedback to the ship’s crew, to raise awareness and to aid in optimizing vessel and engine operations for reduced underwater noise radiation. | Maritime Working Group to be involved and informed on activities related to this action. Possible input from CCB in connection with a pilot project on mitigation measures. Action related to action S57b) in the BSAP.
22 | Enhance Baltic Sea wide cooperation of port authorities to introduce novel initiatives, such as harbour fee systems, in order to set incentives for voluntary quiet vessel operation. | See Port of Vancouver (2017), ECHO Program | Maritime Working Group to be involved and informed on activities related to this action. Consider the findings of the Informal consultation workshop on underwater noise by shipping organised online by BSH and CCB on 8-9 Septemper 2022 (https://www.ccb.se/event/2022-workshop-underwater-noise-shipping). Action related to action S57b) in the BSAP.
23 | Identification of other noise sources with significant impact on the marine ecosystems but not covered by the measures targeting impulsive and continuous noise | This includes, but is not limited to, sources with main energy above 10 kHz: echosounders, military and non-military sonars, sub-bottom profilers, net pingers, and hydroacoustic instruments. | Action related to action S57c) in the BSAP.
24 | Identification of important habitats and biologically sensitive areas and periods in the Baltic Sea region, vulnerable to elevated levels of noise from other sources than those covered by existing pressure indicators. | Based on biological data and science-based criteria and in cooperation with other HELCOM working and expert groups (such as EG-MAMA)
25 | Compile and assess available information about potential impact caused by noise from leisure boats | As detailed in the HELCOM science agenda | To be a topic for a workshop under preparation on all leisure craft related actions in the BSAP. Possible input from CCB in connection with a pilot project on mitigation measures. SYKE (Finland) as a partner in a LIFE IP project among other work strands measures and models the noise from recreational boating in the Archipelago Sea; vessel slowdown and MPAs are considered within the scope of the project. Action related to action S57c) in the BSAP.
26 | Development of HELCOM indicators suitable for monitoring noise sources identified under measure 23. | Existing indicators cover impulsive noise under 10 kHz and continuous low-frequency noise, but does not include echosounders, most sonars and sub-bottom profilers, net pingers, etc.
27 | Development of common guidelines for assessing impact from echosounders, sonars and other sources not covered by 2.1 and 2.2 | Such as to apply to environmental impact assessments (EIAs) and assessment of environmental status (GES).
28 | Support for research on pressure and impact from echosounders and other low-level, but abundant noise sources. | As detailed in the HELCOM science agenda | Denmark contributes to this task through a specific research pilot project aiming to quantify the pressure from echosounders as measured at Danish noise monitoring stations. The pilot project has been initiated. Action related to action S57c) in the BSAP. | The pilot project is scheduled finalize by the end of 2022.
29 | Reduce the impact from acoustic deterrent devices by developing and agreeing on common guidelines and regulation of the design and use of deterrent devices | Action proposed for BSAP update
30 | Strengthen coordination with IMO on the development of actions, as appropriate, to reduce underwater noise from commercial shipping and cooperate with other relevant actors as needed in the development of technical and operational solutions to reduce such noise in line with the aforementioned IMO actions. | Includes, but it is not limited to, discussions on current and future quiet ship design as well as on shipping's contribution to underwater noise and the impact of underwater noise on marine species. Initiate discussions on feasibility of reducing or otherwise regulate the emissions from echosounders (in general or restricted to sensitive areas) without compromising navigational safety. Discuss feasibility of systems providing real-time feedback to bridge about noise emissions from the ship. | Contracting Parties are following the ongoing process in IMO on the revision of the Guidance on underwater noise. Possible cooperation with the GEF on Capacity Building in the IMO framework. Contracting Parties are encouraged to inform the MEPC sessions 82-85 on lessons learned/best practices in the implementation of the revised IMO Guidelines, noting that extension of the experience building phase beyond MEPC 85 would not be ideal. The Chair of EG Noise is to cooperate with the Secretariat in order to prepare a document to IC WG MARITIME 3-2024 regarding input needed from WG Maritime on the workplan of the action.
31 | Establish platforms to share best practices on policy options within member states and between authorities, the private sector and NGO’s. Improve public awareness, so that political decision makers, local administrations and civil society are adequately informed about the underwater noise challenges. | For example, issuing a bulletin on best practices and policy options in the region and in the world. | Maritime Working Group to be involved, active and informed on activities related to this action. Consider the findings of the Informal consultation workshop on underwater noise by shipping organised online by BSH and CCB on 8-9 Septemper 2022 (https://www.ccb.se/event/2022-workshop-underwater-noise-shipping).
32 | Strengthen the cooperation with OSPAR on development of common and/or compatible indicators, databases and assessment methodologies | As agreed on an overall level in the 2018 HELCOM Brussels declaration
33 | Maintain and strengthen cooperation with the European Union expert group TG-Noise on issues of mutual interest | In particular to assure consistency in development of indicators and criteria and methods for establishing thresholds and targets
34 | Reduce the impact from leisure boats by establishing a discussion with producers of echosounders and fishfinders with the goal of introducing standards for noise emission from echosounders, fishfinders and engines of leisure boats. | This aims for example at installing on/relates to the ability to turn off and adjust source level and frequency of echosounders and fish-finders, as well as developing industry standards for underwater noise emissions for boat engines. | Maritime Working Group to be involved, active and informed on activities related to this action. Possible input from CCB in connection with a pilot project on mitigation measures. Action related to actions S56 and S57b) in the BSAP.
35 | Reduce the impact from underwater explosions in connection to munition clearance, by developing international guidelines for the safe removal and detonation of ammunition. The guidelines should be established through consultation with the Ministry of Defence of the Russian Federation and NATO and lead actions for use of noise mitigation technologies and operating practices in the Baltic Sea. | Initiate discussions on the use of noise mitigation measures, as well as informing nature protection institutions about planned detonations and mitigation methods. | Maritime Working Group to follow this action in relation to safety of navigation, and be consulted if needed. CCB to contribute to the implementation of this action. EG Submerged to support EG Noise on the implementation of the action, noting the strong link between the action and BSAP action S34.

## Leadership by country
LEADERSHIP
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden | CCB | Joint contact group of HELCOM and OSPAR representatives
1 |  |  |  |  | To co-lead the action and to lead task 1
2
3 | Lead |  |  |  | Lead and/or actively promote the implementation process.
4
5 |  | To support | [7 empty] | To support work on other relevant species groups different from marine mammals
6 |  |  |  |  | Lead and/or actively promote the implementation process |  |  |  |  | To support | To support
7 |  |  |  |  | Lead and/or actively promote the implementation process
8 | [9 empty] | To co-lead
9
10 | Lead |  |  |  | Lead and/or actively promote the implementation process
11 | [11 empty] | To lead
12
13
14
15
16
17 | Co-lead; based on specific study on re-routing in Kattegat (as done in the similar BSAP action S57).
18 |  | To support | [7 empty] | To support work on other relevant species groups different from marine mammals
19 |  |  |  |  | Lead and/or actively promote the implementation process | [5 empty] | Possible input in connection with a pilot project on mitigation measures
20 | [10 empty] | Possible input in connection with a pilot project on mitigation measures
21 | [10 empty] | Possible input in connection with a pilot project on mitigation measures
22
23
24
25 | [10 empty] | Possible input in connection with a pilot project on mitigation measures
26
27
28 | Co-lead; based on specific pilot-study that aims to quantify pressure of echosounders at Danish underwater noise monitoring stations.
29
30
31
32
33
34 | [10 empty] | Possible input in connection with a pilot project on mitigation measures
35 | [10 empty] | To contribute

## National actions
ACTIVITIES
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17