## Sheet1
No | Type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
Indicator development
1 |  |  | Integrating data (ferry box, satellite data, modelling) into point measurements aiming for a gridded approach. | Indicator leads | WG Source to sea |  |  | Sharing experiences (e.g., Baltic Data Flows project developments for Chl-a indicator) and discussion in EG, followed by focused development during 2025 and first half of 2026. | Expanded application of high throughput and automated monitoring in assessments.
2 |  |  | Adjusting indicators in Bothnian Bay to reflect carbon and water colour (e.g., CDOM). | Finland and Sweden | WG Source to sea |  |  | FI and SE cooperate in development work with input from the group in 2025, to be completed in mid-2026 | Potential update of indicator evaluation (and process) to reflect CDOM effects.
3 |  |  | Develop shallow water oxygen to core indicator. | Indicator leads | WG Source to sea |  |  | Initial discussion and planning in EG during 2024 followed by defined work on the issue in 2025, including a workshop, and first half of 2026. | Core indicator on shallow water oxygen developed
4 |  |  | Develop spring bloom chlorophyll-a to core indicator. | Indicator leads | WG Source to sea |  |  | Initial discussion and planning in EG during 2024 followed by defined work on the issue in 2025 and first half of 2026. | Core indicator on spring bloom chlorophyll-a developed
5 |  |  | Develop cyanobacterial bloom to core indicator. | Indicator leads | WG Source to sea | EG Phyto |  | Initial discussion and planning in EG during 2024 followed by defined work on the issue in 2025 and first half of 2026. | Core indicator on cyanobacterial bloom developed
6 |  |  | Developing the oxygen debt indicator. | Estonia | WG Source to sea | Sweden |  | General scoping starting directly, with the focused work to initiate in early 2025 and complete by mid-2026. | Adjustment of indicator to be applied at sub-basin scale and also to ensure methodology is clearly defined and applied appropriately.
7 |  |  | Threshold value for water transparency for Pomeranian Bay. | Germany, Poland and indicator leads. |  |  |  | General scoping starting directly, with the focused work to initiate in early 2025 and complete by mid-2026. | Target is to ensure all sub-basins have threshold values applied.
Assessment development
8 |  |  | Review of HEAT to ensure workflows and manual are up to date (i.e., updating Eutro OPER system and manual). | EG Eutro | WG Source to sea |  |  | Review initiated in 2024 and completed by mid-2026. Updating Eutrophication assessment manual. Workshop with ICES in 2024 or 2025. | Ensure HEAT methodology is well documented and that workflows function optimally at HOLAS 4, returning to many of the more defined and systematic approached applied in HOLAS II (though with necessary technical updates included).
9 |  |  | Better incorporation or harmonisation of WFD coastal water assessments in the HOLAS assesments, including establishment of proper data flow with quality assurance (in case of reporting results) and tools fro analysis | EG Eutro | WG Source to sea |  |  | Defining and implmenting WFD result reporting template fields and required QA routines. Defining and implemeneting required tools by mid-2026. | Appropriate use of WFD results or re-use of data/results to develop a more harmonised and approporiate status assesment for HOLAS4.
Monitoring
10 | BSAP action HT6 |  | Support the review of the eutrophication related monitoring programmes | Lead countries | WG GEAR, WG Source to sea | EG Eutro |  | Support the lead countries in updating monitoring programmes in 2024-2025 | Review completed
11 |  |  | Improve regional coordination on oxygen monitoring to address the priority monitoring gap | EG Eutro | WG GEAR, WG Source to sea |  |  | Link to indicator development and data flows as a first step in a workshop in 2025. | Solutions for improved regional coordination
Cooperation
12 |  |  | Improve the quantitative and qualitative linkages between nutrient inputs and eutrophication state | EG Eutro | WG Source to sea | EG RedCore, PLC-8 and PLC-9 projects |  | Continue discussions between groups in 2025
13 |  |  | Support the development of a project for improving land-sea interactions | EG RedCore | WG Source to sea | EG Eutro |  | Based on the outputs of the workshop, support development of project application and seeking relevant partners | Project application submitted
14 |  |  | Support the use of eutrophication related HELCOM indicators in UN SDG 14 reporting | EG Eutro, Secretariat | WG GEAR |  |  | Review and harmonize further with developments under UNEP | Improved dialogue and synergy of UN SDG 14 indicators and HELCOM work
15 |  |  | Improve the quantitative and qualitative linkages between biodiversity and eutrophication state | EG Eutro | WG Source to sea | EG Phyto, EG Foodwebs, EG Zoo |  | Bring the issue to the planned HOLAS cross-over workshops. | Ensure tha this issue is addressed in HOLAS4, primarily via carrying out suitable interaction in the planned cross-over workshops.
16 | BSAP action HT2 |  | Consider the effects of climate change to eutrophication indicators and assessment | EG Eutro | WG Source to sea | EN Clime
17 |  |  | Investigating the role of carbon (e.g. carbon to chlorophyll ratio). | EG Eutro | WG Source to sea | EG Phyto, EG Foodwebs |  | Initiate discussion in mid-2025 with a view to securing resources for work in 2026.