## Status of implementation
CODE OF ACTION | REGIONAL ACTION | FURTHER SPECIFICATION | STATUS OF IMPLEMENTATION | DOCUMENTATION RELATED TO THE STATUS OF IMPLEMENTATION
RL1 | Share best practices and guidelines for municipalities and other responsible authorities regarding environmentally sound and effective cleaning, sorting and collection infrastructure of plastic litter on beaches and other coastal areas. |  | Not initiated
RL2 | Evaluate top findings according to the knowledge available and recommend environmentally sound alternatives to phase out top plastic and rubber litter items. |  | Not initiated
RL3 | Establish a regional pilot project in collaboration with river basin authorities to assess input of macro litter by rivers to build sound regional knowledge base. |  | Ongoing | A riverine litter session of the Regional Seas surrounding Europe was held on 23 May 2024, in Valencia, Spain, in the frame of the MARLICE 2024 forum. In addition, a high-level session was held on 22 May 2024 entitled "Connecting Seas: Regional Assessments on Marine Litter and the Global Framework". Finally, the UNEP/MAP Guidelines for Monitoring Riverine Inputs of Marine litter are being pilot testing in the Baltic Sea, and its inclusion as part of the regional monitoring activities is to be considered once the results of the envisaged pilot testing are available.
RL4 | Reduce marine litter by sharing best practices on national return and refund deposit systems for drink packaging striving to establish such systems in all HELCOM countries and investigate possible bilateral and multilateral solutions to prevent littering and enhance recycling of drink packaging in relation to passenger ships and border shops. |  | Ongoing | Final conference of the PACKGDEPO project took place on 20 April 2023 in Pärnu, Estonia. The results of the project are expected to provide useful input for the implementation of this action. The workshop indicated for May-June in the implementation plan of the action was held on 2 November 2023. As a follow up from the workshop, Contracting Parties were to provide information about their national systems as well as any cross-border arrangements by 19 January 2023, based on which Estonia would prepare a draft for best practices. Input was provided by Germany, Poland and Sweden. Estonia is to provide draft guidelines for the next session of WG Sea-based pressures.
RL5 | Identify environmentally open applications using plastics (e.g. agriculture foil, coastal erosion protection, etc...) which need to be addressed and recommend relevant actions. |  | Not initiated
RL6 | Based on the evaluations made in the EU and among the contracting parties of the most significant products and processes that release both primary and secondary microplastics, assess if they are covered or not by legislation, and act, if appropriate, to influence or adjust the legal framework, or identify other necessary measures to reduce emissions to the aquatic environment. |  | Not initiated
RL7 | Evaluate the possibility to introduce regional recommendations to reduce release of microplastics from WWTP utilizing the outcome of related studies. |  | Not initiated
RL8 | Development of a HELCOM guideline on establishment and operation of artificial turfs, to prevent plastic losses, taking into account the ongoing work within the EU including the proposal by ECHA. |  | Ongoing | Starting firstly by designing a survey questionnaire on artificial football fields. The action was briefly presented in the Nordic Football Association’s Infrastructure Conference 7.-9.9.2022, which Finland hosted. Present were infrastructure experts from Norway, Iceland, Sweden, Denmark, Germany and Finland. Compilation of the results from the online survey on artificial football fields has been conducted (April 2023). CCB offered to translate the questionnaire and share it with relevant football associations to get more information and responses. In Germany there are challenges with finding the appropriate contacts due to the federal arrangement and the lack of a general database on artificial football pitches. However, there is already work in progress on football pitches in relation to the environmental certification scheme Blue Angel, which may be of benefit in relation to developing measures on how to approach this topic. Finland and Germany are to liaise bilaterally in this regard. The survey did not consider the afterlife of artificial pitches, but that this may be included in future guidance documents on the matter, as replacing old pitches with new ones typically causes significant pollution. The second task of the implementation plan of the action (evaluation of the management options for preventing loss of infill material) has been conducted and is opened for comments by Contracting Parties by 30 November 2024. Sweden shared the national guidelines on the matter.
RL9 | Investigate opportunities for substitution with subsequent phasing-out non-degradable shot wads and launch information campaigns targeted at hunters. |  | Accomplished | A survey aiming at getting an overview of degradable shot wads (including shot wads with very reduced volumes of plastic e.g. used as lining) from producers/importers and organisations and how the CPs have targeted this issue by e.g. voluntary agreements, information campaigns or legislative measures was conducted. Input was received from Denmark, Finland and Sweden. The information received as well as knowledge gained through interviews with different stakeholders and otherwise gathered information from e.g. Danmarks Jægerforbund (The Danish Association of Hunters) was used to develop a policy brief on the matter.
RL10 | Provide guidance on best-practice examples and regulatory options for municipalities in the Baltic Sea region to reduce the generation of single use plastic litter. |  | Not initiated | The focus of Germany so far was on finalizing the the Interreg-project CAPonLITTER (Capitalising good coastal practises and improving policies to prevent marine litter, CoL) and implementing a related MSFD measure. The two guidances on Best-Practice examples and regulatory options for municipalities to prevent and reduce plastic litter are now both translated and need final editing before they can be distributed to HELCOM CPs. Results of CoL will be disseminated once the project ends mid-2023.The other steps will then follow.
RL11 | Prevention and reduction of single use plastics consumption and littering at major events and promotion campaigns through the establishment of a catalog of possible measures to be utilized by the organizers and authorities. |  | Not initiated
RL12 | Phase out intentional releases of inflated balloons |  | Accomplished | KIMO International have developed a report that gives an overview of the problem(s) with marine litter from balloons and possible solutions. The report contains available information on the magnitude of the problem and lists which (type of) legislation or other approaches the contracting parties have in place to address the problem. It also suggests possible policy options to phase out intentional releases of balloons. In addition to the report, KIMO international has developed communication material to raise awareness of the environmental problems linked to balloon releases. The #CelebrateBetter campaign contains both videos and social media cards available in six languages: Danish, English, Estonian, Finnish, German and Swedish. Suggestions for social media messages are also provided (in English only). The lead and co-lead have also prepared a policy brief on the issue of balloon and confetti littering in the Baltic Sea area.
RL13a | Consider phasing out the use of plastic components of firework and confetti outdoors - section on plastic components of firework |  | Ongoing | The first point of the roadmap for implementation of this action, the investigation for a first impression of the size of problem, has been concluded (April 2023). The second point, to circualte a survey to gain an overview on the issue of plastic components of firework in the HELCOM area has also concluded (March 2024).
RL13b | Consider phasing out the use of plastic components of firework and confetti outdoors - confetti section |  | Accomplished | KIMO International have developed a report that gives an overview of the problem(s) with marine litter from balloons and possible solutions. The report contains available information on the magnitude of the problem and lists which (type of) legislation or other approaches the contracting parties have in place to address the problem. It also suggests possible policy options to phase out intentional releases of balloons. In addition to the report, KIMO international has developed communication material to raise awareness of the environmental problems linked to balloon releases. The #CelebrateBetter campaign contains both videos and social media cards available in six languages: Danish, English, Estonian, Finnish, German and Swedish. Suggestions for social media messages are also provided (in English only). The lead and co-lead have also prepared a policy brief on the issue of balloon and confetti littering in the Baltic Sea area.
RS1 | Identify opportunities for developing ELB management and recycling methodologies including potential financial arrangements (e.g. producer´s responsibility, eco-fee for registered boats). |  | Ongoing | WG Martitime is to contribute to the implementation of this action. A Finnish project on end-of-life boats, commissioned by the Ministry of Environment, has been finalized and the report is available in Finnish. Findings of the report indicate that there are more than 700 000 fiberglass boats in Finland, most of which are rowing boats or other small boats. A few thousand abandoned boats can be recovered annually, and there are various options for managing them, including incineration in cement kilns where the glass fibre is partially used as fuel and partially as raw material. As part of a government mandate, The Swedish Agency for Marine and Water Management (SwAM) has conducted an in-depth investigation into the current situation of EOL recreational boats in Sweden. The report estimates that there could be up to 400, 0001 derelict boats in Sweden that require collection for recycling or reuse. Currently, approximately 500 boats are recycled annually. The low rate of recycling, combined with the growing number of EOL boats, highlights the urgent need for more comprehensive management solutions. The report finds significant gaps in the ability of government agencies and municipalities to effectively handle derelict and abandoned recreational boats. No single actor is responsible for dealing with these boats, and there is insufficient legal authority to address cases where the ownership of the boat is unknown. SwAM has also put forward several proposals to improve the situation nationally. CCB is organizing a workshop on implementation of BSAP actions related to recreational craft and the development of a “Clean Boating Guide”, to be held on 10 December 2024, where considerations on this topic were invited to be given.
RS2 | Encourage the development and use of buoys, floats and docks, which do not release expanded polystyrene (EPS) and other problematic materials to the marine environment with the aim to phase out the use of those containing unprotected EPS and problematic materials. |  | Accomplished | A questionnaire aiming at getting an overview of methods of encapsulating EPS/XPS and use of alternatives to EPS/XPS containing equipment was circulated. Moreover, the questionnaire went beyond the rather restricted scope of the implementation plan and e.g. also included knowledge of aquaculture and fishing boxes. Five replies were received from different stakeholders covering 3 HELCOM countries, Denmark, Finland and Sweden. The action, as indicated in its implementation plan, aimed originally to develop a guidance on reduction of buoys etc. of EPS/XPS with unprotected surfaces or other problematic materials. Due to the few responses received, a policy brief was drafted instead of a guidance document as originally envisaged. Input on the policy brief has been provided by the European Boating Industry which is to be used during future updates of the policy brief and possible further follow-up actions at national or HELCOM level, in particular the importance of considering the end of life of pontoons.
RS3 | Cooperate with maritime stakeholders to optimize onboard waste management enhancing separation, fostering recycling, and phasing out the use of single-use plastics in shipping, including in cruise operations. |  | Not initiated | WG Martitime is to contribute to the implementation of this action.
RS4 | Investigate the problem with cargo losses causing plastic littering of the marine environment and, based on the findings, together with national competent authorities, consider developing a common guidelines for accident management taking into account ongoing work within the IMO and EU. |  | Not initiated | WG Martitime is to contribute to the implementation of this action.
RS5 | Investigate the problem caused by spills of plastic pellets from ships and, based on the findings, consider developing common guidelines for accident management in such events. |  | Ongoing | Step 1) Assessment report on acute plastic pollution in the Nordic Countries. The report, commissioned by the Nordic Council of Ministers to KIMO, describes preventive measures, emergency responses, experiences from clean-up operations, relevant regulation, and other legal aspects. The roles of authorities and other actors, organisation at national/regional level, and cooperation between countries. As a follow up, a workshop to advance on the matter was held on 6 February 2024. Contracting Parties are to share information on: (i) the outcomes of the negotiations at IMO, EU and OSPAR level related to plastic pellets; (ii) activities contributing to the monitoring of the implementation of the voluntary IMO guidelines; (iii) contributions to the knowledge base on the impact of pellets as well as on the gathering of information of the magnitude of the problem in the Baltic Sea; and (iv) experiences in relation to clean-up technologies to upoming sessions for continuing the discussion. In addition, WG Response is to consider how to assess the possibility of including plastic pellets as part of the ongoing HELCOM cooperation in case of a pollution incident, taking also into account IMO Guidelines on clean-up of plastic pellets from ship-source spills under development.
RS6 | Encourage collection of ALDFG and separation of collected ALDFG from end-of-life gear with a view to establish regional targets for collection of end-of-life fishing gear. |  | Ongoing | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11, RS12 and RS15). In addtion, the Swedish Agency for Marine and Water Management is sponsoring a project to develop the outputs of selected actions in the RAP Marine Litter addressing ALDFG and other fisheries related litter, being RS6 one of them. Thus, a best practices document for collection of ALDFG and separation of collected ALDFG from end-of-life gear is to be drafted, and its outline is available.
RS7 | Elaborate guidelines on the best practices and undertake relevant measures to reduce the input of ALDFG to the Baltic Sea from recreational fisheries with a focus on gillnets taking into account geographical particularities. |  | Ongoing | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11, RS12 and RS15). In addtion, the Swedish Agency for Marine and Water Management is sponsoring a project to develop the outputs of selected actions in the RAP Marine Litter addressing ALDFG and other fisheries related litter, being RS7 one of them. Thus, guidelines on the best practices to reduce the input of ALDFG to the Baltic Sea from recreational fisheries with a focus on gillnets are to be drafted. The outline of the guidelines is available.
RS8 | Evaluate the amounts and composition of lost angling gear in the Baltic Sea including fishing lures and casting weights with corresponding hooks, soft plastic baits and light components and develop appropriate measures to prevent their further loss. |  | Ongoing | 1) A study on the amounts and composition of lost fishing gear – traps, pots and handheld fishing gear including fishing lures, baits, casting weights with corresponding hooks, fishing lines and light components from recreational fishing in the Nordic countries – in order to develop appropriate measures to prevent their further loss. Finalized and published. 2) Depending on the results of the Nordic study, further studies of the amount of lost fishing gear must be carried out in the countries not included in the Nordic study. Finalized and published. The next steps are to follow the adoption of the new EU Fisheries Control Regulation, including the potential future implementing acts on recreational fisheries (see document 2-2 to IC RAP ML 3-2024). Depending on the requirements of the implementing acts, additional measures may be considered at regional level in relation to marking and reporting. In the frame of RS8, HELCOM should also follow the standardization process in the CEN Technical Committee 466 on circularity and recyclability of fishing and aquaculture gear and once the standard is completed, give consideration to whether a regional implementation of the standard is needed. In addtion, the Swedish Agency for Marine and Water Management is sponsoring a project to develop the outputs of selected actions in the RAP Marine Litter addressing ALDFG and other fisheries related litter, being RS8 one of them. Thus, a document on measures to prevent and reduce losses from recreational fishing gear are to be drafted. The outline of the document is available.
RS9 | Investigate available options for fishing gear marking as a tool to prevent and reduce gear losses and produce recommendations to improve gear marking to increase the effectiveness of this tool |  | Ongoing | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11, RS12 and RS15). Developments regarding the marking of fishing gears was discussed at IMO PPR 10 in April 2023. Gear marking is also being considered at FAO and OSPAR, and these developments are to be considered in the further work. The Swedish Agency for Marine and Water Management is sponsoring a project to develop the outputs of selected actions in the RAP Marine Litter addressing ALDFG and other fisheries related litter, being RS9 one of them. Thus, best practices on fishing gear marking are to be drafted. The outline of the best practices is available.
RS10 | Consider innovative constructive features of fishing gear as a tool to prevent and reduce gear losses and a tool to prevent and reduce lost fishing gears from ghost fishing. |  | Ongoing | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11, RS12 and RS15). Denmark is participating in a similar action in OSPAR, which implementation will commence this year. The Swedish Agency for Marine and Water Management is sponsoring a project to develop the outputs of selected actions in the RAP Marine Litter addressing ALDFG and other fisheries related litter, being RS10 one of them. Thus, a report on innovative constructive features of fishing gear as a tool to prevent and reduce gear losses and a tool to prevent and reduce lost fishing gears from ghost fishing is to be drafted. The outline of the report is available.
RS11 | Continue the mapping of areas with high potential for ALDFG accumulation (hot spots) in all HELCOM countries with subsequent update of the HELCOM Map&Data service. |  | Ongoing | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11 and RS12). In relation to this action, note was taken on the mapping of ghost nets via sonar in German waters, reporting of ghost gear via the GhostDiver App and approaches to use ArcGIS and artificial intelligence as well as the methodology used on the mapping. Subsequently, HELCOM countries provided information on available apps and the Secretariat investigated the technical possibilities to upload data from these apps and data sources to the HELCOM Map and Data Service. An informal technical workshop to further advance on the issue of apps to map areas with high potential for ALDFG accumulation was held on 22 August 2024. Following recommendations by the workshop a concept of data flows for reporting of ALDFG data is to be applied and the Secretariat is to inform about its use to the next Sea-based pressures session.
RS12 | Initiate removal of ghost nets and their safe management on land applying the best practices for ALDFG removal in national or international campaigns. |  | Ongoing | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11, RS12 and RS15).
RS13 | HELCOM to join the Global Ghost Gear Initiative (GGGI) which is the world’s largest cross-sectoral alliance committed to driving solutions to the problem of ALDFG worldwide. |  | Accomplished | The Secretariat contacted GGGI and had an online meeting on 11 September 2023 to informally discuss the matter. During the meeting, GGGI welcomed the possibility of HELCOM joining the initiative, clarified that due to HELCOM being an IGO, no fees apply, and indicated that the requisite to be part of the initiative is to fill in a statement of support. The statement of support has been filled in and submitted to GGGIT. HELCOM appears as a member of the GGGI on the dedicated website since the end of 2023.
RS14 | Engage fishermen (both recreational and commercial) and general public to report on lost and observed ghost fishing gear utilizing related reporting tools (e.g. Swedish example of GhostGuard app or German Geistertaucher). |  | Ongoing | Accomplished: • WWF GhostDiver App online and ready to compile different data sources connected to verified ghost gear positions • In the BMUV founded program until March 2023: For Germany, Poland, Estonia = 320 potential ghost gear positions, of which 105 positions are already verified by divers and 98 net findings are already retrieved in several programs (executed e.g. by the Federal State Mecklenburg-Vorpommern). Ongoing (numbering related to the steps foreseen in the implementation plan): 2 Connection to Sweden, Estonia and Poland exist; 4 Reach out to Norwegian Experts 5.1 WWF Workshop in Poland; 5.2 UBA Workshop in Germany scheduled for May 15th, 2023;
RS15 | Consider the development of HELCOM Recommendation and guidelines on the reduction of marine litter through the implementation of Sustainability Education Programmes for Fishers taking into account results of the ongoing work on the revision of IMO STCW-F. |  | Not initiated | An online workshop was organized during autumn 2023 to consider the way forward in implementing of the actions related to fishing gear (RS6, RS7, RS9, RS10, RS11, RS12 and RS15).

## Leadership by country
LEADERSHIP
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden | CCB | WWF Poland
RL1 |  |  |  |  | Lead on starting the implementation of the action
RL2
RL3
RL4 |  | Lead |  |  | To investigate the possibility to contribute
RL5 |  |  |  |  | Lead
RL6 |  |  |  |  | Lead on starting the implementation of the action
RL7
RL8 |  |  |  | Lead | [5 empty] | Co-lead
RL9 | Lead
RL10 |  | Co-lead |  |  | Lead
RL11 | Lead | Co-lead |  |  | Lead on starting the implementation of the action
RL12 | Lead | [8 empty] | Co-lead
RL13 |  |  |  |  | Lead the section on plastic components of firework |  |  |  |  | Lead the confetti section
RS1 |  |  |  | Supporting | [5 empty] | Supporting | Lead
RS2 | Lead
RS3 |  |  |  | Lead
RS4
RS5 | [9 empty] | Lead
RS6
RS7
RS8 |  |  |  |  | Considering co-leading |  |  |  |  | Lead
RS9
RS10
RS11
RS12 |  |  |  |  | Lead on starting the implementation of the action
RS13
RS14 |  |  |  |  | Lead
RS15 |  |  |  |  | Lead on starting the implementation of the action

## Additional information
CODE OF ACTION | ADDITIONAL INFORMATION
RL1
RL3
RL4 | PACKGDEPO project - Bottles reject borders!: https://milttonevents.smai.ly/browser/-8rCD8Bg2w1rY87HfES--UaWiZE8ZRZ5cMEzw4dntsGr68vTvlDsK5eGmEEvo2M0sMNArbl7kTSSbJxnOFz9j6pGFFthwslip1W7X1hR_C_VnGqG4IVhcuplPWIZSJ68QvwdNZsIhDQRKiW_Ccgdug,,/
RL5
RL6
RL7 | CCB launched a series of activities on addressing the microfiber pollution from textiles and solutions on the whole life cycle of textile. Keep Fibers Zipped campaign aimed at developing a trend to reduce microplastic pollution from textiles with the help of existing consumer and production, technological and behavioral solutions was launched. Main activity of the campaign is the development of the report and a case study of available solutions in the Baltic Sea region and the world related to microfiber pollution from textile. The draft report is ready with contribution of experts from CCB MOs and partner organizations. It consists of cases of solutions in the BSR and world on different stages of microfibers leakage and covers different actors (regulation, waste water treatment plants, circularity for textiles, production of the cloths and fabrics, devices for catching microfibers and behavioural practices for the consumers). Release of the report is planned in second quarter of 2023.
RL8 | Swedish national guidelines: https://www.naturvardsverket.se/vagledning-och-stod/plast/vagledning-om-konstgrasplaner/
RL9 | A policy brief on shot wads made of plastic is avaailble: https://helcom.fi/wp-content/uploads/2024/06/policy-brief-on-shot-wads-made-of-plastic.pdf
RL10
RL11
RL12 | The outputs of the project have been made available in a dedicated section of the HELCOM website: https://helcom.fi/action-areas/marine-litter-and-noise/marine-litter/celebrate-better-campaign/. In addition, links to the material have also been provided on the BALLONS project website: https://helcom.fi/helcom-at-work/projects/balloons/ A policy brief on potential measures to prevent marine plastic pollution from balloons and confetti is also available: https://helcom.fi/wp-content/uploads/2024/02/policy-briefs-pollution-from-ballons-confetti.pdf
RL13 | The outputs of the project have been made available in a dedicated section of the HELCOM website: https://helcom.fi/action-areas/marine-litter-and-noise/marine-litter/celebrate-better-campaign/. In addition, links to the material have also been provided on the BALLONS project website: https://helcom.fi/helcom-at-work/projects/balloons/ A policy brief on potential measures to prevent marine plastic pollution from balloons and confetti is also available: https://helcom.fi/wp-content/uploads/2024/02/policy-briefs-pollution-from-ballons-confetti.pdf
RL14
RS1 | Link to the Finnish report: https://julkaisut.valtioneuvosto.fi/bitstream/handle/10024/165410/YM_2024_5.pdf Link to the Swedish report:
RS2 | A policy brief on EPS/XPS in buoys, floats and docks is available: https://helcom.fi/wp-content/uploads/2024/02/policy-briefs-EPS-XPS.pdf
RS3
RS4
RS5 | Assessment report on acute plastic pollution in the Nordic Countries: https://www.norden.org/en/publication/acute-plastic-pollution-causes-problems-and-solutions Memo of IC WS PLASTIC PELLETS 1-2024: https://meetings.helcom.fi/_entity/annotation/eeadd8c6-1dc7-ee11-9079-000d3adeacfa
RS6
RS7
RS8 | A study on the amounts and composition of lost fishing gear: https://pub.norden.org/temanord2022-568/#122745 Evaluate the amounts and composition of lost angling gear in the Baltic: https://www.diva-portal.org/smash/record.jsf?aq2=%5B%5B%5D%5D&c=2&af=%5B%5D&searchType=LIST_LATEST&sortOrder2=title_sort_asc&query=&language=en&pid=diva2%3A1790189&aq=%5B%5B%5D%5D&sf=all&aqe=%5B%5D&sortOrder=author_sort_asc&onlyFullText=false&noOfRows=50&dswid=-8896
RS9
RS10
RS11
RS12
RS13 | https://www.ghostgear.org/members
RS14 | Re:Fish project working on recreational fishing gear under the leadership of Sweden: https://centralbaltic.eu/news/31-regular-projects-approved-for-funding/
RS15