## H-V MSP WG
Approved by the VASAB CSPD/BSR during its 93rd meeting on 12-13 December 2024 and by the Helsinki Commission in March 2025 via correspondence.
No | Task: MSP Roadmap task | Timing | Lead | Contributing | Next steps and comments [note: timeframe in column C] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
Cont. = continuously, Secr. = Secretariat, EU MSP Asst. Mech. = EU MSP Assistance Mechanism, WG = Working Group, usually HELCOM-VASAB MSP Working Group
Regional MSP Roamap Objective 1 : Implementation of maritime spatial plans builds knowledge base for the new MSP cycle
| Roadmap 2030 Action | Timing | Lead | Contributing | Next steps and comments | Concrete output (Roadmap)
Specific for this workplan period:
1.2 | Develop and share a concise and descriptive overview of national MSPs implementation (what does implementation mean in different countries; where/when do they impact on decisions on certain projects, spatial and temporal management of activities etc) | start in 2025 and overview 2028 | DE | DE, EE, FI, LV, SE, CCB, EU MSP Asst. Mech., interim assessment task force | In 2024/2025 - line with the work of Task Force on Interim assessment of Roadmap. Also support the EU process on proposing questions. | Overview of national MSPs implementation if possible, inclusion in established country fiches that would have a dedicated section
1.3 | Develop a regional follow up system on MSP, including monitoring of implementation at the Baltic Sea level | 2027 | LV | DE, EE, FI, LT, LV, SE, CCB, EU MSP Asst. Mech. | A workshop could be supported by EU MSP Asst. Mech., if needed. | BSR follow-up system of implementation of MSPs
1.5 | Analyse and support spatial efficiency by comparing approaches and solutions with regard to spatial use (e.g., exclusive vs multi use of space) and conflicts management. | 2027 | co-leads: DE, tbd | DE, EE; EU, FI, LT, LV, SE, CCB, EU MSP Asst. Mech. | Germany is about to finish an in-depth study on multi-use; the reports may be a good starting point for this work. EU MSP Asst Mech. could share the method and approach related to multi-use and conflict management. | Report on best practices/cases and recommendations on spatial efficiency and good examples of multi-use
1.6 | Improve MSP related data retention and flows and assuring data actuality. Ensure regional compatibility of the MSP Input and Output Data and strengthen mutual cooperation in broader context, especially EU. | 2025 | BSR MSP Data ESG (tbc.) | DE, EE, FI, LT, LV, PL, SE, CCB, EU MSP Asst. Mechanism | Cooperating with EU TEG on Data, HELCOM Secretariat. ReMAP project support. | (continues from 2022-24) Overview on national MSP data portals
Continuous tasks:
1.4 | Facilitate exchange of information on the best practices of MSP implementation, monitoring and evaluation across the BSR and other sea basins | cont. | PASPS project for the Planners Forum | DE, EE; FI, LT, LV, SE | Regular work of the group. Initiation of formalization of the Planners Forum under the group. | Regular exchange in HELCOM-VASAB MSP WG, Planners Forum regularly
1.6 | Improve MSP related data retention and flows and assuring data actuality. Ensure regional compatibility of the MSP Input and Output Data and strengthen mutual cooperation in broader context, especially EU | cont. | BSR MSP Data ESG | DE, EE, FI, LT, LV, PL, SE, CCB, EU MSP Asst. Mechanism | Cooperating with EU TEG on Data for MSP. | Continuously exchange the best practices in MSP related data handling with MSP data platforms beyond the Baltic Sea region
1.7 | Establishing of links with relevant scientific frameworks and maritime knowledge; support the education of MSP planners and international educational exchange | Cont. | WG | DE, EE, FI, LT, SE, regular ICES WG MPCZM collaboration | On EU level when the occasion presents itself. | Regular consideration of recent scientific developments at regional MSP related events; contributing to regional MSP science and educational needs
Regional MSP Roamap Objective 2: Maritime Spatial Planning improves regional policy coherence
No. | Roadmap 2030 Action | Timing | Lead | Contributing | Next steps and comments | Concrete output (Roadmap)
For this workplan period:
2.4 | Further develop institutional framework for the intergovernmental collaboration on MSP in the BSR | by 2026 | PL | DE, EE, FI, LT, LV, SE, EU MSP Asst. mech | EU MSP Asst. Mech. has been developing guidelines and studies on stakeholder involvement and communication; experience could be transferred in the work on review of the H-V Guidelines. Evaluating and tracking progress of carrying out consultations until now. Checklist from eMSP project. | Review Baltic Sea regional “Guidelines on transboundary consultations, public participation and co-operation”
2.6 | Study the relationship between various policies related to protection and sustainable use of marine resources by continuously following national MSP implementation as well as other related processes concerning marine and coastal domain (e.g., European Green Deal, Sustainable Blue Economy, Offshore renewable energy and Biodiversity strategies, etc. | by 2025 | VASAB Secr. for country fiches | DE, EE, EU, FI, LT, LV, SE, EU MSP Asst. mech | EU MSP Asst. Mech. could support with methodological work and EU wide perspective on the topic. | For this period: supplement country fiches with relevant information.
Continuous tasks:
2.1 | The Baltic Sea countries’ MSP authorities continue close collaboration | Cont. | WG, PASPS project for Planners Forum | All Baltic Sea countries, EU MSP Asst. mech | Part of regular work of the group. | Continuous dialogue utilizing various regional platforms, e.g., HELCOM-VASAB MSP Working Group, MSP Planners Forum.
2.2 | HELCOM-VASAB MSP Working Group as a platform for cooperation of MSP authorities with other HELCOM bodies and stakeholders | Cont. | HELCOM Secr. for HELCOM bodies | All Baltic Sea countries, EU MSP Asst. mech | Providing relevant contacts, if needed. Continuing plans with EG ESA, EN CLIME, SAFE NAV etc. | Continuous dialogue with sectors utilizing various regional platforms
2.3 | Enhance Baltic Sea level collaboration of MSP authorities and planners with various sectors to contribute to aligning sectoral policies and sectoral decision-making and by raising awareness on the role of MSP between involved stakeholders | regularly | Relevant ongoing projects | All Baltic Sea countries, EU MSP Asst. mech | EU MSP Asst. Mech. could support with a workshop, if needed. BEMIP collaboration. EUSBSR PA Safe, PA Ship collaboration. | Regular regional events, e.g., Baltic MSP forum.
2.7 | Utilise the prominent role of coordinating Policy Area “Spatial Planning” within the EU Strategy for the Baltic Sea Region (EUSBSR) to improve cross-sectoral and multi-level cooperation across the BSR and contributing to its objectives | Cont. | WG, PASPS project | All Baltic Sea countries, EU MSP Asst. mech | Part of regular work of the group. | HELCOM-VASAB MSP Working Group acts as the Steering Group for MSP within the EUSBSR Policy Area “Spatial Planning”.
Regional MSP Roamap Objective 3: Maritime Spatial Planning contributes to achieving progress towards good environmental status of the Baltic Sea set in the Baltic Sea Action Plan
No. | Roadmap 2030 Action | Timing | Lead | Contributing | Next steps and comments | Concrete output (Roadmap)
For this workplan period
3.1 | Update the EBA-guidelines based on shared experiences in national application of the ecosystem-based approach in MSP and the evaluation of EBA implementation in the latest MSP-round and other relevant input | 2025 | DE, SE, Task Force | EU, EE, FI, LT, LV, PL, EU MSP Asst. mech., HELCOM Secretariat, EUSBSR PA SP | cf. separate workplan | (continues from 2022-24) Updated EBA-guidelines
3.2 | Develop a Baltic SEA-framework including themes, common data, assessment methods for impact evaluation, cross-border consultations. | 2025 | tbc: Regional project, seeking for funding | DE, EE; FI, LT, LV, PL, SE, EU MSP Asst. mech., EUSBSR PA SP tbc. | Possible project development, also using the report on EU survey on the SEA in MSP in the Baltic Sea Region results and experiences in HOLAS3 CIA work. | (continues from 2022-24) Baltic SEA-framework to improve compatibility of SEA practices and results
3.4 | Identify how MSP can support conservation and sustainable use in equitable way (MPAs, OECMs etc.), BSAP targets related to protected areas, national and regional strategies | 2025 | tbd. | DE, EE, FI, LT, LV, PL, SE, EU MSP Asst. mech., regional projects (PROTECT BALTIC, MSP4BIO) | Investigate possibility to harmonize with the Protect Baltic project mapping activities. EU MSP Asst. Mech. could provide contacts from other sea basin or EU wide projects and experts. HOLAS3 ecosystem service maps to be used. Interim assessment to take into account possible revision need. | (continues from 2022-24) Draft Green Infrastructure maps including ecosystem services based on HOLAS 3
3.5 | Promote the use of methods and tools in MSP for assessing cumulative environmental and other impacts of sea-based activities | 2026 | HELCOM Secr., support from regional projects | DE, EE, EU, FI, LT, LV, PL, SE, EUSBSR PA SP | Collaboration with HELCOM work on SPIA (spatial distribution of pressures and impacts assessment). Interlinkage with 3.2. | (continues from 2022-24) Harmonised approaches for cumulative impacts assessments
3.6 | Evaluate how MSPs are supporting the overarching goals of the MSFD and thereby contributing to deliver to good environmental status | 2026 | tbd. | DE, EE, FI, LT, LV, SE, EU MSP Asst. mech., HELCOM Secretariat to liaise with WGs BioDiv tbc., Sea-based Pressures tbc. and GEAR tbc. | Seems like a topic for a study or a project. EU MSP Asst. Mech. could participate by contributing to the methodology of the evaluation. Related EU work going on with review of the MSFD by 2026. | Report on MSP’s impact on the implementation of the MSFD, including programmes of measures and achieving GES
Regional MSP Roamap Objective 4. Maritime Spatial Planning contributes to sustainable blue economy
No. | Roadmap 2030 Action | Timing | Lead | Contributing | Next steps and comments | Concrete output (Roadmap)
For this workplan period
4.1 | Share experiences in guiding sectoral development to minimize economic losses and weakening of ecosystem services, apply cross-border actions that can be enhanced through MSP for sustainable blue economy | 2026 | tbd. | DE, EE, FI, LT, LV, SE, HELCOM EG ESA | Use relevant projects (MSP-Green, eMSP, MSP4BIO). EG ESA collaboration. | (continues from 2022-24) Report/Guiding document on good practices for sectoral sustainable development possibly as a policy brief
4.2 | Investigate the linkage between environmental and social-economic dimensions through an ecosystem services analysis with cross-border MSP perspective | 2027 | tbd. | DE, EE, FI, LT, LV, SE, HELCOM EG ESA | Study or project? Harmonize with Protect Baltic and SELINA projects. | Joint analysis of ecosystem services in relation to MSP in order to achieve sustainable blue economy
4.3 | Encourage participatory and transparent processes with all stakeholders of sea use to ensure successful integrated and holistic MSP and management towards sustainable blue economy | 2025 | tbd. | DE, EE, LT, LV, SE, EU MSP Asst. mech. | Isn't the task more about stakeholder involvement? The task could be linked to the work on task 4.1 and 4.2. and interim assessment of the Roadmap. Linkage to the country fiches and the interim assessment results on transparency. EG ESA collaboration. | An overview of MSP impacts on progress towards sustainable blue economy in the Baltic Sea Region, including contribution to the SDGs 2030
Regional MSP Roamap Objective 5. Spatial planning contributes to climate change mitigation, adaptation and increased resilience of the Baltic Sea Region
No. | Roadmap 2030 Action | Timing | Lead | Contributing | Next steps and comments | Concrete output (Roadmap)
For this workplan period
5.1 | Explore how MSP related sectors will be affected by climate change including how climate change might impact human activities under different future scenarios, aiming at developing MSP-strategies for increasing capacity of different sectors to adapt to expected climate change impacts | 2025 | DE | EE, FI, LV, SE, EN CLIME, MSP-GREEN project | MSPglobal should adopt the climate smart MSP complementary guidance by mid-2025. Harmonize with the work of EN CLIME (e.g. Climate Change Factsheet). Second part of the task should be understood to mean: Explore how MSP can enable adaption strategies of the different sectors and/or find a balance between the strategies of sectors. | (continues from 2022-24) A discussion paper as guidance for strategic ways for integrating climate change adaptation into MSP for the next planning cycle, coordinate timing with mid-term evaluations of national adaptation strategies
5.2 | Explore how MSP can contribute to climate change mitigation and nationally determined contribution in terms of Paris Agreement, including NECPs and relevant national strategies. | 2025 | DE, FI, LV | EE, LV, SE, EU MSP Asst. mech., MSP-GREEN project | EU MSP Asst. Mech. could support with a workshop, if needed. Related EU work to support, methodology to be shared. | (continues from 2022-24) Stocktaking national experiences - an overview published
5.3 | Identify how MSP can support adaptive conservation strategies to cater for spatial changes in ecosystems (e.g. migration), potential for including climate refugia in MSP for the entire Baltic Sea | 2026 | tbd. | DE, EE, FI, SE, EU MSP Asst. mech., projects eMSP, MSP4BIO, MPA Europe, EN CLIME | Study or project? Use projects (MSP4BIO methodological framework). EU MSP Asst. Mech. could support with a workshop, if needed. Collaboration: EN CLIME, HELCOM WG Fish, ICES WG MPCZM. | (continues from 2022-24) Information document on MSP’s role in adaptative conservation strategies, including best practices
|  | 2026 | tbd. | Projects MSP4BIO, MPA Europe, EN CLIME. | Projects MSP4BIO, MPA Europe. EN CLIME. | (continues from 2022-24) Modelled maps of climate change impact on marine ecosystem (depending on availability of spatial data on climate change impacts)
Other tasks relevant for the group
No. | Action / task | Timing | Lead |  | Next steps and comments | Concrete output
For this workplan period
O.1 | Interim assessment of the MSP Roadmap | 2025 | Task Force |  | cf. separate workplan | Interim Assessment Report
O.2 | Underwater heritage | cont. | WG |  |  | Regularly considered in the group, vs. national MSP revision processes
O.3 | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group | 2025 | WG |  |  | Plan in 2025, reportings and revisions in 2026-27