## WG BioDiv
Approved in March 2025 via correspondence by the Helsinki Commission | Approved in March 2025 via correspondence by the Helsinki Commission
ToR duty no. | No | Type of action | BSAP Action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
1. |  |  |  | 1. Assessment of Baltic Sea biodiversity
1 | 1 | National/Joint | B9 | By 2024 assess the status of the Haploops species and the biotopes, as well as key threats and, if relevant based on the assessment, by 2026 develop a joint conservation plan for Haploops species including jointly agreed measures to improve the status of the species and biotopes, to be implemented by 2028. | Denmark | WG BioDiv | - | - | 2025-2026: Based on the results of the assessment and the identified pressures in the Species Information Sheet, the relevant CPs work together using HELCOM as a platform, to identify and agree on measures and develop a joint conservation plan for the species. 2027-2028: national implementation of measures and conservation plan. | By 2024, updated assessment of the status of the species and the biotope, as well as key threats is ready and publicly available. (Joint supporting action)
1 | [9 empty] | If and where relevant, based on the status assessment, by 2026 development of a joint conservation plan to improve the status of haploops species and biotopes, including jointly agreed measures, has been completed. (Joint supporting action)
1 | [9 empty] | By 2028, if and where relevant, based on the status assessment, development of a joint conservation plan to improve the status of haploops species and biotopes, including jointly agreed measures, has been adopted. (Joint supporting action)
1 | 2 | Joint | B10 | Include information on functional and life history traits for the species in the HELCOM Biodiversity Database, by 2024. | PROTECT BALTIC | WG BioDiv | - |  | 2023-2028: PROTECT BALTIC will progress the work, in close cooperation with the lead (collecting trait information and updating the Biodiversity database) | By end of 2026 trait information has been added for the species listed in the HELCOM Biodiversity database, wherever possible.
1 | 3 | Joint | B14 | By 2027 assess the effectiveness of conservation efforts to protect waterbirds against threats and pressures |  | WG BioDiv | JWGBIRD |  |  | Assessment, including information about effectiveness of conservation efforts and the needed measures to protect waterbirds against threats and pressures is publicaly available. (joint supporting action)
1 | 4 | National/Joint | B15 | [Develop and coordinate monitoring and assessment methods, where ecologically relevant, for specified representative coastal fish species, populations and communities, by 2023. Based on these assessment methods, to] regularly assess the state of the coastal fish communty through selected coastal fish species and groups, including threatened species, by at latest 2023. Based on the results of the assessment, develop and implement management measures with the ambition to maintain or improve the status of coastal fish species, including migratory species by 2027. | [Sweden], [EG Coastal fish] | WG BioDiv | WG Fish | - |  | By 2027 appropriate management measures have been implemented with the ambition to maintain or improve the status of coastal fish species. (National measure)
1 | 5 | Joint | B22 | Update the HELCOM Red List Assessments by 2024, including identifying the main individual and cumulative pressures and underlying human activities affecting the red listed species. | RED LIST II | WG BioDiv | EG MaMa JWG Bird; EG Benthic; [EG Coastal Fish] |  | To be implemented under the RED LIST II project (2022-2024). Finalise the Red List final report, including an analysis of national implementation reporting on HELCOM Rec 37/2 since the first RL assessment in 2013 | By mid-2025 Red list assessment and supporting information (data, species information sheets etc) is published and publicly available.
1 | 6 | Joint | B25 | Map ecosystem services and the present and potential spatial distribution of key ecosystem components, including habitat forming species such as bladder wrack, eelgrass, blue mussel and stoneworts Baltic-wide, by 2025. | PROTECT BALTIC | WG BioDiv | WG GEAR, EG ESA, EG Benthic | Possibly MSP4BIO and BLUE4ALL | 2023-2028: PROTECT BALTIC project, will develop a multi-use methodology for identification, mapping and quantification of ecosystem services Exploration of ecosystem component quality and location for upscaling of ecosystem services and spatial overlaps of ecosystem services and human activities First output, PROTECT WP3 modelling based on WP4 instructions, second output based on the first | By mid-2026 a regional list of ecosystem services connected to key ecosystem components as well as spatial distribution of these ecosystem services is publicly available.
1 | [9 empty] | By 2026 regional maps presenting current and potential distribution of key ecosystem components are prepared and publicly available.
1 | 7 | Joint | B28 | Update the HELCOM Red List Assessments by 2024, including identifying the main individual and cumulative pressures and underlying human activities affecting the red listed biotopes and habitats | RED LIST II | WG BioDiv | EG Benthic |  | To be implemented under the RED LIST II project (2022-2024). End 2024/mid-2025: carry out assessment based on approach and maps agreed during September 2024 WS using a sub-set of IUCN criteria and a sub-set of biotopes | By mid-2025 Red list assessment and supporting information (data, species information sheets etc) is published and publicly available.
1 | 8 | Joint | B29 | By 2025 develop, and by 2027 implement, and ensure compliance with, ecologically relevant conservation plans or other relevant programmes or measures, limiting direct and indirect pressures stemming from human activities for threatened and declining biotopes and habitats. |  | WG BioDiv |  |  | 2024: Prepare a list of what habitats/biotopes on the Red List are relevant for what CP. | By end of 2024 an overview list of what Red Listed habitats/biotopes are relevant for each CP has been produced.
1 | 9 | Joint | B31 | Identify by 2022 data needs for spatial pressure and impact assessment of human activities, including cumulative impacts, and implement by 2024 at latest methods for mapping and assessment of adverse effects on the ecosystem of human activities in the Baltic Sea region. | HOLAS 3 | WG BioDiv | - | ReMap project | 2024: Long-term dataflows and infrastructure established with CPs. TBD steps for 2025 | Data needs for spatial pressure and impact assessment of human activities, including cumulative impacts, are addressed and long term dataflow plans have been established by 2024.
1 | [9 empty] | Latest improved methods for mapping and assessment of adverse effects on the ecosystem of human activities in the Baltic Sea region are implemented and results made publicly available by 2029.
1 | 10 | Joint | B32 | Update the HELCOM Underwater biotope and habitat (HUB) classification where gaps have been identified by 2024, and by 2025 develop a fully functioning translation matrix between HUB, Marine Strategy Framework Directive (MSFD) broad habitat types, Habitats Directive habitats and the European Nature Information System (EUNIS), in co-operation with the European Marine Observation and Data network (EMODnet). | RED LIST II, PROTECT BALTIC | WG BioDiv | - | TG SEABED | 2022-2024: Resources for updating the HUB classification have been secured under the RED LIST II project and initial communication with the consultant established. mid-2025: HUB classification updated with biotopes identified in data but missing in classification 2025: longer-term updates to be discussed at IC WG BIODIV 5-2025 Work on the translation matrix is included under the PROTECT BALTIC project and, will be ready by end of 2025. PROTECT to elaborate alignment of split-rules and interpratation of 'function' of several species per biotope. Identify any gaps and interpret 'fully' as achieved when alignement has been achieved as every aspect is not anticipated to be completely matched and aligned. | By 2025 HELCOM HUB-classification is updated, where gaps have been identified.
1 | [9 empty] | By 2025 a fully functioning translation matrix between HUB, MSFD broad habitat types, HD habitats and EUNIS is developed
1 | 11 | Joint | B33 | By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). |  | WG GEAR | WG BioDiv, WG Sea-based activities, WG Source to Sea |  | 2023-2024: ensure that there are Expert Groups established to support the indicator and assessment methodology development for those topics where no such support currently exists. Spring 2023: overview of linkages between biodiversity topics and EGs presented and considered. 2025: fish and commercial fish assessments to be clarified 2025-2027: integration rules to be reviewed and adjusted as needed | By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available
1 | 12 | Joint | B34 | Develop core indicators, and threshold values to evaluate the status of food webs by 2026, where applicable, and implement a holistic assessment of food webs no later than 2030. | EG Foodweb | WG BioDiv | - | Upcoming EU Foodweb group? | 2025/2026 present indicator concept. explore approaches where single indicators are used or whether a food-web assessment methodology would be appropriate | By 2026 a minimum of one indicator has been established with an agreed threshold value to evaluate the status of food web in a holistic way.
1 | [9 empty] | By 2030 a holistic assessment of food webs is available.
1 | 13 | Joint | B35 | By 2024 operationalize a set of indicators for the assessment of fish population health, including size and age distribution, where applicable, and, by 2029, for any remaining relevant species. | EG Coastal Fish | WG BioDiv | WG GEAR, WG Fish | S40 (WG Fish), S48 (WG Fish), possible ongoing work within ICES? | 2023/2024: secure agreement amongst CPs on how to address commercial fish. 2024: implement workplans (if possible with the support of external funding). | By 2029 health, size and distributional indicators are available for all relevant species
1 | 14 | Joint | S67 | Define the characteristics of benthic habitats, develop core indicators and undertake an integrated assessment of the status of benthic habitats, including their structure, function, […] leading to the identification of measures to reduce adverse effects where needed. Work should be done in close cooperation with work undertaken by Contracting Parties in other relevant fora, taking into account activities in EU Technical Group on seabed habitats and sea-floor integrity (TG Seabed), and considering the ICES advice on a sea-floor assessment process. | Indicator leads | WG BioDiv | WG Sea-based pressures, EG Benthic, EG Dreds | EU TG Seabed, ICES | EG Benthic workplan: cooperation with EMODnet Seabed Habitats to get usable data products / output from IC WS HABMAP 1-2024; EG Benthic workplan: Review of EUNIS classification in line with HUB / engaging with EEA (i.e. split-rules); Elaboration of regional list of species ecologically relevant per EUNIS habitats (level 5 onwards) for further application (i.e. function / distribution); HOLAS 4: topic of function to be developped and review of SPIA sensitivity scores / cooperation with EG Benthic; EG Benthic workplan / HOLAS 4: loss of habitats should be more harmonized between SPIA/CumI (incl. D6C5); EG Benthic workplan / HOLAS 4: common definition on adverse effect (i.e. limits); Follow-up of additional tasks carried by EG Benthic (c.f. workplan 2025-2026) related to HOLAS RevDev issues C, D, E, G, F, K, H, I; 2024/2025: elaborate proposed measures for reducing adverse impact on the structure and function of seabed habitats, towards the MM planned for 2026. | By 2026 (as per HOLAS RevDev/EG Benthic workplan - TBD cross-check) HELCOM indicators evaluating the status, structure, function and distribution of benthic habitats has been developed and operationalized.
1 | [9 empty] | By 2028 HELCOM indicator evaluating the extent of loss of benthic habitats has been developed and operationalized.
1 | [9 empty] | By end of 2025, where needed measures to reduce adverse effects have been identified.
1 | [9 empty] | Relevant new measures adopted by Ministerial Meeting in 2026
1 | 15 | NA |  | Collate available information on and define “favourable conservation status” (e.g. threshold value) for harbour porpoise, considering also IUCN red-list criteria. | Harbour porpoise team under EG MaMa | WG BioDiv |  | ASCOBANS Jastarnia Group | 2024/2027: Definition of favorable conservation status established. To be linked to ongoing work under the ASCOBANS Jastarnia Group that is addressing two plans one for the western Baltic Population and the other for Baltic Proper 2024/2027: Harbour porpoise team and indicator leads executing EG MaMa workplan, with guidance from BioDiv. | By end of 2027 favorable conservation status agreed.
1 | [9 empty] | By 2027 threshold values and operational indicators established for all populations.
2 |  |  |  | 2. Protection of Baltic Sea biodiversity
2 | 16 | National/Joint | B1 | By 2030 at the latest, establish a resilient, regionally coherent, effectively and equitably managed, ecologically representative and well-connected system of HELCOM marine protected areas (MPAs), supported by those other spatial conservation measures, under alternative regimes for marine protection, which can contribute to the coherence of the network. Where scientifically justified, special attention should be given to offshore areas beyond territorial waters. The network of marine protected areas will: - cover at least 30% of the marine area of the Baltic Sea, of which at least 1/3 will be strictly protected. Other Effective Area-based Conservation Measures (OECMs) could be counted towards the 30% targets only if they, as a minimum, comply with the OECM criteria agreed by the Convention on Biological Diversity (CBD). - where scientifically justified, consider including no-use zones within marine protected areas, which can also serve as scientific reference areas. - expand conservation efforts to actively include areas of particular importance for biodiversity and ecosystem resilience, including important ecosystem elements such as species or areas recognized to be ecologically significant based on function for the ecosystem/provisioning of ecosystem services and broad habitat types, but which may not necessarily be rare or threatened. | Finland/ PROTECT BALTIC | WG BioDiv | - | HT13 (HELCOM-VASAB MSP WG), HT14 (HELCOM-VASAB MSP WG), CBD targets, EU Biodiversity Strategy, upcoming Nature Restoration Law. | 2023-2028: PROTECT BALTIC will progress the task using the project as a platform, but in close cooperation with WG BioDiv. 2025 spring dedicated session on strict protection 2025/2026 focus on considering how to address the section, possibly in cooperation with PROTECT BALTIC activities "- where scientifically justified, consider including no-use zones within marine protected areas, which can also serve as scientific reference areas." | By the end of 2030 the HELCOM MPA network is resilient. (joint measure)
2 | [9 empty] | By the end of 2030 the HELCOM MPA network is regionally coherent. (joint measure)
2 | [9 empty] | By end of 2030 the HELCOM MPA network is effectively and equitably managed. (joint measure)
2 | [9 empty] | By end of 2030 the HELCOM MPA network, together with OECMs complying with the CBD criteria, covers at least 30% of the marine area of the Baltic Sea. (joint measure)
2 | [9 empty] | At least 1/3 of the area covered by the HELCOM MPA network is strictly protected. (Joint measure) (2030)
2 | [9 empty] | Conservation efforts target and include areas of particular importance for biodiversity and ecosystem resilience, irrespective of threat status, as outlined in the action. (National measure) (2030)
2 | 17 | National/Joint | B2 | By 2022 come to a common understanding of the Other Effective Area-based Conservation Measures (OECMs) criteria and their use in HELCOM, based on definitions agreed in the Convention on Biological Diversity (CBD) and the EU, and define how OECMs can support the coherence of the Baltic Sea marine protected area (MPA) network. By 2025 identification of OECMs in the Baltic Sea region. | PROTECT BALTIC for how OECMs can support the MPA network | WG BioDiv | HELCOM-VASA MSP WG | - | 2023-2028: PROTECT BALTIC will progress work on the second half of the action (defining how OECMs can support the coherence of the Baltic Sea marine protected area (MPA) network) 2025/2026: PROTECT BALTIC to continue exploring how to 'define how OECMs can support coherence' including through SOM analysis of what measures contribute to protection Coherence analysis outputs to inform spatial aspects. 2025: develop a definition to support national work on identifying and recognising OECMs | By 2025 a definition of how OECMs can support the coherence of the MPA network and the spatial conservation target of protecting 30% of Baltic Sea marine area has been established (joint supporting action)
2 | [9 empty] | By 2025 OECMs have been identified for the Baltic Sea region. (National)
2 | 18 | National/Joint | B3 | By 2030 strengthen the management of the Baltic Sea marine protected area (MPA) network by introducing key elements into management efforts, including but not limited to those highlighted here, to increase effectiveness of protection, including by providing support to Baltic Sea MPA managers through capacity building e.g., through annual workshops. By 2023 update, and by 2025, apply HELCOM MPA management guidelines with focus on: a) Assessments and evaluation methodology and structures for management effectiveness; b) Setting quantitative conservation objectives; c) Effective conservation measures that reduce pressures; d) Establishment of indicators to monitor management performance and status of conservation features; e) Establishment of a common monitoring strategy and evaluation of conservation features and pressures; f) Adaptive management. | PROTECT BALTIC/Germany | WG BioDiv | - | S64 (WG Sea-based pressures) S42 (WG Fish), S47 (WG Fish), S54 (WG Fish), S57 (WG Seabased) | [2023-2028: PROTECT BALTIC project will progress outputs in close cooperation with WG BioDiv. 2025-2028: PROTECT BALTIC deliverable 6.10 to deliver MPA management guidelines | (Annual workshops for MPA managers are carried out, contributing to building capacity (joint action)) 2025 workshop for MPA managers carried out, contributing to building capacity.
2 | [9 empty] | 2026 workshop for MPA managers carried out, contributing to building capacity.
2 | [9 empty] | By 2028 the HELCOM Guidelines for MPA Management are updated. (joint supporting action)
2 | [9 empty] | By 2025 the HELCOM MPA Management Guidelines are applied. (national supporting action)
2 | [9 empty] | By 2030 improved key elements are introduced into MPA management to increase the effectiveness of protection. (national measure)
2 | 19 | NA |  | Update the national information in the MPA database. | PROTECT BALTIC/CPs | WG BioDiv | - | - | 2023-2028: PROTECT BALTIC will improve database functionality and reporting, preparing reporting manuals, collating MPA specific information, translating it and populating the database. | By 2028 new MPA database with improved functionality ready and publicly available
2 | 20 | NA |  | Update and expand the MPA database. Produce guidance for using and updating the MPA Database. | PROTECT BALTIC | WG BioDiv | - | - | 2023-2028: PROTECT BALTIC will update the database platform and the functionality of the database, draft a manual for its use and collate and populate the database with updated MPA information. | By 2028 improved functionality and accessibility of MPA information for region.
2 | [9 empty] | By 2028 facilitate reporting to the database.
| 21 | National/Joint | B5 | Develop, implement and share information on effective management measures, including measures to ensure compliance/control measures, to reduce the impact of fisheries inside marine protected areas (MPAs) in order to contribute to achieve their conservation objectives. | Lead needed | WG Fish | WG BioDiv | S43 |  | Management measures for fisheries inside MPAs, contributing to the area’s conservation objectives, are more widely in place. (National measure)
Fisheries measures are documented in the HELCOM MPA Database. (Joint supporting action)
2 | 22 | National/Joint | B6 | The coherence of the marine protected area (MPA) network will be periodically assessed at least every ten years, with the next such assessment to be carried out by 2025. By 2027 the results from the coherence assessment are to be used to take appropriate actions to ensure conservation and resilience of biodiversity, and to identify possible spatial conservation expansion needs to improve coherence. | PROTECT BALTIC/Sweden | WG BioDiv |  | - | 2023-2028: PROTECT BALTIC will be improving and implementing the assessment of MPA coherence and guidance on the expansion of spatial conservation. Autumn 2023: scope the need for improving the assessment methodology, as well as establish data requirements. 2024: Methodology development, publication of data call, data collation. 2025: run assessment, analysis of results and finalizing report. 2027-2030: Once the assessment is available the WG is to share information on how CPs are taking action to improve coherence. | The assessment of coherence of HELCOM MPAs is completed by 2025. (Joint supporting action)
2 | [9 empty] | Possible spatial conservation expansion to improve coherence are identified by 2027. (National measure)
2 | [9 empty] | The HELCOM MPA network is fully coherent including with respect to adequacy, connectivity (incl. migration), replication and representativity, taking into account the changing climate, in 2030. (Joint measures)
2 | 23 | NA |  | Improve the understanding of the role of MPAs for ecosystem services, in order to enhance cost-effectiveness of MPAs management and yield the greatest environmental benefits. | PROTECT BALTIC | WG BioDiv | - | MSP4BIO, BLUE4All | 2023-2028: PROTECT BALTIC and BLUE4All will progress the work on ecosystem service provisioning, distribution and valuation. PROTECT deliverables 4.1 conceptual framework mid/end 2026, 4.2 decision support tool mid/end 2026, 4.3 updated ecosys assessment methodology mid 2027, 4.4 gap analysis of ecosystem services methodoly end 2027, 4.5 report on multipupose use end 2027 | By 2028 provide clear indication of current and future potential of MPAs to contribute to provisioning of ecosystem services (type and magnitude of contribution), as well as the value associated with the services.
2 | 24 | NA |  | Establish coordination mechanisms for management of pressures and impacts on MPAs, in particular for adjacent transnational MPAs | PROTECT BALTIC | WG BioDiv | - | PROTECT BALTIC | Spring 2024: Working group to scope needs and requirements for a coordination mechanism and prepare a proposal. Autumn 2024: include an agreed way forward in the updated workplan. TBD the way forward to be included in this workplan 2023-2028: PROTECT BALTIC project will produce regional overviews of the spatial distribution of pressures and impacts inside and outside of MPAs, as well as divide pressures into direct and indirect, directing how these should be handled, as well as provide impact analysis for the various ecosystem components existing in and/or included in the conservation objectives of the MPAs (both adjacent transnational ones and others) | By end of 2024: Clear next steps agreed and included in next WP update.
2 | [9 empty] | By 2027: Transnational coordination mechanism established
2 | 25 | NA |  | Increase capacity for developing multi-management plans for marine protected areas. | PROTECT BALTIC | WG BioDiv | - | - | Autumn 2024: Arrange a MPA managers capacity building WS on the process, experiences and best practices of developing multi-management plans. 2023-2028 PROTECT BALTIC: Include guidance on developing multi management plans in the update of the HELCOM MPA management manual | By end of 2028: Chapter on multi management plans in the update of the HELCOM MPA management guideline.
2 | 26 | NA |  | Collate and provide information on how to consider nature conservation needs, ecologically significant areas (also outside the protected areas) and ecosystem function in Maritime Spatial Planning and vice versa. |  | WG BioDiv | HELCOM-VASAB MSP WG | MSP4BIO, eMSP | 2023: Scoping workshop jointly with MSP practitioners to identify a common language and shared objectives as well as concrete areas and formats of cooperation (MSP4BIO and eMSP). 2023-2028: PROTECT BALTIC will prepare biodiversity distribution maps, ecosystem service distribution maps, connectivity analyses etc which are of high relevance for MSP.
2
2 | 27 | National/Joint | B8 | By 2022 at the latest, specify knowledge gaps on all threats to the Baltic Proper harbour porpoise population, and by 2023 for the western Baltic population, including by-catch and areas of high by-catch risk, underwater noise, contaminants and prey depletion. Knowledge gaps related to areas of high by-catch risk are to be addressed and by 2028 at the latest additional areas of high by-catch risk for both Baltic Sea populations are to be determined. To strengthen Baltic harbour porpoise population, by 2025 identify possible mitigation measures for threats other than by-catch and implement such measures as they become available. | Poland, [WWF] [Sweden] | WG BioDiv | EG MaMa, EG Noise, EG Haz (biological effects), WG Fish, WG Seabased pressures | S43 (WG Fish), S44 (WG Fish), S45 (WG Fish), S46 (WG Fish), S47 (WG Fish), S48 (WG Fish), ASCOBANS Jastarnia Group | 2025: publish compilation of threats to western Baltic population of harbour porpoise 2025/2026: identify high-risk areas and activities ongoing in the areas | By 2025 knowledge gaps on all threats to the western Baltic population have been specified and listed. (joint supporting action)
2 | [9 empty] | By 2025 possible mitigation measures are identified and implemented as they become available. (National measure)
2 | [9 empty] | By 2028 knowledge gaps related to areas of high by-catch risk are addressed. (joint supporting action)
2 | [9 empty] | By 2028 at the latest, additional areas of high by-catch risk for both Baltic Sea populations have been determined. (joint supporting action)
2 | 28 | Joint | B11 | Maintain an updated map of the sensitivity of birds to threats such as wind energy facilities, wave energy installations, shipping and fisheries. Complete, as a first step, the mapping of migration routes, staging, moulting and breeding areas based on existing data by 2022. By 2025 further develop these maps by incorporating new data, post-production investigation information and addressing the subject of cumulative effects from these activities in space and time. | [Germany], EG Birdmove | WG BioDiv | HELCOM-VASAB MSP WG |  | 2023: EG Birdmove to collate relevant information such as timing/drivers of migration, flight altitude and determinants, breeding and feeding behaviour etc for the relevant species, and submit to WG BioDiv for review. Autumn 2023: Nationally coordinate the data delivery for the data call on collating spatial information on migration routes, staging, moulting and breeding areas based on existing data, results to be processed under EG Birdmove. | By 2025 there are publicly available bird maps that include staging areas, migration routes and where possible migration densities, sensitivity, as well as overlap with possible threats exists, including information on confidence and uncertainty.
2 | [9 empty] | Bird sensitivity maps are regularly updated in line with the action, the first update to be ready by 2025.
2 | 29 | Joint | B24 | Develop tools for, and regularly assess, the effectiveness of other conservation measures for species, besides marine protected areas (MPAs), the first assessment to be done by 2025 as well as assess effect on species through risk- and status assessments by 2029. |  | WG BioDiv | JWG Bird, EG MaMa, [EG Coastal Fish] | - | Autumn 2025: Dedicated session to identify what other conservation measures are available. Using the Habitats Directive list of conservation measures, removing the spatial measures, as a basis. 2026: Explore how to best combine the assessment of effectiveness of other conservation measures with MPAs and develop methodology/tools. 2026: run the assessment and prepare report. | By end of 2025: Overview of available other conservation measures prepared.
2 | [9 empty] | By 2026 tools for assessment of effectiveness of conservation measures for species, other than MPAs, have been developed.
2 | [9 empty] | By 2026 the first assessment of effectiveness of other conservation measures for species, besides MPAs, is ready and publicly available.
2 | [9 empty] | By 2029 the effect of conservation measures for species, other than MPAs, has been evaluated through risk- and status assessments.
2 | 30 | National/Joint | B26 | Protect key ecosystem components including habitat forming species by 2030, by: - assessing the state of, and threats to these key ecosystem components by 2023 -implement effective and relevant threat mitigation measures based on the threat and state assessments, including restricting human activities associated with causing physical loss or disturbance, by 2030 [- identifying suitable measures and types of habitats, biotopes and key ecosystem components for passive or active restoration by 2025 and implementing programmes for restroation as outlined in the HELCOM Restoration Action Plan by 2030] |  | WG BioDiv | WG Sea-based pressures (on mitigation measures), EN Clime, HOLAS | PROTECT BALTIC, B22, B28, B31, B32, S68, B10 | 2025: complement currently prioritized conservation features with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services. 2023-2028: PROTECT BALTIC functions as the platform for identifying key representative ecosystem components based on function for the ecosystem/provisioning of ecosystem services. 2025/2026: BioDiv to come back to discussing and addressing how to cooperate on measures and specify intermediate outputs to help meet the 2030 protection outcome. Coherence with the Nature Restoration Regulation would be important | By 2027 currently prioritized conservation features have been complemented with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services. (joint supportive action)
By 2030 effective measures are in place to mitigate threats and pressures, to improve the status of the identified key ecosystem components. (National measure)
By 2025 suitable areas for restoration of the key system components, including habitat forming species, have been identified. (Joint supporting action)
2 | 31 | Joint | B29 | By 2025 develop, and by 2027 implement, and ensure compliance with, ecologically relevant conservation plans or other relevant programmes or measures, limiting direct and indirect pressures stemming from human activities for threatened and declining biotopes and habitats. |  | WG BioDiv | - | PROTECT BALTIC, B22, B28, B31, B32, S68, B10 | 2025: Based on the results of the assessment and the identified pressures in the Habitat Information Sheet, the relevant CPs work to identify and agree on measures and develop conservation plans for the relevant habitat/biotope. Conservation plans and measures can also be prepared jointly by several CPs. WG BioDiv to track progress. 2026-2027: national implementation of measures and conservation plan. WG BioDiv to track progress.
2 | [9 empty] | By 2025 conservation plans or environmental measures are developed and ready to be implemented. (National supporting action)
2 | [9 empty] | By 2027 conservation plans or other relevant programmes or measures are implemented. (National measure)
2 | [9 empty] | Negative status trends are turned, in the long-term securing favourable status of the relevant habitats and biotopes. (National measure)
2 | [9 empty] | 2025-2030: Track status to support adaptive management and transboundary initiatives
2 | 32 | Joint | B30 | Develop tools for, and regularly assess, the effectiveness of other conservation measures for habitats and biotopes, besides marine protected areas (MPAs), the first assessment to be done by 2025 as well as assess effect on biotopes and habitats through risk- and status assessments by 2029. |  | WG BioDiv | - | - | Autumn : Dedicated session to identify what other conservation measures are available. Using the Habitats Directive list of conservation measures, removing the spatial measures, as a basis. 2024: Explore how to best combine the assessment of effectiveness of other conservation measures with MPAs and develop methodology/tools. 2025: run the assessment and prepare report. | By end of 2025: Overview of available other conservation measures prepared through dedicated session using HD list of conservation measures removing spatial measures as a basis.
2 | [9 empty] | By 2025 tools for assessment of effectiveness of conservation measures for habitats and biotopes, other than MPAs, have been developed.
2 | [9 empty] | By 2025 the first assessment of effectiveness of other conservation measures for habitats and biotopes, besides MPAs, is ready and publicly available.
2 | [9 empty] | By 2029 the effect of conservation measures for habitats and biotopes, other than MPAs, on species has been evaluated through risk- and status assessments.
| 33 |  | S59 | Reduce the impact of impulsive underwater noise on marine biodiversity. (National/Joint) |  | WG Sea-based pressures; EG Noise | HELCOM-VASAB MSP; WG BioDiv; EG Noise; EG MaMa |  |  | Regional and national mitigation measures for the activities generating impulsive noise are in place as defined in the Recommendation on the Regional Action Plan on Underwater Noise. (Joint and national)
3 |  |  |  | 3. Restoration of Baltic Sea biodiversity
3 | 34 | National/Joint | B18 | Restore functional populations of Baltic sturgeon by 2029 implementing the HELCOM Baltic Sea Sturgeon Action Plan. | EG Stur | WG BioDiv | WG Fish, EG Fish-M | activities related to the European Sturgeon Action Plan | The next steps are included in the Action Plan 2025: agree and publish regional database for sturgeon by-catch, initiate possible development of regional sturgeon assessment as indicator on by-catch pressure | Consistent ex-situ conservation programme is implemented, taking advantage of the specimens already secured. (National measure)
3 | [9 empty] | Adoption of the Recommendation on large river restoration.
3 | [9 empty] | In situ conservation programme is implemented and enforced, preventing further loss of the remaining specimens. (National measure)
3 | [9 empty] | A strategic long-term monitoring programme for population development and habitat use, to support adaptive management, is in place in all relevant countries. (National supporting action)
3 | [9 empty] | A dedicated programme on habitat protection and rehabilitation has been developed, in order to ensure that spawning and nursery sites meet the needs of the species and are accessible for the respective life cycle stages. (Joint supporting action)
3 | [9 empty] | A dedicated programme on habitat protection and rehabilitation, ensuring that spawning and nursery sites meet the needs of the species and are accessible for the respective life cycle stages, has been implemented where relevant. (National measure)
3 | [9 empty] | Successful, self-sustaining, re-introduced population of Baltic sturgeon is in its potential spawning rivers and in key areas of its former natural range. (National measure)
3 | 35 | National/Joint | B26 | Protect key ecosystem components including habitat forming species by 2030, by: [- assessing the state of, and threats to these key ecosystem components by 2023] -implement effective and relevant threat mitigation measures based on the threat and state assessments, including restricting human activities associated with causing physical loss or disturbance, by 2030] - identifying suitable measures and types of habitats, biotopes and key ecosystem components for passive or active restoration by 2025 and implementing programmes for restoration as outlined in the HELCOM Restoration Action Plan by 2030. | PROTECT BALTIC | WG BioDiv | - | implementation of the EU restoration law and the UN Decade of Ecosystem Restoration | 2023-2028: PROTECT BALTIC will work on the identification and agreement of a list of key ecosystem components, identification of possible measures, measures effectiveness analysis and, development of the Restoration Action Plan and toolbox, in close collaboration with WG BioDiv | By 2026 suitable areas for restoration of the key ecosystem components, including habitat forming species, have been identified. (joint supporting action)
3 | [9 empty] | By 2030 effective measures are in place to mitigate threats and pressures, to improve the status of the identified key ecosystem components. (National measure)
3 | 36 | National/Joint | B27 | By 2025 develop and by 2026 start implementing a HELCOM Action Plan for habitat and biotope restoration, including qualitative and quantitative regional targets, a prioritized list of actions, and an associated implementation toolbox outlining best practices and methods for restoration in the Baltic Sea region. | PROTECT BALTIC/Sweden | WG BioDiv | - | S52 (WG Fish). This work will be closely tied to the EU regulation on restoration. | PROTECT deliverable 6.23 restoration action plan, 6.24 restoration toolbox, 2026/2027 From 2022 onwards: at regular intervals identify and share information on methods and national work on ecosystem restoration in the Baltic Sea, From 2023 onwards: share information on development of indicators to track progress of restoration efforts and their effect 2024: use the discussions in the WG to identify regional priorities, taking into account possible measures outlined in the Red List recommendation and Red List Species and Habitat Information Sheets. 2024: explore the need/possibility of a HELCOM Recommendation on restoration, to support the Action Plan. 2023-2028: PROTECT BALTIC will function as the platform for discussions, arranging dedicated sessions/WSs as needed and preparing input material, as well as the draft plan | By 2025 qualitative and quantitative regional targets for habitat and biotope restoration have been established. (Joint supporting action)
3 | [9 empty] | By 2025 a prioritized list of restoration actions has been developed and is publicly available. (Joint supporting action)
3 | [9 empty] | By 2025 a HELCOM Action Plan for habitat and biotope restoration has been developed and is publicly available. (Joint supporting action)
3 | [9 empty] | By 2026 an implementation toolbox outlining best practices and methods for restoration has been developed to support the implementation of the HELCOM Action Plan for habitat and biotope restoration (Joint supporting action)
3 | [9 empty] | By 2026 the implementation of the HELCOM Action Plan has commenced. (National measure)
3 | 37 | NA |  | To discuss and share experiences on the national work on the EU Restoration Law |  | WG BioDiv | - | EU Restoration Regulation | From 2022 onwards: WG BioDiv to be used as a platform for regional coordination of national restoration efforts, by helping to ensure that efforts are ecologically relevant, synergistic and that actions in one area do not jeopardize the possibility of success, nor effectiveness of, restoration efforts elsewhere. | By 2026 review and identify topics where a regional approach would be useful to Contracting Parties that are also EU Member States in developing their national restoration plans
4 |  |  |  | 4. Climate change impacts on Baltic Sea biodiversity
4 | 38 | Joint | HT1 | Using the HELCOM/Baltic Earth Joint Expert Network on Climate Change as a platform and through committed implementation of the HELCOM Science Agenda, improve the access of policy-makers to scientific information on the impacts of climate change together with multiple other pressures on the Baltic Sea marine environment through periodic updates of the HELCOM Climate Change Fact Sheet, and incorporate the possible effect of climate change into the holistic assessment of status as well as effectiveness of measures by 2030 at latest. | EN Clime | WG GEAR | WG BioDiv, WG Source to sea, WG Sea-based pressures, WG Fish, EG MaMa, EG Benthic, EG Phyto, EG Zoo, JWG Bird, [EG Coastal Fish] | BEAR development under BALTIC EARTH | 2023-2024: Review of HOLAS 3 and scoping and planning the HOLAS 4 preparatory work, including how to further improve integration of climate change in the status assessment for biodiversity and ecosystems. 2025: support the preparation of possible additional parameters, using the established CCFS procedure. | By 2025, possible inclusion of additional biodiversity parameters into the updated CCFS
4 | 39 | Joint | HT5 | Develop a strategic approach to ocean acidification for the Baltic Sea with first steps addressing the knowledge gaps by 2025. |  | WG GEAR | WG BioDiv, EN Clime, WG Source to sea, EG Eutro, EG RedCore | Indicator development for acidification under HELCOM. ECOSTAT acidification processes, EEA acidification indicator work. OSPAR ICG on Acidification and the Ocean Acidification Alliance. | 2025 WG BioDiv to provide input to scoping study as requested | By end of 2025 knowledge gaps in relation to ocean acidification in the Baltic Sea have been identified.
4 | [9 empty] | By end of 2025 identified knowledge gaps in relation to ocean acidification in the Baltic Sea have been addressed.
4 | [9 empty] | By 2030 a strategic approach to ocean acidification for the Baltic Sea has been developed and adopted.
4 | 40 | NA |  | Concretize how the MPA network are and/or could contribute to mitigating the effects of climate change. | PROTECT BALTIC | WG BioDiv | - | Climate Change Fact Sheet (EN Clime), ecosystem service work (EG ESA, HOLAS) | 2023-2028: PROTECT BALTIC will work with ecosystem service provisioning, species distribution under various climate scenarios, resilience proxies. PROTECT deliverables; 3.8, 3.9 estimates for future abiotic conditions and distribution of species and habitats by mid/end 2026, 5.5. optimising MPA maps 2028 (among the last activities to be started in the project) IC WG BIODIV 4-2024 pointed out that the task could consider how strict protection encompasses carbon rich environments, how many climate considerations have already been reflected in MPA designations and management, noting further that in some Contracting Parties a species occurrence being sensitive to climate change impacts is a criterion for MPA designation. | By 2028 present clear indication of the current and future potential of MPAs to contribution to mitigation of the effects of climate change (type and magnitude of contribution).
5 |  |  |  | 5. Monitor Baltic Sea biodiversity
5 | 41 | Joint | HT6 | Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements. | CP leads as identified under GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDiv, WG Source to sea; WG Sea-based pressures; EG Haz; EG Eutro; EG MaMa; EG ML; EG Noise; EG Phyto; EG Zoo; JWG Bird, EG Benthic | PROTECT BALTIC, MSFD Art.11 | Autumn 2024-2026: Begin the process to update the biodiversity related monitoring programmes to ensure the review and update is finalized and the updated monitoring manual and programmes are published in early 2026, in good time before the national Art.11 reporting concludes. [2023-2028: PROTECT BALTIC will review monitoring methods for monitoring of pressures and biodiversity in MPAs, but which are possibly also relevant for monitoring overall and could be used to support the review of the monitoring programmes]. | Updated monitoring programmes are available every six years in line with what is specified in the action.
5 | 42 | NA |  | Contribute to and guide the development of biodiversity and ecosystem related regional monitoring guidelines. | On a need basis. | WG BioDiv | - | - | [2023-2028: PROTECT BALTIC will review monitoring methods for monitoring of pressures and biodiversity in MPAs, but which are possibly also relevant for monitoring overall and could be used to support the review/development of monitoring guidelines]. | New monitoring guidelines for biodiversity and protection available when relevant.
5 | 43 |  | HT9 | Map biotopes and habitats nationally based on regionally comparable classification systems, including key habitats and habitat forming species, and identify gaps in spatial coverage of mapping efforts, with the aim to produce Baltic-wide models, including production of maps, of distribution of habitats and biotopes by 2028. |  | WG BioDiv |  |  | PROTECT BALTIC WG BioDiv to come back to guidance issues with benthic work by identifying gaps in coverage of mapping and modelling efforts and specify regional tasks
5 | 44 | National/Joint | HT10 | Target the gaps identified in the HELCOM monitoring programmes of biotopes, habitats, including key habitats and key habitats forming species by 2024 and operationalize continual Baltic-wide monitoring of those biotopes and habitats by 2030. |  | WG BioDiv | EG Benthic | MSDF Art.11 | Spring 2023: Utilize the gap analysis prepared under the SEAM and FUMARI project, as well as any relevant information identified under the scoping of gaps in at sea monitoring, to collate an overview of existing gaps. Review the overview to identify national gaps, as well as any overlooked species/habitat/biotope specific gaps. Autumn 2023: Identify possible solutions to the gaps 2024: Agree on methodology, data formats, target components, frequency etc. 2025: update HELCOM Monitoring Manual monitoring programmes to represent status-quo and identify any significant gaps in spatio/temporal coverage for any project 2029: expand national monitoring programmes so that all HELCOM indicator assessment requirements have been met | By 2025 a full gap analysis is made for monitoring programmes of biotopes and habitats. (joint)
5 | [9 empty] | By 2027 gaps for monitoring programmes of biotopes and habitats are addressed and updated monitoring programmes and guidelines prepared. (joint)
5 | [9 empty] | By 2030 continual Baltic-wide monitoring of biotopes and habitats is operationalized. (National)
5 | 45 | Joint | HT11 | Develop quality standards for seafloor habitat mapping and derived products by 2024. | needed | WG BioDiv | EG Benthic | EMODnet EUSeamap, PROTECT BALTIC | Spring 2024: WG to review plan, identify lead(s) for drafting. Autumn 2026: WG to review the draft standards and provide guidance and input. Spring 2029: Approve the finalized standards for layout and publication. 2023-2028: PROTECT BALTIC will develop modelling approaches for modelling benthic habitats and biotopes, as well as produce maps. As part of this work it is likely that the project will produce information on quality requirements for both data and products, which can be included in the work on establishing standards. 2025/2026: Engagement with EMODNet Seabed | By end of 2026 standards for quality of seafloor habitat mapping have been developed and agreed
5 | [9 empty] | Standards for quality of seafloor habitat mapping products have been agreed
5 | 46 | National/Joint | B15 | Develop and coordinate monitoring and assessment methods, where ecologically relevant, for specified representative coastal fish species, populations and communities, by 2023. [Based on these assessment methods, to regularly assess the state of the coastal fish communty through selected coastal fish species and groups, including threatened species, by at latest 2023. Based on the results of the assessment, develp and implement management measures with the ambition to maintain or improve the status of coastal fish species, including migratory species by 2027.] | [EG Coastal fish] | WG BioDiv | WG Fish | S53 (WG Fish) | 2025: [EG Coastal fish] to develop HELCOM monitoring guidelines for the representative species, WG to approve, with the ultimate aim of securing comparable data and results 2024-2026: [EG Coastal fish] to further develop assessment methods for assessment of coastal fish species towards HOLAS | By 2025 monitoring guidelines are available which cover all the representative species.
5 | [9 empty] | By 2027 further refined assessment methodology available for assessment of representative coastal fish.
5 | 47 | NA |  | Establish persistent regular data flows and data management for all biodiversity and ecosystem data needed for HELCOM assessment and tracking purposes. |  | WG BioDiv | EG MaMa, JWG Bird, EG Birdmove, [EG Coastal Fish], EG Zoo, EG Phyto, EG Benthic | - | From 2023 onwards: Using the review of the HOLAS 3 (2023), RED LIST (2023) and PROTECT BALTIC (2025) data reporting and processes as a basis, identify gaps in dataflows and infrastructure. Analyze the underlying causes and identify solutions. Implement solutions to secure improved, consistent dataflows. | Lower resource requirements long term due to automatised data reporting.
5 | [9 empty] | Improved access to data and information across the region.
5 | [9 empty] | Enabling automatising assessment procedure.
5 | 48 | S38 | S38 | Undertake monitoring and pollution risk assessment regarding species and habitats in the Baltic Region by 2026. |  | WG Response | WG GEAR;WG BioDiv; EG Wildlife, EG Birdmove; EG MaMa; JWG BIRD | Other groups to report barriers to WG GEAR. Need to interpret the action jointly to come up with a cross-topical plan for how to address this action, what is already available and where further HELCOM work can add value. | WG BioDiv to respond to WG Response request for input as relevant | An analysis of data stemming from existing monitoring to determine vulnerable species, vulnerable areas, vulnerable times of the year is conducted.
5 | [9 empty] | Results are presented in a format which fulfils the needs of an operational manager, e.g. seasonal maps with risk indications, scale indications. etc.
5 | [9 empty] | A risk analysis as to how response activities could also impact certain species and habitats in areas, seasons, or certain circumstances is conducted.
6 |  |  |  | 6. Cooperate with international organisations
6 | 49 | NA |  | Identify and engage in relevant current and emerging international initiatives and processes on regional, interregional, EU and global level. | - | WG BioDiv | - | Biodiversity related SDGs, CBD, UNEP, UN Decade of Ocean Science, UN Decade of Ecosystem Restoration, EU Green Deal, EU Biodiversity Strategy, EU MSFD, EU HBD, EU Restoration Law, RSC initiatives, CMS. | At each meeting share information on current and emerging international initiatives and processes of relevance for the WG. Scope the possible contribution and benefit for HELCOM and engage accordingly. | Improved visibility, impact and uptake of HELCOM work outside of the immediate Baltic Sea region. (continuous)
6 | [9 empty] | HELCOM work is current, fit-for-purpose and can support CPs in their efforts to implement other international commitments.
6 | 50 | NA |  | Communicate regional work that contributes to CBD global biodiversity targets |  | WG BioDiv | - | CBD global biodiversity targets. | Desscribe the regional HELCOM work that could be put forward as contributions to CBD GBF targets | Improved overview of, and possibility to report on, how CPs work in HELCOM concretely contributes to reaching the global targets.
0 |  |  |  | General and recurring tasks inlcuding implementation or relevant HELCOM commitments
0 | 51 | NA |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group | relevant country leading the Recommendation. | WG BioDiv | - | - | Persistent agenda item on the WG’s agenda with overview and discussion during autumn-meetings, with the intention that implementation is supported, a lead is available for each Recommendation, reporting intervals and formats are established and that reporting follows a rolling system where implementation of Recommendations are regularly tracked and reviewed. | Plan for the implementation, reporting and possible revision of the Recommendation at each meeting.
0 | 52 | NA |  | Regularly review Baltic Sea Environment Factsheets (BSEFs) relevant to the groups remit and approve any new BSEFs for publication. | relevant country leading the Recommendation. | WG BioDiv | - | - | Persistent agenda item on the WG’s agenda, with the intention to ensure information presented is current and relevant and that any emerging topics are covered. 2 BioDiv BSEFS to maintain | Up-to-date BSEFs available on the HELCOM website.
0 | 53 | NA |  | Review, and possibly revise, the HELCOM Recommendation 35/1 | Finland, supported by Sweden | WG BioDiv | - | PROTECT BALTIC | 2024/2027: [in close cooperation with PROTECT BALTIC] elaborate the needed revisions, reporting requirements, structures intervals etc. 2027: Submit the updated Recommendation to HOD for approval. 2028: Adoption of new Recommendation at HELCOM | By 2028 reviewed and possibly updated Recommendation adopted.
0 | 54 | NA |  | Note and discuss results from national reporting on BSAP action implementation or BioDiv relevance |  | WG GEAR |  |  | TBC Spring 2026
0 | 55 | NA |  | Follow up on and support EG work to achieve RevDev workplan aims