## WG GEAR
Approved in March 2025 via correspondence by the Helsinki Commission
No | BSAP Action | Task | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments | Output
I. Strategic level guidance and coordination of internal HELCOM processes
1 | NA | Integrate and utilize the work of other working groups and projects so as to ensure the implementation of the ecosystem approach. (ToR duty) | WG Chairs | WG GEAR |  | HELCOM projects. | 2025: Note and discuss the interpretation of practical application of an ecosystem-based approach to managing human activities related to ongoing work in - WG Fish to create a common understanding in collarboation with BALTFISH and BSAC - HELCOM-VASAB MSP WG on updating Guidelines on ecosystem based MSP | Common understanding of practical application of ecosystem-based approach to managing human activities
2 | NA | Communicate the needs for activities and deliverables (e.g. purpose, timing and alignment of the work with HELCOM commitments) to other HELCOM subsidiary bodies. (ToR duty) | no lead necessary | WG GEAR | All HELCOM groups | HELCOM projects. |  | Maintain the living-document compilation of HELCOM timelines and make it available as INF to WG sessions
3 | NA | Oversee timely finalization of implementation processes, following the scrutiny in the scientific, technical and management working groups (ToR duty) | [5 empty] | HELCOM peer-reviewed implementation outputs of high scientific, technical and managerial standard
4 | NA | Catalyze/facilitate cooperation across HELCOM groups through enabling communication between Group Chairs. (ToR duty) | no lead necessary. | WG GEAR | All HELCOM Working Groups. |  | Annually during autumn sessions of WG GEAR; plan a dedicated session for all HELCOM WG Chairpersons, including identifying issues of a horizontal nature that would benefit from being shared/discussed at the session. NB: climate change topics are a standing agenda item for this cooperation session | Annual dedicated session for all HELCOM WG Chairpersons arranged.
II. Identifying funding to implement relevant activities
5 | NA | Propose/initiate projects according to HELCOM needs. (ToR duty) | no lead necessary. | WG GEAR | All HELCOM groups |  |  | Maintain the living document compilation funding sources and make it available as INF to WG sessions
6 | NA | Support prioritization and securing of resources to enable implementation (ToR duty) | no lead necessary. | WG GEAR | - |  | At every meeting: share information on possible upcoming funding opportunities/calls. Communicate priority for work towards HOLAS 4, and identify national processes or opportunities to support the prioritized work. | Regularly share information on possible upcoming funding opportunities and national priorities for funding
Draft and maintain a living document identifying priority assessment method development work towards HOLAS 4, and HELCOM Science Agenda priorities and make it available as INF to WG sessions
Provide input to HOD discussions based on coordinated discussions on financing priorities and gaps
Tool for identifying open actions/financing instruments to inform future WG workplan updates.
III. Coordination of BSAP implementation
7 | NA | Horizontal coordination of BSAP implementation, e.g. to provide guidance to, and assist, other HELCOM groups in identifying and overcoming barriers and challenges related to the implementation of the BSAP actions, under the remit of the ecosystem approach and ecosystem-based management. (ToR duty) | no lead necessary | WG GEAR | All HELCOM Groups. |  |  | By 2026 update full, cross-segmental, overview of BSAP target years based on 2025 implementation reporting
From 2023 onwards: Dedicated time set aside in each meeting to troubles-shoot and find solutions for barriers to implementation.
2025: review functionality of BSAP implementation tracking approach and WG GEAR support to WGs on addressing barriers to implementation, and update approach as needed
2026: develop an updated WG GEAR workplan for 2027-2028 including identification of barriers to implementation
8 | NA | Track the progress of implementation of the BSAP actions, including analyses based on the reporting to the HELCOM Explorer. (ToR duty) | no lead necessary. | WG GEAR | All HELCOM Working Groups |  |  | spring 2025: Develop guidance for natioal focal points to complete implementation reporting on national BSAP actions
autumn 2025: Oversee national implementation reporting on BSAP actions
Spring 2025: Analyse all results for joint actions reporting identifying and considering possible barriers for implementations, and compile preliminary report to HOD including an update of the overview of target years of BSAP actions (IC WG GEAR 4-2023 doc 5-3 Att1):
spring 2026: consider any final updates from WGs on joint action implementation. Analyse all results from national implementation reporting, and compile preliminary report to HOD
late spring / early summer 2026: draft brouchure/report of BSAP implementation for 2026 Ministerial Meeting utilising reports on joint and national actions and the overview of target years
2026: targeted, fit-for-purpose complementary measures and actions presented for adoption at the 2026 MM.
9 | NA | Coordinate the implementation of the horizontal topic knowledge exchange and awareness raising. (ToR duty) | no lead necessary. | WG GEAR | - |  | 2025: based on the input from the campaign, as well as the results of the tracking of BSAP implementation, priorities topics for targeted future campaigns. | 2025: Priotritise topics for future BSAP implementation communication campaigns
2026: Develop BSAP implementation communication campaign towards Ministerial Meeting 2026
10 | NA | Explore resources for the implementation of the BSAP actions, both nationally and jointly using HELCOM as a platform. This can include following up on resources used or planned as well as identifying and supporting securing external resources (ToR duty) | [5 empty] | Implement ToR duties under theme II. Identifying funding to implement relevant activities
11 | NA | Ensure the periodical review of the Science Agenda to ensure that the science and research needs to implement the BSAP are up to date. (ToR duty) |  | WG GEAR | All HELCOM groups |  | 2025: establish a process for how the review and update of the Science Agenda should take place. 2025: based on the information on barriers to progress identified as part of the review of BSAP implementation, as well as any new or complementary measures and actions elaborated for the Declaration, update the Science Agenda. 2026: submit the updated Science Agenda to the 2026 Ministerial Meeting. | 2025: identify topics from the HOLAS3 review and HOLAS4 RevDev that may benefit from inclusion in an update of the HELCOM Science Agenda
2025: Invite WGs to list proposals for concrete topics and issues that would benefit from inclusion on the HELCOM Science Agenda
2026: Up to date and fit for purpose Science Agenda to support the implementation of BSAP as a contribution to the 2026 Ministerial Meeting.
IV. Initiating and coordinating assessments and indicators
12 |  | Follow and guide the assessment work under HELCOM to ensure horizontal coordination and that planned work supports HELCOM commitments (ToR duty) | EG MSFD | WG GEAR |  |  | As needed, work with HELCOM projects to provide policy and governance input, as well as where relevant guide the production of end-products to ensure they align with HELCOM needs. (STEP MOVED FROM PREVIOUS TASK 14) | Implement B33 (by 2030)
Early 2025: Carry out survey of how Contracting Parties have used HELCOM pre-filled information in national EU MSFD Art 8 reporting, and use the information to guide development
13 | B33 | By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). (Joint) | No lead needed. | WG GEAR | WG BioDiv;WG Source to sea; WG Sea-based pressures |  | Roadmap for addressing gaps in assessments towards HOLAS 4 was developed based on HOLAS 3 surveys and subsequent RevDev work, and identified topical workplans. Follow-up on the implementation of the Roadmap and preparations for the HOLAS 4 assessment phase. (MOVED from previous task 14) 2026/2027: guide the development of the indicator, thematic assessment and summary reports, e.g. through the review and approval of report templates etc. | 2025: Establish a detailed timeline, process and workplan for HOLAS 4 assessment phase (moved from previous task 11)
2026: HOLAS 4 data call published (moved from previous task 11)
By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available.
14 | B35 | By 2024 operationalize a set of indicators for the assessment of fish population health, including size and age distribution, where applicable, and, by 2029, for any remaining relevant species. | [EG Coastal Fish] [Sweden] | WG BioDiv | WG GEAR, WG Fish | S40, S48, possible ongoing work within ICES | Support the role of HELCOM in driving the assessment including policy steer for setting threshold values, communication with WG Fish and WG BioDiv | By 2029 health, size and distributional indicators are available for all relevant species.
15 | NA | Secure and ensure consistent dataflows horizontally across topics in HELCOM. | no lead necessary. | WG GEAR | relevant Working/Expert Groups involved in data reporting. |  | Regularly, jointly with relevant WGs and subsidiary bodies and using the review of the data reporting under HOLAS 3 (2023), RED LIST (2023), ReMap [PROTECT BALTIC (2025)] and other initiatives and processes as a basis, identify gaps in dataflows and infrastructure. Analyze the underlying causes and identify solutions, both regional and national. Implement solutions to secure improved, consistent dataflows. Explore any issues with using pre-filled information in EU MSFD Art8 reporting, and as necessary develop furhter instructions on templates to collect the information needed as pre-fill information in indicator assessments for HOLAS 4 | Lower resource requirements long term due to automatised data reporting.
Improved access to data and information across the region.
Enabling automatising assessment procedure.
16 | NA | Oversee development of spatial datasets (further develop the HELCOM Spatial Pressure and Impacts Assessment (SPIA) |  | WG GEAR | WG BioDiv, WG Sea-based Pressure, WG Source to Sea, WG Maritime |  | Coordinate and steer the further development of the methodology and the data collection for SPIA. Give policy steer on the use of SPIA in applications of the ecosystem based approach to managing human activities | Use of SPIA data for HOLAS 4
V. Initiate and coordinate horizontal aspects of monitoring
17 | NA | Coordinate the recurring review and update of the HELCOM Monitoring Manual and Monitoring Programmes (ToR duty) | [5 empty] | Implement HT6
18 | HT6 | Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements. (Joint) | CP leads as identified under WG GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDiv;WG Source to sea; WG Sea-based pressures based on topical expertise; EG Haz; EG Eutro; EG MaMa; EG ML; EG Noise; EG Phyto; EG Zoo; JWG BIRD | MSFD monitoring programs review and reporting. | Begin the update process latest in autumn 2024 to ensure the review and update is finalized and the updated monitoring manual and programmes are published in early 2026, in good time before the national Art.11 reporting concludes. | Updated monitoring programmes are available every six years in line with what is specified in the action.
19 | NA | Coordinate the HELCOM Monitoring and Assessment Strategy and Data and Information Strategy regiew and update (ToR duty) |  |  |  |  | This task equates to coordinting implementation of Recommendation 19/3 which RECOMMENDS to the Governments of the Contracting Parties to the Helsinki Convention that: a) the monitoring of the state of the marine environment of the Baltic Sea should be performed in accordance with the HELCOM Monitoring and Assessment Strategy and the HELCOM Monitoring Manual; b) the annual coordinated monitoring data, as committed by the Contracting Parties in the HELCOM Data and Information Strategy, should be reported or made available to the Commission on deadlines given in the HELCOM Monitoring Manual (Introduction, chapter “Data and reporting“). | Implement HT7 (and HT6, HT8)
20 | HT7 | The validity of HELCOM Monitoring and Assessment Strategy and Data and Information Strategy should be reviewed within two years after updating the BSAP and revised as needed. (Joint) | Estonia, Germany, Sweden, Poland | WG GEAR |  |  | Updated Strategy to be approved in spring 2026 and adopted at HELCOM Ministerial Meeting in autumn 2026. | Reviewed and, as necessary, updated monitoring and assessment strategy is available by 2026.
21 | NA | Track progress, and report on Recommendation 37/1 “Co-operation and Coordination of Research Vessel Based Monitoring in Off-Shore Areas and Procedures for Granting Permits for Monitoring and Research Activities” |  | WG GEAR | WG BioDiv;WG Source to sea; WG Sea-based pressures based on topical expertise. |  |  | By 2025 disucss the use and dissemination and then publish the results from the 2024 reporting under the Monitoring Strategy secion of the helom.fi web-page
By 2026 use the coordination of vessel information to plan and implement joint monitoring activities
22 | NA | Work to ensure that identified gaps across the monitoring programmes are filled and that monitoring programmes are regionally coordinated (ToR duty) |  | WG GEAR |  |  |  | Implement HT8
23 | HT8 | Ensure all HELCOM monitoring programmes are regionally coordinated by 2026. (Joint) | The entity that develops a monitoring programme is also lead to ensure regional coordination | WG GEAR | EG Haz; EG Eutro; EG MaMa; EG ML; EG Noise; EG Phyto; EG Zoo; JWG BIRD; EG Benthic |  | Follow up Working Group efforts in addressing the 9 prioritised gaps in coordination | By end of 2026 all monitoring programmes fulfil the requirements for the category "regionally coordinated", as defined under the Marine Strategy Framework Directive and in the guidance for review of the HELCOM monitoring programmes.
24 | S38 | Undertake monitoring and pollution risk assessment regarding species and habitats in the Baltic Region by 2026. (National/Joint) |  | WG Response | WG GEAR;WG BioDiv; EG Wildlife, EG BirdMove; EG MaMa; JWG BIRD |  | Other groups to report barriers to WG GEAR. Need to interpret the action jointly to come up with a cross-topical plan for how to address this action, what is already available and where further HELCOM work can add value. | An analysis of data stemming from existing monitoring to determine vulnerable species, vulnerable areas, vulnerable times of the year is conducted.
Results are presented in a format which fulfils the needs of an operational manager, e.g. seasonal maps with risk indications, scale indications. etc.
A risk analysis as to how response activities could also impact certain species and habitats in areas, seasons, or certain circumstances is conducted.
VI. Initiate and coordinate work on climate change
25 | NA | Coordinate the identification of, and ensure synergies across, climate change related work under the various work stands of HELCOM. (ToR duty) | No lead necessary. | WG GEAR | WG Chair from all HELCOM WGs |  | The WG Chairs to report back on ongoing and planned work under each WG at the autumn meeting of WG GEAR annually. Annually the spring meeting reviews ongoing and planned work under the WGs and relevant project work with HELCOM involvement for possible synergies and, where such are found, provides guidance to the next meeting of the relevant WGs. | Discuss climate change topics during the WG GEAR and WG Chairs sessions
Implement HT1, HT4, HT5
26 | HT1 | Using the HELCOM/Baltic Earth Joint Expert Network on Climate Change as a platform and through committed implementation of the HELCOM Science Agenda, improve the access of policy-makers to scientific information on the impacts of climate change together with multiple other pressures on the Baltic Sea marine environment through periodic updates of the HELCOM Climate Change Fact Sheet, and incorporate the possible effect of climate change into the holistic assessment of status as well as effectiveness of measures by 2030 at latest. | EN Clime | WG GEAR | WG BioDiv, WG Source to sea, WG Sea-based pressures, WG Fish, EG MaMa, EG Benthic, EG Phyto, EG Zoo, JWG Bird, [EG Coastal Fish] |  | The latest update of climate change fact sheets in 2024 updated some parameters and included some new parameters. The next update is scheduled for 2028 (i.e. at 7-year intervals). | The HELCOM Climate Change Fact Sheet is periodically updated.
[7 empty] | No climate change specific RevDev workplan was developed based on HOLAS3, however some RevDev tasks reference needed improvements regarding climate change. The next step in delivering the agreed output could be to specify the indicator reports and thematic reports where climate change effects should be more robustly incoorprated, for example by using the climate change fact sheets. In HOLAS 3 indicator managers were requested to add descriptive information or assessments of how the indicator would be affected by climate change. | Possible effect of climate change have been incorporated into the holistic assessment of status of the Baltic Sea environment
[7 empty] | WG GEAR to instruct EG ESA and project sucha s PROTECT to take climate change into account in SOM analyses | Possible effect of climate change have been incorporated into the assessment of effectiveness of measures.
27 | HT4 | Promote research that increases understanding of the role of the Baltic Sea land-sea system in the carbon cycle and identifies how mitigation by natural blue carbon processes can be maximised and implement suitable measures. Increased understanding should be utilised to enable consideration of additional management measures. (National/Joint) | No lead necessary. | WG GEAR | EN Clime |  | Analyze the action components and identify possible individual steps for implementation and identify the most appropriate groups to take the work forward. Discuss how to promote research nationally/regionally. List financing initiatives that have been put in place under each country. | By 2030 understanding has been improved e.g. through the financing of relevant research projects. (National)
By 2030 the improved knowledge base has been utilized to review and, if relevant, identify additional management measures. (Joint)
28 | HT5 | Develop a strategic approach to ocean acidification for the Baltic Sea with first steps addressing the knowledge gaps by 2025. (Joint) |  | WG GEAR | WG BioDiv, EN Clime, WG Source to sea, EG Eutro, EG RedCore | Indicator development for acidification under HELCOM. ECOSTAT acidification processes, EEA indicator work, OSPAR ICG on acidification, Ocean Acidification Alliance | Utilize existing approaches from other areas when developing the strategic approach. | By 2026 knowledge gaps in relation to ocean acidification in the Baltic Sea have been identified.
By 2028 identified knowledge gaps in relation to ocean acidification in the Baltic Sea have been addressed.
By end of 2025 a strategic approach to ocean acidification for the Baltic Sea has been developed and adopted.
29 |  | Coordinate and help execute the process of incorporating climate change in HELCOM policies (ToR duty) | [5 empty] | Implement HT2
30 | HT2 | Identify the needs and possibilities to further adapt HELCOM’s policies and recommendations to account for effects and impacts on the environment under the changing climate and to develop and carry out a climate change policy review process as part of the work of HELCOM, starting e.g. with indicators and open recommendations. (Joint) | Recommendation leads, lead for different policies needed | WG GEAR | EN Clime | all HELCOM work strands, MSFD update |  | By 2030 a process for adapting HELCOM’s policies and recommendations to account for effects and impacts on the environment under the changing climate is developed and agreed.
By 2030 climate change review process is included as an integral part of all HELCOM policy review processes.
VII. Iinitiate and coordinate work on economic and social analysis
31 | NA | Ensure that HELCOMs work on economic and social analysis is aligned with relevant international initiative and the needs of the Contracting Parties (ToR duty) | [5 empty] | In 2025 provide policy steer on tailoring ESA assessments for policy needs
Implement HT15, HT18, HT20
32 | HT15 | By 2023, integrate economic and social analyses in HELCOM work strands to support the implementation of the ecosystem-based approach and allow for assessment of the linkages between the marine environment and human wellbeing, including carrying out regionally coordinated economic and social analysis of the marine environment. (Joint) | HOLAS 3 | WG GEAR | EG ESA |  | Supporting assessments for HOLAS 4 | Regionally coordinated economic and social analyses which are integrated into environmental assessments such that changes in environmental condition can be linked to changes in welfare.
33 | HT16 | By 2028, improve the use of results from economic and social analyses in decision-making, including through establishing a set of indicators that describe the economic and social aspects of the marine environment. |  | WG GEAR | EG ESA |  |  | A set of indicators for measuring economic and social aspects of the marine environment has been established.
34 | HT17 | By 2030, integrate quantitative and qualitative economic values of the environment into the management of human activities and maritime spatial planning. (national) |  | WG GEAR | EG ESA, HELCOM-VASAB MSP WG |  |  | Quantitative and qualitative values of the marine environment are expressed in relevant documentation/documents for the management of human activities and maritime spatial planning
35 | HT19 | By 2028, apply the framework of ecosystem accounting to assess the contributions of marine ecosystems to economic activity (e.g. Gross domestic product (GDP)) using values that are compatible with the system of national accounts and comparable with other economic sectors. |  | WG GEAR | EG ESA |  | The ecosystem service aspect of further ES assessment work would be taken forward under this BSAP action (carrying on work from HT18 which was completed during HOLAS 3 and included a specific reference to ecosystem services) Further development of ES valuation is planned to take place under the PROTECT BALTIC project, should it be funded (Developing a methodology for valuation of ecosystem services) | Pilot studies on physical and monetary ecosystem services as well as ecosystem asset accounts have been developed and/or compiled.
36 | HT20 | By 2024 analyse existing tools for analysing sufficiency of measures, with the aim to plan monitoring and assessment of the effect and cost of measures, in order to further make use of the experiences when the need of new measures occurs. By 2028, further develop and apply regionally coordinated methods for analyses of sufficiency of measures as well as for cost-effectiveness of measures and costs and benefits to achieve good environmental status of the Baltic Sea marine environment. (Joint) | EG ESA | WG GEAR | EG ESA | [PROTECT BALTIC] | A joint scoping session on SOM development with EG ESA. Some targeted work on conservation measures planned to take place under the PROTECT BALTIC project. | By 2024 existing tools for analysing sufficiency of measures, have been analysed.
By 2028 updated, regionally coordinated methods and tools for analysing sufficiency of measures, cost-effectiveness of measures and costs and benefits to achieve good environmental status of the Baltic Sea marine environment have been created and tested.
By 2028 regionally coordinated methods for analyses of sufficiency of measures as well as for cost-effectiveness of measures and costs and benefits to achieve good environmental status have been applied.
37 |  | Coordinate the efforts to secure data and information to support the work on social and economic analyses | [5 empty] | Consider findings of the Horizon project AquaInfra on identifying and harvesting information, outputting a multi-disciplinary FAIR virtual environment with data in a co-designed EOSC-compliant pilot service
Implement HT21, HT22
38 | HT21 | By 2025 identify incentives to reduce pressures on the marine environment, including public and private economic and regulatory incentives, and by 2030 increase the use of incentives and fill possible gaps. (National/joint) | EG ESA | WG GEAR |  |  | By 2026 identify and secure resources for a study to identify incentives used nationally and regionally and provide initial information on their cost effectiveness. By 2028: publish study and make it available to enable Contracting Parties to learn from each other and identify best practices and gaps. | By 2028 a study on incentives to reduce pressures on the marine environment has been finalized, including proposals for action. (Joint supporting action)
By 2030 the use of incentives should have been increased (at least one relevant example given). (National measure)
These added incentives should preferably be filling a gap where this type of tool was missing. (National measure)
39 | HT22 | By 2025 HELCOM should identify subsidies or incentives which are harmful for the marine environment and, by 2030 work, in cooperation with relevant international organizations, on phasing out such subsidies or incentives. (Joint) | EG ESA | WG GEAR |  |  | 2026 identify and secure resources for a study to identify subsidies and incentives used nationally and regionally and provide initial information on the magnitude of their potential negative effect. By:2028 publish study and make it available to enable Contracting Parties to learn from each other and identify best practices and gaps. | By 2028 finalize an analysis on what subsidies or incentives can be considered harmful and propose actions to reduce these. (Supporting action)
By 2030 cooperative action should have been undertaken on phasing out such subsidies or incentives. (Measure)
VIII. Activities under other international frameworks
40 | NA | Providing information and guidance on HELCOMs role in relation to external international policy processes including but not limited to how is HELCOM contributing or interacting with the process, how are the Contracting Parties working with implementation and how could HELCOM contribute or interact with the process. (ToR duty) | No lead necessary | WG GEAR | all HELCOM Working Groups | SDGs, CBD, UNEP, UN Decade of Ocean Science, UN Decade of Ecosystem Restoration, EU Green Deal, EU Biodiversity Strategy, EU MSFD, EU HBD, EU Restoration Law, RSC initiatives, CMS. PERMAGOV project. | 2025: review progress and, if relevant, provide concretized suggestions for actions for inclusion in the 2026 MM declaration. | Maintain an overview of processes HELCOM is engaged with.
Where needed clear guidance is available on how and why HELCOM engages in other international processes.
41 | NA | Acting as the responsible body for the regional coordination for the implementation of the MSFD, for those Contracting Parties that are also EU Member States, and including coordination with activities under the Maritime Doctrine of the Russian Federation, with the aim to achieve respective coherent national marine strategies. (ToR duty) | no lead necessary. | WG GEAR | EG MSFD | EU MSFD CIS processes | Continue regional coordination efforts in EG MSFD. Include both a formal and informal agenda item on MSFD coordination in the GEAR agenda for each meeting. Coordinate HELCOM work with the national needs and ongoing work on implementation (e.g. assessment, measures, monitoring). Actively align timelines of work to ensure added value of HELCOM processes for national commitments. | Improved, regionally coordinated national strategy.
Supporting material for Contracting Parties who are also EU Member States for national and regional coordination of MSFD implementation.
42 | NA | Identification of areas where there is a need for consistency and opportunities for cooperation and coordination between HELCOM and other Regional Seas Conventions, utilizing the regional Action Plans/strategies to identify areas of cooperation and plan ahead. (ToR duty) | No lead necessary. | WG GEAR |  | EU MSFD CIS processes, inter-regional projects | arrange for informal bilateral meetings with the Secretariats/relevant strategic coordination groups under other RSCs to look for areas of cooperation/synergistic efforts with regards to action plans/strategies as well as planned development work towards the next assessment cycle. | Areas, topics and formats of cooperation identified between HELCOM and other RSCs.
Other tasks
43 | HT27 | Increase knowledge exchange and awareness raising to promote public and stakeholder support and interest in understanding the state of the Baltic Sea and threats to its environment as well as promote opportunities for the general public to participate in citizen science. |  | All |  |  |  | Activities may include issuing press releases, briefings and commentaries
Disseminating reports, studies and publications;
Holding stakeholder meetings related to the work of HELCOM, as well as public meetings, conferences and creating and contributing to educational materials workshops
Development of HELCOM map- and data services to provide coherent information on the status and pressures of the Baltic Sea.
44 | HT28 | Share experiences and best practices on measures that have been implemented. |  | All |  |  |  | Activities may include disseminating reports, studies and publications;
Conferences and workshops as well as information sharing at HELCOM groups.