## WG Maritime
Approved in March 2025 via correspondence by the Helsinki Commission
No | Type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Output [for BSAP actions this will be criteria for achievement, including the deadline]
Regular tasks for the Working Group
Measures and actions enhancing maritime safety
1 |  |  | Propose additional safety measures, including routeing measures | Contracting Parties | WG Maritime | EG Safe Nav |  | Additional safety measures proposed and considered.
2 |  |  | Maintain and update the “HELCOM Routeing Guide for the Baltic Sea” – chart and web page version | Contracting Parties - chart - Germany - web page version – Denmark | WG Maritime |  |  | HELCOM Routeing Guide for the Baltic Sea kept up to date and available online.
3 |  |  | Contribute to HELCOM Maritime Spatial Planning work with maritime input | HELCOM - VASAB WG MSP | WG Maritime | HELCOM Secretariat |  | Input from the Maritime Working Group taken into account in HELCOM Maritime Spatial Planning work.
4 |  |  | Follow-up, contribute to and utilize the results of various risk assessments of shipping accidents in the Baltic Sea |  | WG Maritime |  | In co-operation with WG Response | Results of various risk assessments utilized in informed decision making to reduce the risk of shipping accidents.
5 |  |  | Co-operate with Baltic Icebreaking Management to further improve the safety of navigation in ice conditions | Contracting Parties | WG Maritime |  |  | Recommendation 25/7 is kept up-to-date, as needed.
6 |  |  | Follow up implementation of HELCOM Recommendation 31E/5 on Mutual Plan for Places of Refuge |  | Contracting Parties In co-operation with WG Response and EG Places of Refuge |  | WG Response and EG Places of Refuge | Recommendation 31E/5 is kept up to date and implemented by Contracting Parties.
Consideration of the ways to further reduce emissions and discharges from shipping
7 |  |  | Follow-up new developments regarding availability of technology to treat sewage to Special Area standards and promote harmonised application of Special Area requirements |  | WG Maritime | CP PRF |  | Baltic Sea Special Area under MARPOL Annex IV complied with by ships, as appropriate.
8 |  |  | Carry out work with regard to enforcement of the Baltic Sea NECA area, taking into accoun the NECA Roadmap |  | WG Maritime | Green Team |  | NECA regulations enforced and complied with by ships.
9 |  |  | Consider revision of Recommendation 28/3 on Guidelines on Bunkering Operations and Ship to Ship Cargo Transfer | Contracting Parties | WG Maritime | WG Response |  | Recommendation 28/3 reviewed and updated, if appropriate.
10 |  |  | Carry out activities and provide policy guidance according to the work plan of expert groups and platforms under the WG Maritime umbrella (Green Team, EG AIS, EG Safe Nav, CP PRF, JTG Ballast & Biofouling) |  | WG Maritime
11 |  |  | Summarize the outcome of implementation of more stringent limits of SOx emissions that came into force in 2015 |  | WG Maritime |  |  | Implementation of SOx regulations summarized and followed up.
12 |  |  | Assess whether there is room/need for other HELCOM measures to address emissions from shipping |  | WG Maritime | Green Team |  | New HELCOM measures to address emissions from shipping proposed, if appropriate.
Port Reception Facilities
13 |  |  | Identify further gaps in availability of PRF for other ship-generated wastes than sewage, mandatory delivery of waste and the application of the “no-special-fee” system, and propose measures to fill in these gaps | Contracting Parties | WG Maritime |  |  | PRF available for all types of ship generated wastes, passively fished waste and relevant cargo residues in all ports of the Baltic Sea, as appropriate.
Cooperation to prevent the introduction of non-indigenous species from shipping related vectors
14 |  |  | Regularly update the Baltic Sea target species list |  | JTG Ballast & Biofouling | Information on progress will be provided to WG BioDiv and WG Maritime |  | Target species list will be kept updated.
Co-operation to ensure enforcement of regulations and detection, investigation and successful conviction of offenders of anti-pollution regulations
15 |  |  | Carry out work related to the enforcement of regulations and detection, investigation and conviction of offenders related to anti-pollution regulations |  | WG Maritime | WG Response |  | Enforcement of regulations and detection, investigation and conviction of offenders related to anti-pollution regulations in place in all Contracting Parties.
Collection and analyses of the statistics on ships’ movements in the Baltic and on environmental impact of shipping/experience exchange
16 |  |  | Provide modelling data on emissions, discharges and underwater noise from ships in the Baltic Sea area | Finland | WG Maritime |  |  | Measurements on emissions, discharges and underwater noise available to support informed decision making.
17 |  |  | Provide available measurement data on emissions, discharges and underwater noise from ships in the Baltic Sea area as the primary source of data | Contracting Parties | WG Maritime | Contracting Parties |  | Up-to-date data on emissions, discharges and underwater noise available to support informed decision making.
18 |  |  | Collect and compile information on shipping accidents in the Baltic Sea | Secretariat | Contracting Parties in liaison with EMSA |  |  | Annual HELCOM report on shipping accidents approved by the Maritime Working Group.
19 |  |  | Analyse and use annual HELCOM reports on illegal discharges observed during aerial surveillance | In co-operation with WG Response | WG Maritime |  |  | HELCOM reports on illegal discharges observed during aerial surveillance are analyzed and used.
20 |  |  | Uphold, maintain and further develop the HELCOM AIS System |  | EG AIS |  |  | HELCOM AIS System in use and fit for purpose.
21 |  |  | Analyse AIS based information on shipping in the Baltic Sea | Secretariat | Contracting Parties |  |  | AIS data used for making publications and informed decision making.
22 |  |  | Regulating access to AIS information according to HELCOM Recommendation 33/1 Rev.3 | Secretariat | EG AIS national contact points |  |  | Recommendation 33/1 Rev.2 implemented.
23 |  |  | Contribute to producing thematic assessments and GES relevant indicators related to Maritime Activities to support work of WG GEAR | Secretariat | WG Maritime |  |  | Thematic assessments and indicators are produced with contribution from the Maritime Working Group.
Information to mariners
24 |  |  | Update and disseminate the revised HELCOM Baltic Sea Clean Shipping Guide | Secretariat. Sweden, Finland and EUSBSR PA Ship to support. | WG Maritime | Expert Groups to contribute as needed |  | Baltic Sea Clean Shipping Guide kept up to date.
Cooperation with other Working Groups and organisations
25 |  |  | Contribute to the implementation of the Regional Action Plan on Marine Litter (RAP ML) on those actions linked to the activity of the Group |  | WG Maritime (on shipping related actions in the RAP ML) | In coordination with WG Sea-based pressures (which has overall responsibility of the RAP ML) and EG Marine Litter. Contracting Parties |  | Relevant actions of the Regional Action Plan on Marine Litter implemented.
26 |  |  | Contribute to the implementation of the Regional Action Plan on Underwater Noise (RAP Noise) on those actions linked to the activity of the Group |  | WG Maritime (on shipping, recreational boating and offshore activities, related actions in the RAP Noise) | In coordination with WG Sea-based pressures (which has overall responsibility of the RAP Noise, supported by EG Noise) and in contact with EG Submerged in relation to action 35 of the RAP Noise |  | Relevant actions of the Regional Action Plan on Underwater Noise implemented.
27 |  |  | Exchange information about offshore activities |  | WG Maritime | WG Response |  | Up-to-date information on offshore activities available for informed decision making.
28 |  |  | Consider an assessment of pleasure craft activities in the Baltic Sea region including, i.a., environmental impacts and risks of accidents |  | WG Maritime | EBA, EBI, CCB, Contracting Parties |  | Assessment of pleasure craft activities in the Baltic Sea region developed.
29 |  |  | Consider joint proposals to IMO on clean and safe shipping in the Baltic Sea |  | WG Maritime |  |  | HELCOM Contracting Parties actively contributing to IMO work and submitting joint proposals, as appropriate, considering also relevant actions of the 2021 BSAP.
Tasks stemming from the 2021 BSAP, where S codes refer to BSAP action coding
Discharges from offshore platforms
30 | Measure | S1 | Update the Action Plan for the protection of the environment from offshore platforms to put into practice the “zero-discharge” principle in respect of all chemicals and substances used and produced during the operation of offshore platforms by 2026. (Joint) |  | WG Maritime |  |  | HELCOM Offshore Action Plan is updated to include the “zero-discharge” principle for all chemicals.
Maritime safety
31 | Suporting action | S2 | Take actions to ensure the completion of the re-surveys for Category I and II areas used by navigation by 2030 at the latest. (National) |  | WG Maritime | EG Safe Nav |  | All CAT. I and II areas have been re-surveyed, as specified in the revised resurvey scheme. (National)
32 | Suporting action | S3 | Ensure the completion of the re-surveys for near shore areas and other areas used typically for safe boating, environmental protection, GIS data purposes and oil recovery contingency (also called Category III areas), by the time specified in the revised Baltic Sea Hydrographic Commission (BSHC)-HELCOM Revised Baltic Sea Harmonized Hydrographic Re-Survey Scheme. (National) | No lead needed | EG Safe Nav | WG Maritime |  | All CAT. III areas have been re-surveyed by the time specified in the revised Baltic Sea Hydrographic Commission (BSHC)- HELCOM Revised Baltic Sea Harmonized Hydrographic Re-Survey Scheme.
33 | Suporting action | S4 | Further work with regard to the regional HELCOM Automatic Information System (AIS) and also new systems such as VHF Data Exchange System (VDES) and other e-navigation services by 2027 in order to increase safety of navigation and gain environmental benefits. (National/Joint) |  | EG AIS | WG Maritime |  | Data availability and quality on ship movements and use of such data, e.g. through making use of VDES or other e-navigation services has been improved (Joint and national)
34 | Suporting action | S5 | Further strengthen co-operation with the International Maritime Organization (IMO) and regional co-operation in the field of safety of navigation in the framework of the HELCOM Maritime Group, as appropriate, in particular recognizing the need for the exchange of technical expertise regarding risk assessment to avoid shipping accidents in the Baltic Sea. (Joint) | EG Safe Nav | EG Safe Nav | WG Maritime |  | Concrete cooperation has taken place in the field of safety of navigation between HELCOM and IMO within the framework of EG Safe Nav and Maritime Working Group, as well as cooperation on the regional level between Contracting Parties. Significant new developments can be linked to the cooperation, inter alia new traffic management measures, updated risk assessments, risk control measures and new measures to increase safety of winter navigation. Ongoing action.
35 | Suporting action | S6 | Continue close technical cooperation with the European Maritime Safety Agency (EMSA) in collection and analysis of maritime data relevant for the development of safer shipping in the Baltic Sea, such as EMCIP and explore possibilities for future cooperation on the provision of data to EMSA, including on drug/alcohol abuse as a cause of accidents as well as data on linked spills and cargo losses to the environment. (Joint) | Lead could be useful acting as a focal point within the relevant EU meetings | EG Safe Nav | WG Maritime |  | Improvements are made in the availability, collection and analysis of data on shipping accidents, their causes and their consequences, by e.g. the addition of new or more precise data points. Ongoing action.
Non-indigenous species
36 | Measure | S7 | Establish by 2024 and subsequently implement the early warning system in case of the introduction of invasive species in ports. | Lithuania | WG Maritime | JTG Ballast & Biofouling |  | By 2024 an early warning system (EWS) is established and being implemented (Joint and national).
37 | Measure | S8 | Work for the harmonized implementation of the International Maritime Organization (IMO) Biofouling Guidelines and Guidance, taking into account e.g. the proposed Biofouling Management Roadmap, and further contribute to the work carried out in the IMO. (National/Joint) | JTG Ballast & Biofouling | WG Maritime | JTG Ballast & Biofouling |  | Ongoing harmonized implementation of the IMO Biofouling Guidelines and Guidance in the Baltic Sea and ongoing active contribution of HELCOM or HELCOM Contracting Parties to the work carried out in the IMO. Implementation by HELCOM and OSPAR Contracting Parties of the IMO Biofouling Guidelines and Guidance is harmonized. Contribution to work carried out in IMO (e.g. submission of proposals developed within or based on HELCOM work, incorporation of HELCOM approaches to IMO Guidelines or Conventions etc.) has taken place. Ongoing action. (National/Joint)
38 | Suporting action | S9 | Promote the development and use of effective, environmentally sustainable biofouling management techniques and antifouling systems on ships and recreational craft, including biocide-free alternatives to prevent biofouling by supporting related research and development activities in the Baltic Sea region. (National/Joint) | JTG Ballast & Biofouling | WG Maritime | JTG Ballast & Biofouling |  | Research and development activities related to the development and use of effective, environmentally sustainable biofouling management techniques and antifouling systems, including biocide-free alternatives, are ongoing and the results are communicated with users/shippers through appropriate channels (joint and national). Ongoing action.
39 | Measure | S10 | Strengthen cooperation with stakeholders in the development and implementation of sustainable biofouling management options by 2026 to minimize the introduction of invasive aquatic species, the release of hazardous substances and microplastics from anti-fouling systems, as well as enhancing energy efficiency. (National) | JTG Ballast & Biofouling | WG Maritime | JTG Ballast & Biofouling |  | Cooperation with stakeholders in the development and implementation of sustainable biofouling management options in place, by e.g. networks and communication channels (outreach) established.
40 | Measure | HL30 | Minimize the release of biocides from antifouling products to the marine environment, and preferably by 2027 replace the use of biocidal antifouling products with biocide-free alternatives on structures, equipment and recreational craft in cases not already subject to the International Convention on the Control of Harmful Anti-fouling Systems on Ships when available and environmentally and technically feasible. (Joint) | EG Haz | WG Source to sea | WG Maritime |  | Revised or new HELCOM Recommendation on antifouling is adopted, addressing both biocidal and biocide-free practices. HELCOM Roadmap towards biocide free antifouling in the Baltic Sea region is developed.
41 | Suporting action | S11 | Implement the Joint Harmonised Procedure for the Contracting Parties of OSPAR and HELCOM on the granting of exemptions under the Ballast Water Management (BWM) Convention, Regulation A-4, and keep the Ballast Water Risk Assessment Tool up to date with data from conducted port surveys. (National/Joint) | JTG Ballast & Biofouling | WG Maritime | JTG Ballast & Biofouling |  | The JHP is Implemented among Contracting Parties. Evaluation of the sufficiency of the data from port surveys in the Ballast Water Exemptions Decision Support Tool has been carried out. Ongoing action.
42 | Suporting action | S12 | Continue close cooperation with OSPAR on the implementation of the Ballast Water Management (BWM) Convention and the issue of biofouling management at the regional and inter-regional level. (Joint) | JTG Ballast & Biofouling | WG Maritime | JTG Ballast & Biofouling |  | Progress in implementing this ongoing action can be reviewed through assessing what new recommendations, guidelines, tools, principles or publications related to the implementation of the BWM Convention or the Biofouling Guidelines have been developed between HELCOM and OSPAR through JTG Ballast & Biofouling. Ongoing action.
Recreational boating
43 | Suporting action | S13 | Promote environmentally sustainable recreational boating, including the use of best environmental practices through education and raising awareness of boat users and the personnel of marinas and guest harbours. Promote also “green” marinas and guest harbours by e.g. introducing eco-labelling of marinas and developing guidance and best practice documents by 2025 as a help for the marinas to reach criteria. (National/Joint) | Leed needed. CCB willing to support work on a "Clean Boating Guide" for recreational craft. Sweden willing to contribute and considering taking the lead of the action. | WG Maritime | JTG Ballast & Biofouling | Reference to regular task on Clean Shipping Guide | By 2025 best practices for pleasure boating, marinas and guest harbours are adopted and promoted. (Joint) Awareness raising campaigns are implemented. Increased number of eco-labelled “green” marinas and guest harbours are in place. (National)
Pollution from ships
44 | Measure | S14 | Carry out a study and impact assessment by 2025, assessing the possible ways for cargo ships to deliver sewage to port reception facilities (PRF) or take treatment measures, using onboard treatment plants, before discharging it into the sea. Based on the results, take relevant action in making a decision by 2027 on whether to widen the scope of the Baltic Sea Special Area regulations under the International Convention for the Prevention of Pollution from Ships (MARPOL) Annex IV to cover also sewage discharges from cargo ships. (Joint) | Finland | WG Maritime |  |  | By 2025 study and impact assessment has been conducted. If appropriate, by 2027 relevant action is taken to widen the scope of the MARPOL Annex IV special area regulation to cover also sewage discharges from cargo ships.
45 | Measure | S15 | Carry out a study and impact assessment by 2027, assessing the volume and potential harmful effects of grey water and the possibilities for ships to deliver it to port reception facilities or take treatment measures using onboard treatment plants, before discharging it into the sea. Based on the results, take relevant action in making a decision by 2029 on whether and how to manage grey water discharges from ships. (Joint) | Finland | WG Maritime |  |  | By 2027 a study and impact assessment are conducted. If appropriate, by 2029 relevant action is taken to regulate grey water discharges from ships in the Baltic Sea
46 | Measure | S16 | Carry out a study and impact assessment by 2026 to estimate and evaluate the volumes and impact of discharges of residues of noxious liquid substances contained in cargo tank washing waters under the International Convention for the Prevention of Pollution from Ships (MARPOL) Convention Annex II into the Baltic Sea. Based on the results, take relevant action by 2028 on whether and how to further limit discharges of residues of noxious liquid substances contained in cargo tank washing waters under MARPOL Annex II into the Baltic Sea. (Joint) | Lead needed | WG Maritime |  |  | By 2026 study and impact assessment are conducted. If appropriate by 2028, relevant action is taken to limit discharges of cargo tank washing waters containing residues of noxious liquid substances in the Baltic Sea.
47 | Measure | S17 | Study the adequacy and use of port reception facilities (PRF) for the International Convention for the Prevention of Pollution from Ships (MARPOL) Convention Annex V cargo residues by 2024 and, based on this information, ensure adequate PRFs in Baltic Sea ports for cargo residues classified as non-HME substances under MARPOL Annex V and further ensure incentives for ships to use them by 2027. (Joint) | Lead needed | WG Maritime | CP PRF |  | By 2024 a study on PRF adequacy is conducted. By 2027 adequate PRF in relevant ports are in place and being used by ships to discharge washing waters containing dry bulk cargo residues.
48 | Measure | S18 | Develop a Roadmap to minimize the discharges of food waste into the Baltic Sea and subsequently develop by 2025 a HELCOM Recommendation to encourage voluntary agreements on delivering all food waste from ships to port reception facilities. (Joint) | Finland | WG Maritime |  |  | HELCOM Recommendation to encourage voluntary agreements on delivering all food waste from ships to port reception facilities is adopted. Adoption of a Roadmap to minimize the discharges of food waste into the Baltic Sea.
49 | Measure | S19 | Enforce the requirements of the Baltic Sea Special Area under the International Convention for the Prevention of Pollution from Ships (MARPOL) Convention Annex IV and continuously ensure the availability of adequate port reception facilities in passenger ports in the Baltic Sea Area taking into account the “Technical Guidance for the handling of wastewater in Ports of the Baltic Sea Special Area under MARPOL Annex IV”. (National/Joint) | No lead needed | WG Maritime | CP PRF |  | Availability, adequacy and capacity of sewage port reception facilities (information available through annual PRF Overview) has been improved. Port State control statistics show decreased violations against the MARPOL Annex IV requirements in the Baltic Sea. Ongoing action.
50 | Measure | S20 | Ensure the no-special-fee system for marine litter applies to all passively fished waste by 2024. (National) | No lead needed | WG Maritime | CP PRF |  | The no-special fee system for marine litter applies to all passively fished waste discharged in ports normally used by fishing vessels in the Baltic Sea area by 2024.
51 | Measure | S21 | Develop and introduce best technologies, techniques and practices (BAT/BEP) to minimize nutrient losses from dry bulk fertilizer storage and handling in ports in the Baltic Sea region by 2024. (Joint) |  | WG Maritime |  |  | BAT/BEP is in place to minimize nutrient losses from dry bulk fertilizer storage and handling in relevant Baltic Sea ports by 2024.
52 | Supporting action | S22 | Develop a Roadmap by 2025 to reduce the input of pollutants from Exhaust Gas Cleaning System discharge waters, as a minimum in line with existing legislation, taking into consideration the precautionary principle and the outcome of the work of the International Maritime Organization (IMO). (Joint) | Sweden | WG Maritime |  |  | By 2025, the roadmap is developed and adopted.
53 | Supporting action | S23 | Develop a Roadmap to strengthen the implementation and enforcement of the Baltic Sea NOx Emission Control Area (NECA) by 2023 based on experience and lessons learned. (Joint) | Lead needed | WG Maritime |  |  | The Roadmap to strengthen the implementation and enforcement of the Baltic Sea NECA is adopted by 2023.
54 | Measure | S24 | Enhance the use of alternative fuels and sources of energy in shipping as well as recreational boating, as well as enhance the use of digitalization and other innovations in technology by 2027 to optimize energy efficiency in the Baltic Sea area with the view to reduce emissions of both greenhouse gases and air pollutants. (National/Joint) |  | WG Maritime | Green Team |  | Use of alternative fuels and sources of energy, as well other technological innovations are enhanced to increase energy efficiency in Baltic Sea shipping. (National) Pathway forward to achieve carbon free Baltic Sea shipping by 2100 in line with the target of IMO has been agreed. (Joint)
55 | Measure | S25 | Actively follow and contribute to the discussions at the International Maritime Organization (IMO) on greenhouse gas (GHG) emission reduction and ensure that ice navigation and its special requirements are duly taken into account. Ensure, through the work of the HELCOM Green Team, that shipping in the Baltic Sea area meets targets of the IMO GHG strategy by 2030 while at the same not impairing efforts on reducing air pollution or other environmental effects (Joint) |  | WG Maritime | Green Team |  | Baltic Sea shipping meets IMO’s greenhouse gas emission reduction targets by 2030. Contributions to the discussions at the IMO have been made (document submissions by Contracting Parties or HELCOM, or other input for consideration by relevant IMO Committees, Sub-Committees, Working Groups and Correspondence Groups) with the aim to ensuring that Baltic Sea conditions are taken into account in IMO work on reducing greenhouse gas emissions.
56 | Supporting action | S26 | Work towards securing ship financing and innovation funding to support more sustainable shipping and to ensure maritime transport components in applicable funding mechanisms. (National) | No lead needed | WG Maritime | Green Team |  | Ship financing and innovation funding for green technologies is in place in all HELCOM Contracting Parties.
57 | Measure | S27 | Enable onshore power in the Baltic Sea region by promoting onshore power supply availability and ensuring initial economic incentives for the use and supply of onshore power by 2027. (National) | No lead needed | WG Maritime | Green Team |  | Onshore power supply (OPS) is widely available in Baltic Sea Ports. Incentives are in place for ships to utilize OPS. National action.
58 | Measure | S28 | Develop and facilitate implementation of feasible and effective economic incentives to reduce pollution from ships, taking into account HELCOM Recommendation 28E/13 as amended 19 June 2019. (National) | No lead needed | WG Maritime | Green Team |  | Increased number of feasible and effective economic incentives to reduce pollution from ships is in place in the Contracting Parties. Ongoing action.
59 | Supporting action | S29 | Continue the dialogue established by the Baltic Sea Platform for Green Technology and Alternative fuels in shipping (HELCOM Green Team) and work jointly in co-operation with other regional governmental and non-governmental organizations, the industry and research community, to further promote development and use of green technologies and alternative fuels, in order to reduce harmful exhaust gas emissions and to strive for clean and low-carbon shipping. (Joint) | Green Team | WG Maritime | Green Team |  | An active dialogue between HELCOM and its Contracting Parties, other regional governmental and non-governmental organizations, the industry and research community is in place with regard to promoting the development and use of green technologies and alternative fuels. Ongoing action.
60 | Supporting action | S31 | Conduct a feasibility study by 2022 for, and as appropriate, undertake a risk analysis for oil and hazardous and noxious substances (HNS) pollution of the marine environment in the Baltic Sea area by 2025. (Joint) |  | WG Response | EG Shore, WG Maritime |  | Updated risk analysis for oil and HNS pollution in the Baltic Sea has been conducted.
61 | Measure | HL29 | Limit the use of firefighting foam containing per- and polyfluoroalkyl substances (PFAS) at sea and in the catchment area and promote sustainable alternatives by 2027. (Joint) | EG Haz | WG Source to sea | WG Maritime |  | HELCOM Recommendation limiting the use of PFAS in firefighting foams at sea. HELCOM Recommendation limiting the use of PFAS in firefighting foams in catchment area. Regional report on sustainable fluorine free alternatives to PFAS in firefighting foams. HELCOM proposal to IMO to limit the use of firefighting foam containing PFAS at ships.; Communication with ECHA to facilitate the development of related restrictions at the EU level.
Underwater noise
62 | Measure | S55 | Identify at the latest by 2025, as well as regularly update every two years, mitigation measures according to Best Environmental Practice and Best Available Technique for continuous underwater noise in the Baltic Sea and implement thereafter in line with recommendations and regulations of the international Maritime Organization (IMO). (Joint) | Lead Germany – close cooperation with EG Noise and WG Sea-based pressures | WG Maritime | WG Sea-based pressures, EG Noise |  | BAT and BET are identified and implemented at the latest by 2025.
63 | Supporting action | S56 | Actively support and contribute to the ongoing discussions on underwater noise at the International Maritime Organization (IMO) by, amongst other things, working towards regionally coordinated implementation of actions by 2028. (Joint) | Lead needed. Could be several lead countries for various elements of implementation – Close cooperation with EG Noise and WG Sea-based pressures | WG Maritime | EG Noise, WG Sea-based pressures |  | Connected action n. 30 in the Regional Action Plan on Underwater Noise is implemented.
64 | Measure/ Supporting action | S57 | Start working as soon as possible towards regionally coordinated actions on underwater noise, aiming in the long term towards addressing adverse effects of underwater noise on marine species identified as sensitive to noise, whilst safeguarding the potential of the Baltic Sea for sustainable human activities by: a) Supporting a swift implementation of the Regional Action Plan on Underwater Noise b) Initiating and supporting pilot projects to study efficacy of vessel slow down, rerouting and other operational measures, on noise emissions and responses of target species by the end of 2026. Results are to be communicated to the International Maritime Organization (IMO) for follow-up and further action. c) By 2027 Mapping the contribution of recreational craft to the noise in the marine environment; supporting studies on efficiency of mitigation measures, such as speed limitations and time-area restrictions; and studies on impact from echo sounders and fish-finders. Based on available evidence and new results, developing guidelines for implementing regulation to reduce impact on sensitive species. Simultaneously, establishing a discussion with the industry and relevant international standardization bodies and aiming at developing industry or/and application standards for underwater noise emissions of engines with respect to recreational craft, echo-sounders and fish finders, which can be utilized in national regulation of activities in marine protected areas (MPAs) and other noise sensitive areas in the Baltic Sea. (National/Joint) | Denmark to take partial lead of S57 part b). Finland to lead part c) of the action and CCB to support. | WG Maritime | WG Sea-based pressures and EG Noise |  | Implementation of the Regional Action Plan on Underwater Noise. (Joint and national) In the Baltic Sea region, at least one pilot project has been initiated by the end of 2026 to study efficacy of vessel slow down, rerouting and other operational measures, on noise emissions and responses of target species. Results of such studies have been communicated to the IMO. (Joint measure) Information on the contribution of recreational craft (including the use of echo sounders and fish finders) to underwater noise in the marine environment is available. Discussions with the industry and relevant standardization bodies have been established, aiming at developing industry and/or application standards for underwater noise emissions of engines with respect to recreational craft, echosounders and fish finders, which can be utilized for national regulation of activities in marine protected areas (MPAs) and other noise sensitive areas in the Baltic Sea.
Other tasks
65 |  |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group |  | WG Maritime |  |  | A plan is developed for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group.
66 |  |  | Evaluation and reporting on implementation of BSAP actions under the responsibility of the working group |  | WG Maritime |  |  | Updated workplan for 2027-2028. Identification of barriers to implementation as well as possible synergies or areas of cooperation with other working groups.