## Sheet 1
Approved in March 2025 via correspondence by the Helsinki Commission
No | Type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
Regular tasks for the Working Group
Topic: Maintain and further develop the standing operational network for trans-national response in case of incidents
1 |  |  | Keep HELCOM Response Manual and the Multi-regional Marine HNS Response Manual up-to-date | Contracting Parties/Secretariat Intersessional work | WG Response |  |  | Continuously Scrutiny at at meetings of WG Response | Up-to-date response manuals
2 |  |  | Updating the HELCOM Response Exercise Plan (HREP) and the Practical Guide for Response Exercises annually | HEDMOT | WG Response |  |  | Annually, based on exercise needs and experiences from previous BALEX exercises. Considered at meetings of WG Response | Up-to-date HREP
3 |  |  | Carry out operational and other kinds of exercises in order to train the topics included in the HELCOM Response Exercise Plan (HREP) | Lead Countries/Contracting Parties BALEX 2025: Lead Country Poland HEDMOT to inform about the applicability of the evaluation framework developed for shore exercises Other HELCOM and sub-regional exercises On shore response, OWR and aerial surveillance exercises, which can be combined with other exercises, as appropriate. | WG Response |  |  | Annual activities HEDMOT of BALEX 2025 Meetings of WG Response | Annual BALEX and other exercises carried out in accordance with the HREP and HELCOM Response Manual
4 |  |  | Exchage information on new knowledge on dispersants | Contracting Parties | WG Response |  |  | Continuously | New knowledge on the possibility of dispersants as a method in the Baltic Sea region.
Topic: Implement a three-tier approach to ensure adequate response to incidents in the Baltic Sea Area, with a special focus on the second tier (sub-regional level)
5 |  |  | Exchange information on maritime risks | Contracting Parties | WG Response | WG Maritime (EG Safe Nav) |  | Continuously Further discussion at meetings of WG Response | Information on maritime risks available.
6 |  |  | Conclude/implement sub-regional agreements | Contracting Parties | WG Response |  |  | Continuously | Sub-regional agreements in place in order to ensure coordinated response operations and assistance.
7 |  |  | Co-operate by conducting trainings and organizing exchange programmes to ensure swift and adequate response capacity to shoreline pollution and to exchange best practices | Contracting Parties Intersessional work | WG Response | (delegated to) EG Shore |  | Continuously | Swift and adequate response capacity to shoreline pollution in place.
8 |  |  | Exchange of information on development of national OWR plans, authority-NGO cooperation, national trainings and exercises Develop OWR protocols and facilities Develop OWR preparedness and response Ensure wide participation | Contracting Parties | WG Response | (delegated to)EG Wildlife |  | EG Wildlife reports to WG Response | OWR integrated into existing contingency plans and applied among HELCOM Contracting Parties.
9 |  |  | Review the RESPONSE related HELCOM recommendations | Contracting Parties | WG Response, WG Response Expert Groups Intersessional work | (delegated to) EG Shore; EG Surveillance; EG Wildlife In consultation with WG Maritime |  | Intersessional discussion Further discussion at next meetings | Up-to-date and relevant HELCOM Recommendations in place.
Topic: Enhance co-operation with regard to places of refuge according to HELCOM Recommendation 31E/5
10 |  |  | Make the Mutual Plan for Places of Refuge operational and implemented within/through sub-regional agreements | Contracting Parties | WG Response | [(delegated to) EG PoR] |  | Continuously Reports to WG Response and WG Maritime | Mutual Plan for Places of Refuge operational and implemented
11 |  |  | Ratify the relevant compensation and liability conventions according to HELCOM Recommendation 31E/5 | Contracting Parties | WG Response |  |  | Reports to WG Response and WG Maritime Secretariat to provide update of the ratification status of relevant conventions at each WG Response meeting | All Contracting Parties have ratified relevant international compensation and liability conventions.
Topic: Detection, investigation and prosecution of violations to anti-pollution regulations
12 |  |  | Co-ordinate aerial surveillance flights and harmonize aerial surveillance with satellite surveillance | Contracting Parties | EG Surveillance | In co-operation with EMSA (CleanSeaNet) |  | Meetings of EG Surveillance and WG Response | Coordinated aerial surveillance flights, harmonized with satellite surveillance.
13 |  |  | Identify operational needs for satellite surveillance in each sub-region of the Baltic | EG Surveillance | WG Response |  |  | Continuously | Fit for purpose satellite surveillance requests from HELCOM Contracting Parties to EMSA.
14 |  |  | Supervise CEPCO and other flights | Lead Countries/Contracting Parties | EG Surveillance |  |  | Annual activities to be discussed and coordinated during meetings of EG Surveillance and WG Response | CEPCOs organized in accordance with the HELCOM Response Manual.
15 |  |  | Harmonize aerial surveillance reporting systems with Bonn Agreement area | Contracting Parties | EG Surveillance |  |  | Continuously | Harmonized aerial surveillance reporting systems with Bonn Agreement area
16 |  |  | Supervise the use of SeaTrack Web/AIS/SAT for improved identification of possible polluters | Contracting Parties | WG Response in cooperation with EMSA |  |  | Continuously | Seatrack Web/AIS/SAT maintained and used by Contracting Parties for identification of possible polluters.
17 |  |  | Co-operate/assist and exchange experience in pollution investigations | Contracting Parties | WG Response |  |  | Continuously | Contracting Parties co-operate, provide assistance and exchange of experiences in pollution investigations.
18 |  |  | Co-operate with the Network of the Prosecutors on Environmental Crime (ENPRO) | Contracting Parties/Secretariat | WG Response |  |  | Continuously | Co-operation ongoing with the ENPRO with regard to prosecution and sanctions to deter pollution.
Topic: Carry out information exchange about offshore activities to be able to respond to accidental spills from such installations
19 |  |  | Report on ongoing/planned offshore activities (exploration/exploitation) | Contracting Parties | WG Response |  |  | Information to be submitted to WG Response meetings, when applicable | Information regarding ongoing/planned offshore activities available to all Contracting Parties in a timely manner.
Topic: Collect information/exchange experience/promote development and use of new technology and best practices
20 |  |  | Collect and publish information on shipping accidents and response operations in the Baltic Sea and their impact on marine environment | Secretariat/ Contracting Parties | WG Maritime | WG Response | Data flows from EMSA's EMCIP | Annually | Annual report on shipping accidents in the Baltic Sea published.
21 |  |  | Developing response related indicators |  | WG Response | (delegated to) EG Surveillance; Secretariat |  | Meetings of WG Response | Up-to-date response related indicators developed and approved.
22 |  |  | National and sub-regional reports on response operations and lessons learned to be submitted by Contracting Parties | Contracting Parties | WG Response |  |  | Meetings of WG Response | National and sub-regional reports on response operations and lessons learned provided.
23 |  |  | Collect, compile and publish regional summaries of response operations and lessons learned | Secretariat/ Contracting Parties | WG Response |  |  | Meetings of WG Response | Compiled information on response operations included in annual reports on shipping accidents in the Baltic Sea.
24 |  |  | Collect information on observed oil discharges, other substances and unknown substances and related statistics | Secretariat/ Contracting Parties | EG Surveillance |  |  | Meetings of EG Surveillance and WG Response | Annual report on discharges observed during aerial surveillance published.
25 |  |  | Update HELCOM Map and Data Service (MADS) with RESPONSE related information | Secretariat/ Contracting Parties | WG Response |  |  | Meetings of WG Response | Up-to-date RESPONSE related information in MADS.
26 |  |  | Update of national equipment list in CECIS MP database | Contracting Parties | WG Response |  |  | Secretariat to request Contracting Parties to review information annually | Up-to-date national response equipment list available on the HELCOM website.
27 |  |  | Exchange information with other regional agreements | Chair/Secretariat | WG Response |  |  | Annual meetings between regional agreements, EMSA and DG ECHO | Ongoing cooperation and information sharing between HELCOM, other regional agreements and EMSA.
28 |  |  | Support the use and development of technology to respond to accidents at night, in bad visibility, in bad weather, oil on ice, accidents involving all oil and chemical types. | Contracting Parties | WG Response |  |  | Meetings of WG Response | Fit for purpose technologies to respond to accidents at night, in bad visibility, in bad weather, oil on ice, accidents involving all oil and chemical types available in Contracting Parties.
29 |  |  | Participate in and share information of research on non-traditional oils and fuel types | Contracting Parties | WG Response |  |  | Continuously Meetings of WG Response | Latest information available to facilitate improvement of response capabilities.
Tasks steaming from the 2021 BSAP, where S codes refer to BSAP action coding
30 |  | S30 | Further develop regional preparedness and response related services by e.g. investigating options for upgrading SeaTrack Web to include live data feed in order to improve oil spill trajectory prognoses no later than by 2027. Investigate options to prepare SeaTrack Web for integration with the Clean Sea Net satellite detection service. | Sweden (SMHI) | WG Response |  |  | An understanding with EMSA will be needed regarding integration of SeaTrackWeb and CleanSeaNet. | Operational version of SeaTrack Web supporting live feed of current data is in place. Options are available for integrating SeaTrackWeb to CleanSea Net satellite detection service.
31 |  | S31 | Conduct a feasibility study by 2022 for, and as appropriate, undertake a risk analysis for oil and hazardous and noxious substances (HNS) pollution of the marine environment in the Baltic Sea area by 2025. |  | WG Response | WG Maritime, tasks also delegated to EG Shore |  | Long term risk analysis project to commence in early 2025, subject to funding. | Updated risk analysis for oil and HNS pollution in the Baltic Sea has been conducted.
32 |  | S32 | Develop a framework for holistic/integrated management of marine pollution incidents to enable coordinated response operation at sea and on shore by 2025. |  | WG Response | (delegated to) EG Shore, EG Wildlife, EG Surveillance | On the national level, the national competent response authorities should coordinate implementation. | Input from IRA-MAR project to be taken into account by the Response Working Group. Information sharing and coordination on the national level to ensure that national shore response plans and wildlife response are implemented and coordinated. An informal meeting between the Chairs of WG Response, EG Wildlife, EG Shore and EG Surveillance to be organized at the latest in 2025 to plan and coordinate implementation. Information sharing to ensure that national OWR plans are implemented by all relevant actors. Denmark to share experiences with the Response Working Group and other relevant groups. EG Surveillance to draft a new sub-chapter to the HELCOM Response Manual or the Practical Guide for HELCOM Response Exercise Projects to integrate aerial surveillance in the planning of BALEX exercises. | Amendments have been made in the HELCOM Response Manual with improved integration of holistic management of pollution incidents at sea, on shore and cross-sectoral cooperation between sea and shore.
33 |  | S33 | Strengthen mutual assistance for oiled wildlife response in the Baltic Region by 2025. |  | EG Wildlife | WG Response, HEDMOT (HREP), tasks also delegated to EG Shore |  | EG Wildlife to familiarize with EUROWA 2 deliverables. Contracting Parties to consider how to integrate EUROWA at national level and report via the Self-Assessment Tool. Work towards ensuring that mutual assistance is structurally implemented and exercised at regional level. Oiled wildlife response to be included in BALEX exercises. | Adoption and integration of the EUROWA framework at regional and national levels, as appropriate. (Joint and national) Regional implementation of mutual assistance mechanisms, standards and procedures, as described in Chapter 7 of the HELCOM Response Manual. (Joint) Oiled wildlife response is fully integrated into the national and regional response framework. (Joint and national) A multi-year exercise agenda has been set for different exercise categories (Alpha, Bravo, Charlie, Delta), and rotation between Contracting Parties to organise, where possible integrated with oil spill exercises. (Joint)
34 |  | S36 | Implement the Multi-Regional Marine HNS Response Manual in operational response to spills involving hazardous and noxious substances as well as exercises by 2025. |  | WG Response |  |  | Reports from implementing the Multi-Regional HNS Response Manual at BALEX 2024 and 2025 exercises to be considered by meetings of the Response Working Group in 2025, and 2026 if needed.. | The Joint Multi-Regional Marine HNS Response Manual is implemented by all HELCOM Contracting Parties as a replacement to Volume 2 of the HELCOM Response Manual (National and joint).
35 |  | S38 | Undertake monitoring and pollution risk assessment regarding species and habitats in the Baltic Region by 2026. |  | WG Response | WG BioDiv; WG GEAR; EG Wildlife, EG BirdMove; EG MaMa; JWG BIRD | Implementigng this action will require cooperation among WG Response and contributing bodies. The role of WG Response in leading the action is to express the type of input needed from other subsidiary bodies, mainly related to existing monitoring programmes and other interlinked activities, and then to process the material received into the output. | Arrange a planning meeting between Chairs of WG bioDiv and EG Wildlife with the aim to plan the work. Long-term risk analysis project to contribute. Action to be interpreted jointly between groups, to come up with a cross-topical plan for how to address this action, what is already available and where further HELCOM work can add value. The third criteria for achievement (output) should be jointly considered by response and biodiversity experts. Relevant WGs and EG to track progress and identify barriers/challenges to implementation. To report progress/barriers to WG GEAR. | An analysis of data stemming from existing monitoring to determine vulnerable species, vulnerable areas, vulnerable times of the year is conducted. Results are presented in a format which fulfils the needs of an operational manager, e.g. seasonal maps with risk indications, scale indications. etc. A risk analysis as to how response activities could also impact certain species and habitats in areas, seasons, or certain circumstances is conducted.