## WG Sea-based pressures
Approved in March 2025 via correspondence by the Helsinki Commission
No | Type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Output [for BSAP actions this will be criteria for achievement, including the deadline]
General/recurring tasks
1 |  |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group |  | WG Sea-based pressures |  |  | Plan on how to address the implementation, reporting and revision of the Recommendations by the end of 2026
Marine litter
2 |  |  | Coordinate the implementation of the HELCOM Regional Action Plan on Marine Litter | EG Marine Litter | WG Sea-based pressures |  | The actions in the Action Plan have individual leads, implementation plans and follow-up | Organization of annual sessions
Tasks stemming from the 2021 BSAP, where HL codes refer to BSAP action coding
3 | Supporting action | HL31 | Improve the evidence base on the impact of marine litter on the Baltic Sea region in order to develop and agree on new measures by 2025. (Joint) | Lead needed | WG Sea-based pressures | EG Marine litter |  | The evidence base has been improved by addressing identified knowledge gaps and the information has been published by 2025.
4 | Supporting action | HL32 | Agree on core indicators and harmonised monitoring methods to evaluate quantities, composition, distribution and sources (including riverine input), of marine litter, including microlitter, by 2022, where applicable and for the rest no later than 2026. Work should be done in close coordination with work undertaken by Contracting Parties in other relevant fora, such as the Technical Group on marine litter under the Marine Strategy Framework Directive. (Joint) | Lead needed | WG Sea-based pressures | EG Marine litter |  | Fully developed core indicators are available by 2026. Harmonised monitoring methods are agreed through the development and approval of regional monitoring guidelines by 2026.
5 | Measure | E23 | Strengthen the HELCOM Recommendation 28E/5 on municipal wastewater treatment by 2027.(Joint) | Co-lead: Germany | WG Source to sea (nutrients, hazardous substances), WG Sea-based pressures (litter) |  |  | Revised or new Recommendation with stricter requirements is adopted.
Underwater noise
6 |  |  | Coordinate the implementation of the HELCOM Regional Action Plan on Underwater Noise | EG Noise | WG Sea-based pressures |  | The actions in the action plan have individual leads, implementation plans and follow-up | Organization of annual informal consultation sessions
Tasks stemming from the 2021 BSAP, where S codes refer to BSAP action coding
7 | Measure/Supporting action | B8 | By 2022 at the latest, specify knowledge gaps on all threats to the Baltic Proper harbour porpoise population, and by 2023 for the western Baltic population, including by-catch and areas of high by-catch risk, underwater noise, contaminants and prey depletion. Knowledge gaps related to areas of high by-catch risk are to be addressed and by 2028 at the latest additional areas of high by-catch risk for both Baltic Sea populations are to be determined. To strengthen the Baltic harbour porpoise population, by 2025 identify possible mitigation measures for threats other than by-catch and implement such measures as they become available. (National/Joint) | Poland, [WWF] [Sweden] | WG BioDiv | EG MaMa, EG Noise, EG Haz (biological effects), WG Fish, WG Sea-based pressures | S43 (WG Fish), S44 (WG Fish), S45 (WG Fish), S46 (WG Fish), S47 (WG Fish), S48 (WG Fish), ASCOBANS Jastarnia Group | By 2022 knowledge gaps on all threats to the Baltic Proper harbour porpoise population have been specified and listed. (Joint supporting action)
By 2023 knowledge gaps on all threats to the western Baltic population have been specified and listed. (Joint supporting action)
By 2025 possible mitigation measures are identified and implemented as they become available. (National measure)
By 2028 knowledge gaps related to areas of high by-catch risk are addressed. (Joint supporting action).
By 2028 year, at the latest, additional areas of high by-catch risk for both Baltic Sea populations have been determined. (Joint supporting action).
8 | Measure/Supporting action | S54 | Share information among Contracting Parties, the Baltic Sea Fisheries Forum (BALTFISH) and Baltic Sea Advisory Council (BSAC) on non-lethal mitigation measures or other ways to manage seals-fisheries interactions and implement those measures by 2025, as appropriate.(National/Joint) | Lead needed | WG FISH | EG Noise, WG Sea-based pressures |  | HELCOM-BALTFISH toolbox, or other means of sharing information on non-lethal mitigation measures or ways to manage seals-fisheries interactions are in place (Joint supporting action) and such measures are being implemented, as appropriate. (National measure); Overview of actions that are suitable within the existing legal framework.
9 | Measure | S55 | Identify at the latest by 2025, as well as regularly update every two years, mitigation measures according to Best Environmental Practice and Best Available Technique for continuous underwater noise in the Baltic Sea and implement thereafter in line with recommendations and regulations of the international Maritime Organization (IMO). (Joint) | Germany | WG Maritime | WG Sea based pressures, EG Noise |  | BAT and BEP are identified and implemented at the latest by 2025.
10 | Supporting action | S56 | Actively support and contribute to the ongoing discussions on underwater noise at the International Maritime Organization (IMO) by, amongst other things, working towards regionally coordinated implementation of actions by 2028.(Joint) |  | WG Maritime | EG Noise, WG Sea-based pressures |  | Connected action n. 30 in the Regional Action Plan on Underwater Noise is implemented.
11 | Measure/Supporting action | S57 | Start working as soon as possible towards regionally coordinated actions on underwater noise, aiming in the long term towards addressing adverse effects of underwater noise on marine species identified as sensitive to noise, whilst safeguarding the potential of the Baltic Sea for sustainable human activities by: a) Supporting a swift implementation of the Regional Action Plan on Underwater Noise b) Initiating and supporting pilot projects to study efficacy of vessel slow down, rerouting and other operational measures, on noise emissions and responses of target species by the end of 2026. Results are to be communicated to the International Maritime Organization (IMO) for follow-up and further action. c) By 2027 Mapping the contribution of recreational craft to the noise in the marine environment; supporting studies on efficiency of mitigation measures, such as speed limitations and time-area restrictions; and studies on impact from echo sounders and fish-finders. Based on available evidence and new results, developing guidelines for implementing regulation to reduce impact on sensitive species. Simultaneously, establishing a discussion with the industry and relevant international standardization bodies and aiming at developing industry or/and application standards for underwater noise emissions of engines with respect to recreational craft, echo-sounders and fish finders, which can be utilized in national regulation of activities in marine protected areas (MPAs) and other noise sensitive areas in the Baltic Sea. (National/joint)) | Denmark to take partial lead of S57 part b). Finland to lead part c) of the action and CCB to support. | WG Maritime | WG Sea based pressures; EG Noise |  | Implementation of the Regional Action Plan on Underwater Noise. (Joint and national). In the Baltic Sea region, at least one pilot project has been initiated by the end of 2026 to study efficacy of vessel slow down, rerouting and other operational measures, on noise emissions and responses of target species. Results of such studies have been communicated to the IMO. (Joint measure) Information on the contribution of recreational craft (including the use of echo sounders and fish finders) to underwater noise in the marine environment is available. Discussions with the industry and relevant standardization bodies have been established, aiming at developing industry and/or application standards for underwater noise emissions of engines with respect to recreational craft, echo-sounders and fish finders, which can be utilized for national regulation of activities in marine protected areas (MPAs) and other noise sensitive areas in the Baltic Sea. (Joint supporting action)
12 | Measure/Supporting action | S58 | Study by 2026 the impacts of continuous underwater noise from the installation, operation and decommissioning of offshore windfarms on marine biota, including cumulative effects of multiple windfarms. Based on the results, take relevant action, if necessary, in developing appropriate mitigation measures for the continuous underwater noise generated by offshore wind farms by 2029. (Joint) | Lead needed, Sweden and CCB to support | WG Sea-based pressures | HELCOM-VASAB MSP WG; EG Noise; EG MaMA |  | By 2026 study on the impacts of continuous underwater noise from offshore windfarms, including cumulative effects of multiple windfarms, is conducted. If appropriate, by 2029 relevant action is taken to develop appropriate mitigation measures
13 | Measure | S59 | Reduce the impact of impulsive underwater noise on marine biodiversity. (National/Joint) |  | WG Sea-based pressures; EG Noise | HELCOM-VASAB MSP WG, WG BioDiv, EG Noise, EG MaMa |  | Regional and national mitigation measures for the activities generating impulsive noise are in place as defined in the Recommendation on the Regional Action Plan on Underwater Noise. (Joint and national)
14 | Measure | S60 | Identify at the latest by 2023, as well as regularly update every two years, mitigation measures according to Best Environmental Practice and Best Available Technique for impulsive underwater noise in the Baltic Sea and implement thereafter without delay. (Joint) | Estonia, Sweden and CCB to support | WG Sea-based pressures | EG Noise |  | BAT/BEP guidelines for impulsive noise sources are updated.
15 | Measure | S61 | Develop and implement guidelines for the design and use of acoustic deterrent devices to avoid detrimental impacts on the environment from underwater noise by 2024. (Joint) | EG Noise | WG Fish | WG Sea-based pressures, EG Mama |  | Guidelines for the design and use of acoustic deterrent devices are in place and implemented in all Contracting Parties.
16 | Supporting action | S62 | Develop and implement threshold values and assessment methods for adverse effect of impulsive and ambient noise for marine life, in cooperation with OSPAR, the EU and other relevant expert groups, by 2023 at latest for marine mammals and by 2026 for other relevant species groups. (Joint) | Lead needed, Sweden to support the second part of the action related to other relevant species groups. Estonia to support | WG Sea-based pressures | EG Noise |  | By 2023 threshold values and assessment methods for adverse effect of impulsive and ambient noise for marine mammals have been developed and implemented. By 2026 threshold values and assessment methods for adverse effect of impulsive and ambient noise for other relevant species groups have been developed and implemented.
17 | Supporting action | S63 | Implement regular and regional harmonized monitoring of ambient and impulsive noise by 2023 to follow up effects of mitigation measures.(National) |  | WG BioDiv; WG Sea-based pressures; EG Noise |  |  | Regular and regional harmonized monitoring of ambient and impulsive noise is in place.
Seabed loss and disturbance
18 |  |  | Compile data on dredging/depositing operations at sea reported at intervals specified in the Guidelines for Management of Dredged Material at Sea. Support the consolidated reporting to the London Convention and its 1996 Protocol utilizing the reported data on handling of dredged material at sea. | EG DreDS | WG Sea-based pressures |  |  | BSEFS on dredging and depositing operations at sea are published at intervals specified in the Guidelines for Management of Dredged Material at Sea, and the information is used for annual consolidated reporting to London convention/London Protocol on behalf of Contracting Parties.
Tasks steaming from the 2021 BSAP, where S, B and HT codes refer to BSAP action coding
19 | Measure | S64 | Enforce and implement by 2025, in line with the update of the marine protected area (MPA) management guidelines, effective management plans and/or conservation measures to not allow destructive and exploitative activities related to the seabed that may compromise the conservation objectives of MPAs. |  | WG Seabased Pressures | WG Fish, HELCOM-VASAB MSP, EG Dreds |  | Effective management plans, conservation rules or other equivalent systems to not allow for destructive and exploitative activities related to the seabed compromising the conservation objectives of MPAs are implemented and enforced.
20 | Measure/Supporting action | S65 | By 2026 implement a common approach to address and where possible minimize the loss of and disturbance to seabed habitats caused by human activities. (National/joint) | Lead needed | WG Sea-based pressures | EG Benthic; EG DreDS |  | A common approach to addressing loss and disturbance to seabed habitats has been developed and regionally agreed. (Joint supporting action). A common approach to addressing loss and disturbance to seabed habitats has been implemented. (National measure)
21 | Supporting action | S66 | Regularly update and improve the HELCOM Recommendation and Guideline for handling dredged material at sea using the best available knowledge to minimize environmental impact of these activities further developing Best Environmental Practice (BEP) and Best Available Technique (BAT) for dredging and depositing operations. (Joint) | EG DreDS | WG Sea-based pressures |  |  | HELCOM Recommendation and Guidelines for management of dredged material at sea are improved and maintained up to date. BAT/BEP to minimize environmental impact of dredging/depositing operations is developed.
22 | Supporting action | S67 | Define the characteristics of benthic habitats, develop core indicators and undertake an integrated assessment of […] distribution and extent of loss, no later than 2023, leading to the identification of measures to reduce adverse effects where needed. Work should be done in close cooperation with work undertaken by Contracting Parties in other relevant fora, taking into account activities in EU Technical Group on seabed habitats and sea-floor integrity (TG Seabed), and considering the ICES advice on a sea-floor assessment process. (Joint) | Indicator leads | WG BioDiv | WG Sea-based pressures, EG Benthic; EG DreDS | EU TG Seabed, ICES | By 2023 characteristics of benthic habitats have been defined.
By end of 2023 HELCOM indicators evaluating the status, structure, function and distribution of benthic habitats has been developed and operationalized.
By 2023 HELCOM indicator evaluating the extent of loss of benthic habitats has been developed and operationalized.
By end of 2023 assessment of benthic habitats has been undertaken.
By end of 2025, where needed measures to reduce adverse effects have been identified.
Relevant new measures adopted by Ministerial Meeting in 2026
23 | Measure/Supporting action | B26 | Protect key ecosystem components including habitat forming species by 2030, by: - assessing the state of, and threats to these key ecosystem components by 2023 - implement effective and relevant threat mitigation measures based on the threat and state assessments, including restricting human activities associated with causing physical loss or disturbance, by 2030 - identifying suitable measures and types of habitats, biotopes and key ecosystem components for passive or active restoration by 2025 and implementing programmes for restoration as outlined in the HELCOM Restoration Action plan by 2030. (National/Joint) |  | WG BioDiv; WG Sea-based pressures (on mitigation measures) | WG Sea-based pressures |  | By 2023 currently prioritized conservation features have been complemented with a list of key representative ecosystem components identified based on function for the ecosystem/provisioning of ecosystem services. (Joint supporting action).
By 2023 an assessment, is ready and publicly available. (Joint supporting action)
By 2030 effective measures are in place to mitigate threats and pressures, to improve the status of the identified key ecosystem components. (National measure)
By 2025 suitable areas for restoration of the key system components, including habitat forming species, have been identified. (Joint supporting action)
Munitions, wrecks and hazardous submerged objects
24 | Supporting action | S34 | Develop Best Environmental Practice (BEP) for comprehensive risk assessment of munitions, wrecks and hazardous submerged objects by 2025 and implement the Best Available Techniques (BAT) for environmentally sound and safe management by 2028. (Joint) | Germany is considering the possibility of being a lead for the implementation of this action. Poland is willing to support the implementation of this action but further national consultations are needed | EG Submerged | WG Sea-based pressures |  | By 2025 BEP/BAT and control of threats posed by munitions, wrecks and other hazardous submerged objects in the Baltic Sea are in place
By 2028 are being implemented for environmentally sound and safe management.
25 | Supporting action | S35 | Maintain the HELCOM thematic assessment on hazardous submerged objects as a living document, including munitions and wrecks and regularly update the information in the HELCOM Map and Data Service by 2024. (Joint) | Sweden has taken the lead on the wrecks part of the Submerged Assessment | EG Submerged | WG Sea-based pressures |  | Up to date HELCOM Submerged Assessment is published. Updated information in the HELCOM Map and Data Service is published.
Hot spots
26 | Measure/Supporting action | HT24 | Consider designating HELCOM hot spots by 2025 on the basis of identified additional sources of major negative impact on the Baltic marine ecosystem, starting with the development of specifying criteria for the designation and deletion of the hot spots by 2023, and based on those criteria, initiate and undertake targeted measures with the aim of eliminating where possible such new hot spots. (National/joint) | Germany | WG Source to sea | WG Sea-based pressures |  | HELCOM criteria for designation and deletion of hot spots is established by 2023. (Joint supporting action). New hot spots are designated by 2025. (Joint/National supporting action) Targeted measures are initiated to eliminate, where possible, the newly designated hot spots. (National measure)
27 | Measure | HT26 | Enhance cooperation with non-HELCOM countries in removing existing hot spots and designate new hot spots applying HELCOM criteria and facilitate undertaking all possible measures to eliminate them. (Joint) |  | WG Source to sea | WG Sea-based pressures |  | Elimination of the remaining hot spots in non-HELCOM countries identified by the Baltic Sea Joint Comprehensive Environmental Action Programme. Designation of new hot spots in non-HELCOM countries and their possible deletion from the hot spot list.
Monitoring
28 | Supporting action | HT6 | Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements.(Joint) | CP leads as identified under WG GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDiv; WG Source to sea; WG Sea-based pressures; EG Haz; EG Eutro; EG MaMa; EG Marine Litter; EG Noise; EG Phyto; EG Zoo; JWG Bird |  | Updated monitoring programmes are available every six years in line with what is specified in the action.
29 |  |  | Contribute to and guide the development of sea-based pressures related regional monitoring guidelines. | Lead needed | WG Sea-based pressures |  |  | Up to date monitoring guidelines in place.
30 |  |  | Establish persistent regular data flows and data management for all sea based pressures data needed for HELCOM assessment and tracking purposes. | Lead needed | WG Sea-based pressures |  |  | Lower resource requirements long term due to automatised data reporting. Improved access to data and information across the region. Enabling automatising assessment procedure.
Indicators
31 | Supporting action | B33 | By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). (Joint) |  | WG GEAR | WG BioDiv; WG Source to sea; WG Sea-based pressures |  | By 2024 a Roadmap for how to fill gaps for both ecosystem components and pressures is developed.
By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available
Climate change
32 | Supporting action | HT1 | Using the HELCOM/Baltic Earth Joint Expert Network on Climate Change as a platform and through committed implementation of the HELCOM Science Agenda, improve the access of policy-makers to scientific information on the impacts of climate change together with multiple other pressures on the Baltic Sea marine environment through periodic updates of the HELCOM Climate Change Fact Sheet, and incorporate the possible effect of climate change into the holistic assessment of status as well as effectiveness of measures by 2030 at latest. | EN Clime | WG GEAR | WG BioDiv, WG Source to sea, WG Sea-based pressures, WG Fish, EG MaMa, EG Benthic, EG Phyto, EG Zoo, JWG Bird, [EG Coastal Fish] |  | The HELCOM Climate Change Fact Sheet is periodically updated.
Possible effect of climate change have been incorporated into the holistic assessment of status of the Baltic Sea environment
Possible effect of climate change have been incorporated into the assessment of effectiveness of measures.
Other tasks
33 |  |  | Evaluation and reporting on implementation of BSAP actions under the responsibility of the working group. |  | WG Sea-based pressures |  |  | Updated workplan for 20257-20268. Identification of barriers to implementation as well as possible synergies or areas of cooperation with other working groups.