## WG Source to sea
Approved in March 2025 via correspondence by the Helsinki Commission
No | Type of action | BSAP action | Task [BSAP action, support to BSAP action lead by another group or other task from ToR] | Lead | Responsible body | Contributing | Interlinked activities | Next steps and comments [including the timeframe] | Output [for BSAP actions this will be criteria for achievement, including the deadline]
General/recurring tasks
1 |  |  | Plan for the implementation, reporting and possible revision of HELCOM Recommendations of relevance for the group | Co-lead: The relevant expert groups under WG Source to sea | WG Source to sea |  | BSAP action HL4 led by Finland | Set the schedule for reporting on Recommendations that have not yet been reported on | Plan on how to address the implementation, reporting and revision of the Recommendations by the end of 2025
Agriculture
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
2 | Measure | E8 | E8 – Develop by 2025 and apply by 2027 the best practices to improve soil structure and aggregate stability on clay soils to reduce phosphorus losses from agricultural lands, for example by using soil structure lime or gypsum. (National/joint) | Drafting group | WG Source to sea |  |  | Finalize the regional document for approval in spring 2025 | By 2025 best practices to improve soil structure and aggregate stability on clay soils to reduce phosphorus losses from agricultural lands are compiled in a regional document. (Joint). By 2027 the best practices are applied nationally in areas where the measures are applicable e.g. with the help of support schemes, regulation or guidelines. (National)
3 | Supporting action | E11 | E11 - Improve knowledge exchange by establishing dialogue between farmers, authorities and decision makers. (National/joint) | CCB supported by Vice-Chair and Secretariat | WG Source to sea |  | EUSBRS PA Nutri and PA Bioeconomy, WWF Baltic Farmer of the Year Award |  | Regular Baltic Sea regional forum to exchange knowledge between farmers, authorities and decision makers is organized. (Joint). Ways or means for regular exchange of knowledge nationally are ensured. (National)
4 | Measure | E13 | E13 - Develop by 2025 recommendations for Best Available Technology (BAT)/Best Environmental Practice (BEP) to reduce ammonia and greenhouse gas emissions from livestock housing, manure storage and spreading. (Joint) | Regional project or drafting group | WG Source to sea |  | Actions E13-E14 are closely connected and are also linked to action E20, to follow the EU Industrial Emissions Directive revision | Recommendation to be adopted in spring 2025 | Regional document on BAT/BEP to reduce ammonia and greenhouse gas emissions from livestock housing, manure storage and spreading is developed.
5 | Measure | E14 | E14 - Develop by 2025 recommendations for manure management specifically for horses, sheep, goats, and fur farming. (Joint) | Regional project or drafting group | WG Source to sea |  | Actions E13-E14 are closely connected and are also linked to action E20 | Recommendation to be adopted in spring 2025 | Regional document such as Recommendation or guideline for manure management specifically for horses, sheep, goats, and fur farming is developed.
Pollution Load Compilations (PLCs)
6 |  |  | Annual compilation of airborne inputs of hazardous substances to the Baltic Sea | PLC-9 project, separate contract with EMEP | WG Source to sea | EG RedCore | Task 8 on developing input estimates | PLC-9 project to produce annual report and Baltic Sea Environment Fact Sheet. Consider inclusion of new and/or rotation of already covered substances in accordance with the HELCOM priorities and data availability. | Baltic Sea Environment Fact Sheet (BSEFS) on selected inputs of hazardous substances are published annually.
7 |  |  | Regular update of the HELCOM information resources to collect, store and provide access to the data on input of nutrients and selected hazardous substances into the Baltic Sea including reporting web applications and relevant HELCOM GIS map services. | BNI (Database Host) | EG RedCore | PLC Data Manager; Secretariat |  |  | Continuous with annual update checks with the PLC-9 project Implementation Group
8 |  |  | Develop the estimation of inputs and source apportionment for HELCOM priority hazardous substances | EG Haz | WG Source to sea | PLC-9 project | Task 6 on annual airborne inputs of hazardous substances | EG Haz to analyse in spring 2025 the information on sources and pathways available for the priority substances and seek funding for a project | Improved assessment of inputs of hazardous substances in PLC-9 project
9 |  |  | Thematic report assessing the sources of nutrient input to the Baltic Sea based on 2025 data | PLC-9 project | WG Source to sea | EG RedCore |  | Part of the PLC-9 project plan with timetable | Thematic report is published as BSEP
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
10 | Supporting action | E2 | E2 - Assess progress towards maximum aIlowable inputs annually and national input ceilings every second year, to follow up implementation of regional and national targets for inputs of nutrients. (Joint) | PLC-9 project | WG Source to sea | EG RedCore; BNI |  | PLC-9 project to produce the assessments. Annual assessment: progress towards MAI by December 2025 and 2026. Biannual assessment: Progress towards NIC by December 2026. | Annual core indicator on progress toward MAI including assessment data is published. Policy message on progress towards NIC including technical annexes and assessment data is published every second year.
11 | Supporting action | E3 | E3 - Provide timely sufficient and consistent data on nutrient loads to the Baltic Sea, ensuring reliability of the follow-up system, by maintaining and enhancing monitoring programmes and networks striving for harmonized methods to estimate nutrient inputs, including from unmonitored areas. (National/joint) | Lead: PLC-9 project | WG Source to sea | EG RedCore, EMEP MSC-W, BNI, PLC data manager |  | Countries to submit the annual data according to the schedule set in the PLC-Water Guidelines. EMEP MSC-W to provide the data on airborne deposition of nitrogen on the Baltic Sea sub-basins and provide the draft BSEFS for approval by WG Source to sea. The PLC-8 project to draft the annual waterborne BSEFS and WG Source to sea to approve. | The PLC database is updated annually. (National/joint). Baltic Sea Environmental Fact Sheet (BSEFS) on waterborne nutrient inputs and annual BSEFS on atmospheric nitrogen inputs are published annually. (Joint)
12 | Measure | E4 | E4 – Strengthen cooperation with river basin management authorities of non-HELCOM countries through official agreements addressing transboundary waterborne nutrient inputs from non-Contracting Parties. (National/joint) | Lead: needed | WG Source to sea |  |  | Invite river basin management authorities in spring 2025 Source-to-sea workshop. Challenges in planning implementation due to political situation | Agreements addressing transboundary waterborne nutrient inputs from non-Contracting Parties are adopted. (National). Common workshops/expert meetings are arranged and all levels of river management are included in this cooperation (National/joint)
13 | Supporting action | E22 | Enhance HELCOM cooperation with the UNECE Convention for Long-Range Transboundary Air Pollution in order to promote the inclusion of the protection of the Baltic Sea ecosystem as an additional criterion in the process of the revision of the emission targets for nitrogen in the Gothenburg Protocol. | EG RedCore, Germany | WG Source to sea |  |  |  | A memorandum of understanding as well as procedures to exchange technical expertise between HELCOM and UNECE CLRTAP have been set. (Joint, as far as applicable)
Wastewater treatment
14 |  |  | Review and possible revision of HELCOM Recommendation 38/1 | Lead: needed | WG Source to sea |  |  | Review to begin after the EU Sewage Sludge Directive update process is completed. Consider the reporting format with the possible revision process of the Recommendation 38/1. | HELCOM Recommendation 38/1 reviewed, and if deemed necessary, revised.
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
15 | Measure | E23 | E23 – Strengthen the HELCOM Recommendation 28E/5 on municipal wastewater treatment by 2027. (Joint) | Co-leads: Germany | WG Source to sea (nutrients, hazardous substances), WG Sea-based pressures (litter) |  |  | Launch delayed because of the ongoing EU UWWTD revision process, that is to be taken into account. One of the most important nutrient actions to reduce also e.g. microlitter and hazardous substances but needs a lot of expertise. Ambition level to be set early in the process. | Revised or new Recommendation with stricter requirements is adopted.
16 | Supporting action | E24 | Facilitate exchange of information on best available treatment techniques for wastewater treatment plants through cooperation with existing regional digital platform(s) acting as a hub for the best knowledge in the wastewater management sector. | Secretariat, UBC | WG Source to sea | EMPEREST project |  |  | A regional digital platform acting as a hub for the best knowledge in the wastewater management sector is established and actively used in the Baltic Sea region.
17 | Supporting action | E25 | Encourage educational cooperation with involvement of relevant non-governmental organizations utilizing such regional digital platform(s) to solve problems of municipal sewage in smaller municipalities and scattered settlements. | Secretariat, UBC | WG Source to sea | EMPEREST project |  |  | New initiatives implemented in educational cooperation using digital platform(s) (National and joint).
18 | Supporting action | E26 | E26 – Cooperate with relevant Policy Areas of the EU Strategy for the Baltic Sea Region (EUSBSR) regarding e.g. wastewater treatment plants (under “save the sea” objective of the EUSBSR) as well as other regional policies to engage a wider network of stakeholders into cooperation to achieve the BSAP targets. (Joint) | Secretariat | WG Source to sea |  |  | Continuous work as an observer of the PA Nutri Steering Group. Continuous work with CP representatives in the PA Nutri Steering Group | HELCOM participates in the Policy Areas’ steering committees. The Policy Area coordinators participate in HELCOM meetings and outcomes of projects and processes supported by Policy Areas are considered at relevant HELCOM Working Group meetings.
19 | Supporting action | E28 | E28 – Build a knowledge base to target the reduction of phosphorus in detergents for industrial & institutional use. By 2025, develop and publish a HELCOM progress report about best available techniques, alternative builders, especially on their use, environmental effects and effectiveness. (Joint) | Lead: needed | WG Source to sea |  | revision of the Recommendation 28E/5 | Germany to contribute with BAT study. Synchronising with EU processes needed. Important to engage the industry in the studies. | HELCOM report on best available techniques (BAT), alternative builders, especially on their use, environmental effects and effectiveness to target the reduction of phosphorus in detergents for industrial & institutional use.
20 | Measure | E29 | Undertake efforts to reduce and where possible eliminate phosphorus in detergents for industrial & institutional use, in particular for institutional use of laundry and dishwater detergents no later than by 2030 based on the knowledge on best available techniques compiled during the first step. | Lead: needed | WG Source to sea |  |  |  | New HELCOM instrument (recommendation or guidelines) based on outcomes of action E28 is adopted. (Joint);All countries have introduced regulations, in line with the HELCOM Recommendation or guidelines, for laundry and dishwasher detergents for industrial and institutional use in which the phosphorus concentration has been reduced and, where possible, eliminated. (National)
Nutrient recycling
21 | Measure | (E30) | Coordinate the implementation of the Baltic Sea Regional Nutrient Recycling Strategy |  | WG Source to sea |  |  | Related BSAP actions have individual target years and criteria, but not all the sub-objectives or possible measures in the Strategy are included in the BSAP. Regular discussions at the WG Source to sea meetings to coordinate the implementation with possible workshops back-to-back with WG Source to sea meetings. | The strategy has been implemented by 2027.
Tasks stemming from the 2021 BSAP, where E codes refer to BSAP action coding
22 | Measure | E32 | E32 – Enhance the use of recycled nutrients in agriculture making use of best available technologies and fertilize according to crop needs. (National/joint) | Lead: needed | WG Source to sea | CiNURGi project | BSAP action E33 | CiNURGi project is making an evaluation of the current use of fertilizers and biomassess. Discussion needed on the how to evaluate substitution of mineral fertilizers. | Support schemes and advice are in place to enhance the use of recycled nutrients in agriculture making use of best available technologies and fertilizing according to crop needs. (National). Evaluation of substitution of mineral fertilizers by recycled nutrients is carried out. (Joint)
23 | Measure | E33 | E33 – Develop by 2027 safety requirements for recycled fertilizer products and minimise the occurrence of harmful compounds in these products to comply with the requirements. (National/joint) | Lead: needed | WG Source to sea | CiNURGi, EG Haz | LEX4BIO project, BSAP action E32 | CiNURGi project to draft the regional document. WG Source to sea to guide the work. | Regional document on the safety requirements for recycled fertilizer products is developed. (Joint). Compliance with the requirements is ensured nationally. (National)
24 | Supporting action | E36 | E36 – Enhance cooperation and share experiences between sectors and actors to create a holistic view on sustainable food systems including nutrient recycling across sectors. (National/joint) | Lead: needed | WG Source to sea | CiNURGi project |  | CiNURGi project as a platform to share experiences | Identification of sectors and organizations that should be part of the national discussion on nutrient recycling. (National). Baltic Sea regional and national conferences, webinars, visits, collaboration with researchers etc. are organized to share experiences and exchange knowledge between sectors and actors. (National and joint)
Possible point sources of nutrients
25 |  |  | Developing the monitoring and management of phosphogypsum stacks | EG RedCore | WG Source to sea |  |  | Finalizing the Recommendation for adoption and background report in spring 2025. Further investigation of possible offshore banks in the region and on reporting of phosphorus load from gypsum stacks to the PLC-9 project. | Report and new Recommendation amending the Recommendation 17/6 on phosphogypsum management
Tasks stemming from the 2021 BSAP, where HT, HL and B codes refer to BSAP action coding
Hot spots
26 | Measure/supporting action | HT24 | HT24 – Consider designating HELCOM hot spots by 2025 on the basis of identified additional sources of major negative impact on the Baltic marine ecosystem, starting with the development of specifying criteria for the designation and deletion of the hot spots by 2023, and based on those criteria, initiate and undertake targeted measures with the aim of eliminating where possible such new hot spots. (National/joint) | Germany | WG Source to sea | WG Sea-based pressures |  | tbd depending on the criteria and desingation process | HELCOM criteria for designation and deletion of hot spots is established by 2023. (Joint supporting action). New hot spots are designated by 2025. (Joint/National supporting action) Targeted measures are initiated to eliminate, where possible, the newly designated hot spots. (National measure)
27 | Measure | HT26 | HT26 – Enhance cooperation with non-HELCOM countries in removing existing hot spots and designate new hot spots applying HELCOM criteria and facilitate undertaking all possible measures to eliminate them. (Joint) | Lead: needed | WG Source to sea |  |  | Possible EUSBSR PA Nutri collaboration | Elimination of the remaining hot spots in non-HELCOM countries identified by the Baltic Sea Joint Comprehensive Environmental Action Programme. Designation of new hot spots in non-HELCOM countries and their possible deletion from the hot spot list.
Hazardous substances
28 | Supporting action | HL1 | HL1 - Develop a regional strategic approach and, on the basis of that approach, an action plan for HELCOM work on hazardous substances by 2024. (Joint) | EG Haz Strategic/holistic sub-team, Secretariat (HAPhazard project), RAP HAZ drafting group | WG Source to sea | EG Haz |  | Finalizing the regional strategic approach for adoption in spring 2025 and the action plan by spring 2026. | Regional strategic approach on hazardous substances is developed. Regional action plan on hazardous substances is adopted.
29 |  |  | Coordination of the implementation of the Regional Action Plan on Hazardous Substances | EG Haz | WG Source to sea | WG Maritime, WG Sea-based pressures, WG Response, EG Submerged |  | Support and guide the implementation of RAP HAZ | Regional Action Plan on Hazardoud Substances is implemented by the target year.
30 | Supporting action | HL4 | Strengthen and update HELCOM recommendations for industrial releases of hazardous substances by applying information produced under the EU Industrial Emissions Directive and other sources in order to sufficiently protect the Baltic Sea environment. | Finland, EG Haz | WG Source to sea |  |  | Guide the project on revision of the relevant Recommendations | New or updated HELCOM Recommendations are adopted.
31 | Measure | HL5 | Decrease the emissions of hazardous substances from small scale emitters in urban areas (municipal entities, businesses and private households) by chemical-smart purchasing strategies, substitution and awareness raising campaigns. | Lead needed | WG Source to sea | EG Haz | NonHazCity 3 project | Find resources, e.g. Project funding or country contributions and guide drafting regional guidelines based on project results. | Regional guideline on best practices for smart chemical management for small-scale emitters e.g. municipal entities, businesses and private households is published. (joint); Awareness-raising campaigns and information materials on chemical-smart procurement and purchasing strategies for preventing releases of hazardous substances is communicated with households, municipal entities and businesses. (national); If feasible, arrange a study illustrating awareness raising among citizens before and after campaigns to prove their effectiveness. (national)
32 | Measure | HL7 | HL7 - Launch educational and information campaigns by 2025 to raise public awareness regarding responsible handling of hazardous substances in household chemicals and articles to prevent their release into the environment. (National/joint) | Lead needed | WG Source to sea | EG Haz | BSAP actions HL5 and HL25 | Find resource, e.g. Project funding or country contributions and guide drafting regional guidelines based on project results. | Regional guidelines/ recommendations for general public and visual outreach material encouraging environmentally responsible selection of products and handling of chemicals in households are published. (Joint). National or local education and outreach campaigns for general public encouraging environmentally responsible selection of products and handling of chemicals in households are arranged based on the guidelines/ recommendations. (National) Reporting can be partly done jointly with action HL5 and HL25.
33 | Measure | HL8 | HL8 - Introduce requirements regarding content of chemicals of high regional environmental concern in public procurement procedures by 2025 and provide support for follow-up. (National/joint) | Sweden | WG Source to sea | EG Haz | BSAP actions HL5 and HL10 | Guide the drafting of the recommendations | Regional guidelines/ recommendations for green procurement procedures are published. (Joint). National or local guidelines/ recommendations for green procurement procedures are issued, if needed. (National) Reporting can be partly done jointly with action HL5.
34 | Supporting action | HL9 | HL9 - Establish procedures by 2025 to utilize information obtained under various policies and policy frameworks addressing the use of chemicals (e.g. Stockholm Convention, SAICM successor, REACH Regulation, Water Framework Directive, Industrial Emissions Directive etc) to prioritize measures targeting regional contaminants and to identify emerging pollutants of high concern. (Joint) | EG Haz priority substances, substances of emerging concern and screening strategic/holistic sub-team, HAPhazard project | WG Source to sea | EG Haz | BSAP action HL1 | Information available from the work on strategic approach. Next update by EG Haz experts to be submitted to EG Haz and WG Source to sea in spring 2026. | Analysis of measures implemented under other policies, including their effectiveness is conducted. Summary of international work and identified measures on contaminants of emerging concern, e.g screening campaigns, is presented every two years for Pressure Working Group and for other relevant HELCOM bodies for planning and prioritizing further the HELCOM work on hazardous substances.
35 | Supporting action | HL10 | HL10 - Establish a mechanism for managing the HELCOM list of priority substances starting from 2025 and respond to screening and assessment results pointing out regional challenges for the Baltic Sea environment and contaminants of emerging concern. (Joint) | Co-leads: Denmark, [Sweden], [Germany] EG Haz priority substances, screening and substances of emerging concern sub-team, HAPhazard project | WG Source to sea | EG Haz | BSAP action HL1 | Finalize the Recommendation for adoption in spring 2025. | A group working in collaboration with relevant other actors (e.g. global treaties, OSPAR, EU NORMAN network) aiming to further risk-based prioritisation tools for the needs of Regional Seas Conventions is formally established. A prioritisation mechanism, which is used for continuous update of the priority list based on reported data and prioritisation criteria is in place.
36 | Supporting action | HL11 | HL11 - Organize continuous follow-up of the work on hazardous substances under various global and EU policies as well as in Regional Sea Conventions (RSCs) starting from 2024, and actively influence these processes by promoting international actions identified as necessary to improve the environmental status with respect to hazardous substances in the Baltic Sea. (Joint) | EG Haz strategic/holistic sub-team, priority substances, substances of emerging concern and screening | WG Source to sea | EG Haz | BSAP action HL1 | Information available from the work on strategic approach. Next update by EG Haz experts to be submitted to EG Haz and WG Source to sea in spring 2026. | Joint HELCOM initiatives are proposed to relevant global or upstream Conventions to reduce inputs of hazardous substances to the HELCOM Convention area.
37 | Supporting action | HL13 | By 2028 develop further relevant monitoring for the biological effects of hazardous substances in order to facilitate a reliable ecosystem health assessment. | EG Haz biological effects sub-team | WG Source to sea | EG Haz |  | Draft joint guidelines from joint HELCOM-OSPAR study group available in spring 2025 and to be finalized. | Monitoring produces sufficient data to enable a reliable ecosystem health assessment by integration of multiple components, considering already existing candidate and pre-core indicators of biological effects of hazardous substances.
38 | Measure | HL14 | Encourage the use of alternative less toxic metals and other materials to replace lead in fishing gear and shooting bullets with the aim to minimize harmful use of metallic lead. | Denmark | WG Source to sea | EG Haz |  | Guide the drafting of the regional guidelines and Recommendation | Regional guidelines and recommendations on substitution of lead in fishing gear and ammunition are adopted. (Joint); National guidelines and recommendations on substitution of lead in fishing gear and ammunition are issued. (National); Related regional and national outreach campaigns are arranged. (Joint and national)
39 | Measure | HL21 | Introduce by 2027 measures based on the best available scientific knowledge and technologies to restrict the use and prevent releases of perfluorinated alkyl substances, phenolic compounds with endocrine disrupting effects and chlorinated paraffins. | Sweden | WG Source to sea | EG Haz |  | Guide finalization of the literature review and consider regional measures based on the report. | A regional report on the state of the Baltic Sea with regard to the listed groups of chemical compounds is published.; Regional measures to prevent the release of these contaminants to the aquatic environment are developed.
40 | Supporting action | HL22 | HL22 - Improve knowledge base on occurrence of pharmaceutical substances in the environment, their persistence and harmful effects and ensure availability of this information for broad expert community by 2025. (Joint) | PharmaSea project | WG Source to sea | EG Haz | BSAP actions HL23, HL24 | Draft report on pharmaceuticals in the Baltic Sea region to be finalized in spring 2025. Pharmaceutical data gathered with HELCOM data call to be uploaded to the CHEMINFO database. | Information for a broad expert community about available information sources (e.g. Background document /internet platform/ database that compiles available information sources) is published.
41 | Supporting action | HL23 | HL23 - Identify priority pharmaceuticals by 2024 utilising the best available knowledge on their releases into the aquatic environment, environmental effects and available data on their use in the region, for efficient risk reduction and for subsequent integration of these substances to HELCOM assessments, as indicators of the state of the Baltic Sea and environmental pressure. (Joint) | PharmaSea project | WG Source to sea | EG Haz | BSAP actions HL22, HL24, HL1, HL10 | Draft list of priority pharmaceuticals to be finalized in spring 2025 and indicator development to be considered after the list is finalized. | By 2024 priority pharmaceuticals for the Baltic Sea region are identified. Available information about effects, releases, uses and efficient risk reduction is compiled. Priority pharmaceuticals are utilized for the assessment of the Baltic Sea state, including as indicators.
42 | Supporting action | HL24 | HL24 - Develop guidance for the environmental monitoring and analysis of pharmaceuticals identified as indicators of the state of the Baltic Sea by 2025.(Joint) | EG Haz | WG Source to sea | EG Haz | BSAP actions HL22, HL23 | The guidance is to consider also other substances than the pre-core indicator substance diclofenac and it should be both for marine and wastewater. Guide the work on developing the guidance in 2025 | Guidance for environmental monitoring and analysis is published.
43 | Supporting action | HL28 | HL28 - Address substances of emerging concern by commencing recurrent screening campaigns starting from 2021 including broad analytical techniques such as suspect screening and non-target screening methods. (Joint) | EG Haz | WG Source to sea | EG Haz | BSAP actions HL1, HL10 | BSEP on PreEMPT project results to be finalized in spring 2025. Planning for the next screening project. | The HELCOM hazardous substances screening project is implemented.
44 | Measure | HL29 | Limit the use of firefighting foam containing per- and polyfluoroalkyl substances (PFAS) at sea and in the catchment area and promote sustainable alternatives by 2027. | EG Haz | WG Source to sea | WG Maritime |  | Scoping of the action in spring 2025 followed by finding a lead and resources for implementation. | HELCOM Recommendation limiting the use of PFAS in firefighting foams at sea.; HELCOM Recommendation limiting the use of PFAS in firefighting foams in catchment area. ; Regional report on sustainable fluorine free alternatives to PFAS in firefighting foams.; HELCOM proposal to IMO to limit the use of firefighting foam containing PFAS at ships.; Communication with ECHA to facilitate the development of related restrictions at the EU level.
45 | Measure | HL30 | Minimize the release of biocides from antifouling products to the marine environment, and preferably by 2027 replace the use of biocidal antifouling products with biocide-free alternatives on structures, equipment and recreational craft in cases not already subject to the International Convention on the Control of Harmful Anti-fouling Systems on Ships when available and environmentally and technically feasible. | EG Haz | WG Source to sea | WG Maritime |  | Scoping of the action in spring 2025 followed by finding a lead and resources for implementation. | Revised or new HELCOM Recommendation on antifouling is adopted, addressing both biocidal and biocide-free practices.; HELCOM Roadmap towards biocide free antifouling in the Baltic Sea region is developed.
Climate change
46 | Supporting action | HT1 | Using the HELCOM/Baltic Earth Joint Expert Network on Climate Change as a platform and through committed implementation of the HELCOM Science Agenda, improve the access of policy-makers to scientific information on the impacts of climate change together with multiple other pressures on the Baltic Sea marine environment through periodic updates of the HELCOM Climate Change Fact Sheet, and incorporate the possible effect of climate change into the holistic assessment of status as well as effectiveness of measures by 2030 at latest. | EN Clime | WG GEAR | WG BioDiv, WG Source to sea, WG Sea-based pressures, WG Fish, EG MaMa, EG Benthic, EG Phyto, EG Zoo, JWG Bird, [EG Coastal Fish] |  | Review the updates to the Climate Change Fact Sheet relevant to the mandate of the group | The HELCOM Climate Change Fact Sheet is periodically updated.; Possible effect of climate change have been incorporated into the holistic assessment of status of the Baltic Sea environment.; Possible effect of climate change have been incorporated into the assessment of effectiveness of measures.
47 | Supporting action | HT5 | Develop a strategic approach to ocean acidification for the Baltic Sea with first steps addressing the knowledge gaps by 2025. |  | WG GEAR | EN Clime, WG BioDiv, WG Source to sea, EG Eutro, EG RedCore |  | Review the proposed strategic approach to ocean acidification for the Baltic Sea and consider organization of work in HELCOM based on proposal by WG GEAR in spring 2025 | Knowledge gaps in relation to ocean acidification in the Baltic Sea have been identified.; Identified knowledge gaps in relation to ocean acidification in the Baltic Sea have been addressed.; A strategic approach to ocean acidification for the Baltic Sea has been developed and adopted.
Monitoring
48 | Supporting action | HT6 | HT6 - Regularly review, and as necessary revise HELCOM monitoring programmes (once per six years), including the level of regional coordination, in line with the Marine Strategy Framework Directive (MSFD) reporting cycle, to adjust them to the latest technical and scientific developments for a cost-effective joint monitoring, which fully supports the indicator-based assessment approach and monitoring of the implementation of the Baltic Sea Action Plan, and is in line with other international monitoring and reporting requirements. | CP leads as identified under WG GEAR, supported by relevant EG and WGs. | WG GEAR | WG BioDIv; WG Source to sea; WG Sea-based pressures; EG Haz; EG Eutro; EG MaMa; EG Marine Litter; EG Noise; EG PhytoPEG; EG ZOO; JWG BIRD; EG RedCore |  | Update the nutrient and hazardous substances pressures related monitoring programmes once the reporting templates are available to ensure the review and update is finalized and the updated monitoring manual and programmes are published in early 2026, in good time before the national Art.11 reporting concludes. | Updated monitoring programmes are available every six years in line with what is specified in the action.
49 |  |  | Contribute to and guide the development of regional monitoring guidelines nutrients and hazardous substances. | Lead: needed | WG Source to sea
50 |  |  | Establish persistent regular data flows and data management for nutrients and hazardous substances data needed for HELCOM assessment and tracking purposes. | Lead: needed | WG Source to sea |  |  | Using the review of the HOLAS 3 (2023), data reporting and processes as a basis, identify gaps in dataflows and infrastructure. Analyze the underlying causes and identify solutions. Implement solutions to secure improved, consistent dataflows. | Lower resource requirements long term due to automatised data reporting. Improved access to data and information across the region. Enabling automatising assessment procedure.
Indicators
51 | Supporting action | B33 | B33 – By 2024 develop a roadmap to fill gaps to enable a holistic assessment for all relevant ecosystem components and pressures and, by 2030 at the latest, develop and fully operationalise a set of indicators fulfilling HELCOM’s needs, including the need to provide a regional platform for the Marine Strategy Framework Directive (MSFD). | Secretariat | WG GEAR | WG BioDiv; WG Source to sea; WG Sea-based pressures |  | Guide and ensure the progress for the development work toward HOLAS 4 related to eutrophication and hazardous substances based on HOLAS 4 workplans for eutrophication and hazardous substances. | By 2024 a Roadmap for how to fill gaps for both ecosystem components and pressures from nutrients and hazardous substances is developed. By 2030 a fully operational set of indicators enabling an ecologically relevant holistic assessment of the Baltic Sea is available
Other tasks
52 |  |  | Evaluation and reporting on implementation of BSAP actions under the responsibility of the working group. |  | WG Source to sea |  |  | WG Source to sea to review and update its workplan during 2026, for approval by HOD in December 2026. The review should include an evaluation to enable horizontal tracking of progress, identifying and tackling barriers to implementation as well as possible synergies or areas of cooperation with other working groups. A common template developed by WG GEAR should be used for reporting of progress and identifying actions where further support is needed. | Updated workplan for 2027-2028. Identification of barriers to implementation as well as possible synergies or areas of cooperation with other working groups.