## Status of implementation
CODE OF ACTION | REGIONAL ACTION | FURTHER SPECIFICATION | STATUS OF IMPLEMENTATION | MILESTONES | AREAS WHICH WILL REQUIRE MORE RESOURCES | DOCUMENTATION RELATED TO THE STATUS OF IMPLEMENTATION
1 | Improve the quality of data submitted to the HELCOM impulsive noise registry by updating and improving the common HELCOM guidelines for monitoring impulsive noise events in the Baltic Sea. | Based on the reporting to the registry already available. Main aim of action is to increase the completeness, spatio-temporal resolution and quality of submissions to the registry. | Action related to action S63 in the BSAP. Progress in EU TG Noise to be taken into account and made use of as appropriate. Germany to submit a document to EG Noise in early 2025. Aim to submit draft Guidance to IC WG SEA-BASED PRESSURES 5-2025. The timelines in the implementation plan will therefore not be met, but task 1 is expected to be completed in mid-2025 while tasks 2 and 3 are expected to be completed during 2025.
2 | Improve assessment of impact of impulsive noise by identifying important habitats and biologically sensitive areas and periods in the Baltic Sea region, where the introduction of high-energy impulsive noise is likely to have negative impact. | Based on HELCOM identified noise sensitive marine animal species (HELCOM 2019), which are to be delineated based on biological data and science-based criteria and in cooperation with other HELCOM working and expert groups (such as EG-MAMA) | IC WS IMPACT NOISE 1-2024 held on 18 September 2024 was the first step in considering this action and contributed to partially fulfilling it. A joint EG Noise and EG MaMa workshop should be organized in 2025, preferably as a physical session.
3 | Establish common methodology for the assessment of negative impact from impulsive noise | Development and description of best practice for assessing potential injury and behavioural disturbance (habitat loss) in relation to for example environmental impact assessments (EIAs) and strategic impact assessments (SIAs). | Denmark and Germany are planning to initiate national and/or bilateral research projects to support the implementation of the action. These national projects will be closely coordinated to create synergies between expert capacities and effectively work towards a common methodology for the assessment of negative impact from impulsive noise for the HELCOM area. IC RAP NOISE 2-2024 noted that Implementation of the action is progressing in accordance with the planned timeline.
4 | Further develop the HELCOM impulsive noise pre-core indicator towards an operational core indicator | This includes development of methods to assess environmental status based on the indicator as well as definition of thresholds and targets. | Possible leadership by Germany to be raised at IC WG SEA-BASED PRESSURES 4-2024. The aim should be to submit a draft updated indicator report to IC WG SEA-BASED PRESSURES 6-2025 in autumn 2025, in line with the timeline for action 16.
5 | Develop and implement one or more HELCOM impact indicators for impulsive noise | Based on the current pressure indicator, but with the inclusion of information about distribution of sensitive species and habitats. This work is a continuation of the work described in the noise sensitivity report (HELCOM 2019) and should preferably be along the same lines as the impact indicator currently under development in OSPAR and in accordance with the recommendations by EU TG-NOISE. | Action related to action S62 in the BSAP. Additional dedicated work will be needed in order to meet the timeline and enable the development of a new impact indicator for HOLAS 4. A lead would therefore be important to identify. Sweden is still working on national indicator for impulsive underwater noise, and is therefore also still considering taking the lead. Discussions at EU TG Noise in early November 2024 may also provide a way forward for this work. EG Noise in early 2025 to evaluate the OSPAR indicator and assess its usefulness for the HELCOM area.
6 | Identify Best Available Technologies (BAT) related to the abatement of impulsive noise. Among these collect existing national regulations and guidelines aimed to reduce the impact of underwater impulsive noise on the ecosystems of the Baltic Sea and related observations in order to form relevant HELCOM guidelines. | Including noise abatement systems and alternative installation methods for offshore wind farms, spatio-temporal exclusion of UXO clearing and alternatives to detonation, commercial sonars and test/training/exercise of military sonars, alternative seismic sources, and sub-bottom profilers. | Action related to action S60 in the BSAP. Germany had developed a questionnaire on BAT/BEP related to the abatement of impulsive noise. IC WG SEA-BASED PRESSURES 3-2024 welcomed the approach and recommended amendments. The Session invited Contracting Parties and Observers to provide feedback. Feedback was received from Finland, Germany, Latvia, Lithuania and Sweden as well as from the Secretariat of the Convention on the Conservation of Migratory Species of Wild Animals (CMS). Additionally, feedback was announced by Denmark. Based on the results of the feedback, three Contracting Parties have confirmed their interest in an online workshop to proceed with drafting HELCOM BAT/BEP lists. The next steps planned are the organization of the online workshop. The date has not been decided yet. In preparation to the workshop, Germany will prepare a summary of the information collected and documents submitted as part of the questionnaire. Further, Germany and a core group of experts will provide the first draft of the BAT/BEP, as outlined in action 6 of the HELCOM RAP on Underwater Noise and HELCOM BSAP action S60. | The first draft BAT Guideline should be considered by EG Noise in early 2025 and submitted for consideration to IC WG SEA-BASED PRESSURES 5-2025.
7 | Increase the use of Best Environmental Practice (BEP) and Best Available Technology (BAT) in mitigation of impact from impulsive noise by establishing common HELCOM best practice guidelines in methods for mitigation of impact from impulsive noise | Implementation of the knowledge gained from action 6. | Germany has initiated a national research project to support the implementation of the HELCOM RAP on Underwater Noise, including this action. This action will be based on progress achieved in Action 6.
8 | Improve regional and cross-border coordination of the spatio-temporal planning and permitting by establishing a common reporting system for planned activities likely to produce impulsive noise. | This constitutes an extension of the impulsive noise registry to include future activities that are currently only recorded after they occurred. | A dedicated pilot project would be needed in order to make progress and meet the envisaged timeline.
9 | Improve protection of areas, which have already been defined as important or critical habitat for noise sensitive species, by obligating the adoption of adequate operational and technical noise mitigation measures. | HELCOM (2019) already identified a number of important areas which are important for noise sensitive species (such as the core habitat of the critically endangered harbour porpoise population of the Baltic proper or spawning areas of fishes using sound for communication). If the area is already protected as an MPA, this can be included as part of the management. This does not imply that measures (such as those identified in action 6) are not required in other areas not specifically protected. | WG Fish should also contribute to the action.
10 | Reduce injury and behavioural disturbance from impulsive noise by establishing common HELCOM criteria for injury and disturbance, as well as common exposure limits. | These criteria and exposure limits are not identical to the GES-thresholds to be established under point 4, but are operational criteria that can be applied to individual activities generating impulsive noise. | Denmark and Germany are planning to initiate national and/or bilateral research projects to support the implementation of this action. These national projects will be closely coordinated to create synergies between expert capacities and effectively work towards common criteria and exposure limits for the HELCOM area. It is important to note that the comparison between Danish and German regulations on pile driving presented in document 4-1 of IC EG NOISE and ICG NOISE 2-2024 was not an official Danish position but the results of research on the matter submitted as an information document. IC RAP Noise 2-2024 noted that implementation of this action, which is linked to action 3, is progressing in accordance with the planned timeline.
11 | Improving accessibility and sharing of monitoring data by operationalisation of the common database for monitoring data on continuous underwater noise | As decided by HOD 55-2019 and implemented by database hosted by ICES. | Action related to action S63 in the BSAP. Maritime Working Group to be informed on developments related to this action.The first informal consultation workshop on HELCOM and OSPAR underwater noise data upload (IC WS NOISE DATA 1-2023), 3-4 October 2023 aimed to contribute to advance on this action. It covered the conversion of processed measured continuous noise data (one-third octave level matrices) to the ICES hdf5 format and the upload to the ICES database. A follow up discussion on the workshop was held on 14 December 2023, and a summary of such discussion is available (document 4-8 to IC WG SEA-BASED PRESSURES 3-2024). Also, an informal technical workshop on calibration and rig design was held on 24-25 September 2024 in Kista, Stockholm, Sweden. The topic is regularly revisited in the joint HELCOM EG Noise /OSPAR ICG Noise sessions (Memo of IC EG NOISE and ICG NOISE 1-2023 and Memo of IC EG NOISE and ICG NOISE 2-2024).
12 | Development of common guidelines for reporting of continuous noise levels in the Baltic Sea. | Linked to and in progress in connection to establishment of common database hosted by ICES. | Action related to action S63 in the BSAP. Progress in EU TG Noise has been slower than expected, which is why the timeline may need to be adjusted. It is still feasible to finalize the HELCOM monitoring guidelines during 2025 in order to be able to use them for HOLAS 4. If a lead is not identified, EG Noise will have to lead the work. An intercalibration workshop was conducted in September 2024, hosted by FOI in Sweden. Several Contracting Parties attended, and the outcome will be reported in due course. Also, the 1st IC Session of the HELCOM EG on Underwater Noise and the OSPAR ICG on Underwater Noise (IC EG NOISE and ICG NOISE 1-2023) in October 2023 was of relevance for this action.
13 | Increase regional coordination and management of continuous noise sources by establishing a common framework for modelling past, present and future noise levels in the Baltic. | Continuation of the Soundscape planning tool developed under the BIAS project, as decided by HOD 55-2019. Such modelling is based on AIS and other relevant information about sources, such as source levels and frequency spectra. Includes developing methods to include noise from leisure boats without AIS transmitters as well as natural ambient noise. | To consider reports on underwater noise emissions from Baltic Sea shipping regularly submitted to meetings of the Maritime Working Group. Implementation of this action on time is important in order to contribute as planned for HOLAS 4. For task 2 progress in EU TG Noise needs to be taken into account. More information on the progress is expected to be available in spring 2025. EG Noise in early 2025 should consider the outcome of work in TG Noise as well as any draft reports that may be available by that time.
14 | Improve assessment of impact of continuous noise by identifying important habitats and biologically sensitive areas and periods in the Baltic Sea region, vulnerable to elevated levels of continuous noise. | Some information available (HELCOM 2019). To be amended based on biological data and science-based criteria and in cooperation with other HELCOM working and expert groups (such as EG-MAMA).
15 | Establishment of a common methodology for assessment of impact of activities generating continuous noise. | Applies to for example shipping, offshore wind farms, offshore installations, construction works (other than pile driving and similar impulsive sources) and offshore infrastructure, etc. | Action related to action S58 in the BSAP. Maritime Working Group to be involved and informed of activities related to this action.
16 | Further develop the HELCOM continuous low-frequency noise pre-core indicator towards an operational core indicator. | This includes development of methods to assess environmental status based on the indicator (action 15) as well as definition of thresholds and targets. | IC RAP NOISE 2-2024 took note of a paper on Environmental impact assessment of continuous underwater noise in the Baltic Sea which is of relevance for this action. Updates or commitments to be provided by Contracting Parties and observers at IC WG SEA-BASED PRESSURES 4-2024. | The aim should be to submit a draft updated indicator report to IC WG SEA-BASED PRESSURES 6-2025 in autumn 2025.
17 | Increase the knowledge and encourage data sharing on impact of noise by supporting research on sources and effects of continuous noise on marine biota. | Impact studies as detailed in the HELCOM science agenda. Encourage exchange of statistical information about continuous low frequency sources, including frequencies’ spectrum characteristics. | Action related to action S57b) in the BSAP. Denmark contributes to this task through the support of a specific research project on re-routing in Kattegat (TANGO). The project was performed in collaboration with Estonia and Sweden, and investigates how splitting a big shipping route (T) into two smaller affects surrounding noise levels and harbor porpoise activity. The report “Effects of rerouting shipping lanes In Kattegat on the underwater soundscape” (document 4-1 to IC RAP Noise 2-2024) presents the results from the project. The report describes the results of the Danish monitoring and includes data from the Swedish monitoring for completeness. The data from the Swedish programs are described in detail elsewhere (Lalander et al. 2022, Owen et al. 2024). The presentations and findings of these sessions are relevant for this action: (i) Informal consultation workshop on underwater noise by shipping organised online by BSH and CCB on 8-9 Septemper 2022 (https://www.ccb.se/event/2022-workshop-underwater-noise-shipping); (ii) Informal Consultation Workshop on improving the assessment of the impact of underwater noise on noise sensitive species held on 18 September 2024 in Helsinki, Finland (IC WS IMPACT 1-2024); and (iii) the webinar and panel discussion “Impacts of continuous underwater noise on fish in the Baltic Sea”, organised by CCB and FishSec on 19 November 2024 (https://www.ccb.se/event/2024-impacts-of-continuous-underwater-noise-on-fish-in-the-baltic-sea#:~:text=Coalition%20Clean%20Baltic%20%28CCB%29%20and%20The%20Fisheries%20Secretariat,place%20online%20on%2019th%20November%202024%20%2814%3A00-16%3A30%20CET%29). Maritime Working Group to be involved and informed on activities related to this action. Finland to contribute to this action through their national Biodiversea project.
18 | Develop and implement one or more HELCOM impact indicators for continuous low-frequency noise. | Based on the current pressure indicator (action 16), but with the inclusion of information about distribution of sensitive species and habitats (action 14). | Action related to action S62 in the BSAP. Discussions and progress at EU TG Noise should be taken into account and to be considered further by EG Noise in early 2025.
19 | Expand and improve the existing and potential operational and technical measures to reduce the impact of continuous noise to form a basis for common guidelines on management. Suitable technical measures to reduce input of continuous noise should be identified (BAT/BEP), based on a scientific justification, and taking into account socioeconomic impacts | Collection of experience from HELCOM members and abroad and collection of new information through research and development, as detailed in the HELCOM science agenda | Action related to action S55 in the BSAP. Germany carried out a national research project to support the implementation of regional strategies and regional action plans in OSPAR and HELCOM (e.g. BSAP and HELCOM RAP on Underwater Noise), including a work package on shipping noise mitigation measures, that compiles and evaluates different possible measures for the reduction of ship-based continuous noise. The final report of the work package on shipping noise mitigation measures is available here: https://www.bsh.de/DE/PUBLIKATIONEN/_Anlagen/Downloads/Projekte/Method-II/Abschlussbericht_MethodII.pdf?__blob=publicationFile&v=4 IC SEA-BASED PRESSURES 3-2024 welcomed the final report and recommended using it as a basis for further developing of the management guidelines and BAT/BEP. The Session invited Contracting Parties and Observers to provide feedback on the content of the project report for consideration when developing management guidelines and BAT/BEP. Contracting Parties and observers are invited to participate in an informal correspondence group to finalize the management guidelines and BAT/BEP. At IC WG MARITIME 3-2024 and IC WG SEA-BASED PRESSURES 4-2024 Contracting Parties and Observers were invited to participate in an informal correspondence group to finalize the management guidelines and BAT/BEP as outlined in action 19 of the HELCOM RAP Noise and HELCOM BSAP action S55. The informal correspondence group started its work in the beginning of 2025 and consists of representatives of Finland, Germany, Sweden and CCB. Based on the results of the concluded national research project, discussions in the informal correspondence group and comments received, Germany provided a first draft to the informal correspondence group in February 2025, and will further guide the final drafting process of the management guidelines and BAT/BEP, as outlined in action 19 of the HELCOM RAP Noise and HELCOM BSAP action S55. | Based on the results of the concluded national research project and comments received, Germany will provide a first draft in January/February 2025, as well as guide the final drafting process of the management guidelines and BAT/BEP in an informal correspondence group starting in Q1 2025 |  | Side event organised by OceanCare, Coalition Clean Baltic (CCB) and BUND Friends of the Earth Germany in Ocean Conference 2022 “Reduce Ocean Noise and save our ocean”. https://www.ccb.se/event/2022-un-ocean-conference-side-event-noise-reduction
20 | Reduction of elevated continuous noise levels in noise sensitive and biologically important areas in the Baltic Sea by adoption of guidelines on management, based on the “HELCOM input to the establishment of environmental targets for underwater noise” (2018). The environmental targets for underwater noise should take into account the target values set by TG Noise at EU level | Implementation of knowledge gained under action 19. | Maritime Working Group to be involved and informed on activities related to this action. Possible input from CCB in connection with a pilot project on mitigation measures. Sweden is leading related work in EU TG Noise. This work could potentially also feed into the implementation of this action. Sweden therefore still considering their possibilities of taking the overall lead of this action. The outcome of pilot projects, as well as guidelines as part of action 19 should be evaluated during 2025-2026, and the results of this will be used for the completion of this action.
21 | Inciting national and voluntary actions with respect to raising awareness of ship and boat operators and cooperation with shipping companies and boat owners on speed management for their vessels including different aspects of adjusting and planning for vessel speed and engine load optimised for the reduction of underwater noise. | This can include installing monitoring systems at strategic locations (for example at outer approaches to ports) with real-time feedback to the ship’s crew, to raise awareness and to aid in optimizing vessel and engine operations for reduced underwater noise radiation. | Action related to action S57b) in the BSAP. Maritime Working Group to be involved and informed on activities related to this action. Possible input from CCB in connection with a pilot project on mitigation measures. An informal Consultation Workshop on implementation of BSAP actions related to recreational crafts (IC WS RECREATIONAL CRAFT 1-2023) was held on 27-28 September 2023 Palanga, Lithuania. A follow up workshop, organized by CCB, with support of the HELCOM Secretariat, was held in December 2024. The workshop served to continue discussions from 2023 and brainstorm ideas on how to develop a HELCOM Clean Boating Guide for the Baltic Sea Region for Contracting Parties and relevant stakeholders during 2025, where underwater noise was a topic for discussion. CCB together with research institutions from Germany, Latvia, Poland and Sweden were involved in the finalised Red Noise Baltship project (2023- 2024) for networking actions and enhancing visibility towards reducing underwater noise from commercial shipping and recreational boating activities in the Baltic Sea. Under the RED NOISE BALTSHIP project, CCB also co-organised, with FishSec, an online Webinar and panel discussion on “Impacts of continuous underwater noise on fish in the Baltic Sea” (co-funded by EU LIFE and SwAM).
22 | Enhance Baltic Sea wide cooperation of port authorities to introduce novel initiatives, such as harbour fee systems, in order to set incentives for voluntary quiet vessel operation. | See Port of Vancouver (2017), ECHO Program | Action related to action S57b) in the BSAP. Maritime Working Group to be involved and informed on activities related to this action. Findings from sessins contributing to the action: (i) the Informal consultation workshop on underwater noise by shipping organised online by BSH and CCB on 8-9 Septemper 2022 (https://www.ccb.se/event/2022-workshop-underwater-noise-shipping); (ii) the informal Consultation Workshop on implementation of BSAP actions related to recreational crafts (IC WS RECREATIONAL CRAFT 1-2023) held on 27-28 September 2023 Palanga, Lithuania; and (iii) the IMO-WMU Workshop on Underwater Radiated Noise Reduction Policies and Strategies with a Focus on Developing Countries held on 15-16 October 2024 in Malmö, Sweden. It is to be noted that a working group to develop incentives for voluntary quiet vessel operation has been established in Germany (Memo of IC EG NOISE and ICG NOISE 2-2024, para. 2.11). CCB, supported by Germany, are considering the possibilities of organizing an informal stakeholder workshop in 2025.
23 | Identification of other noise sources with significant impact on the marine ecosystems but not covered by the measures targeting impulsive and continuous noise | This includes, but is not limited to, sources with main energy above 10 kHz: echosounders, military and non-military sonars, sub-bottom profilers, net pingers, and hydroacoustic instruments. | Action related to action S57c) in the BSAP. Due to the lack of lead, progress on this action has not been achieved in accordance with the planned timeline. The Joint HELCOM/OSPAR EG Noise ICG Noise session in September 2024 noted e.g. seismic surveys and Ultra Short Baseline positioning systems (USBLs) as sources of increasing concern. Also, ultrasonic anti-fouling systems on ships are to be considered. A follow up of the SAMBAH 2 project, (CUMBIA) if funded, is expected to consider the effects of various geophysical equipment giving rise to underwater noise. The EG Noise session in early 2025 should consider this action further with a view to start developing a draft document on the matter.
24 | Identification of important habitats and biologically sensitive areas and periods in the Baltic Sea region, vulnerable to elevated levels of noise from other sources than those covered by existing pressure indicators. | Based on biological data and science-based criteria and in cooperation with other HELCOM working and expert groups (such as EG-MAMA)
25 | Compile and assess available information about potential impact caused by noise from leisure boats | As detailed in the HELCOM science agenda | Action related to action S57c) in the BSAP. Possible input from CCB in connection with a pilot project on mitigation measures. SYKE (Finland) as a partner in a LIFE IP project among other work strands measures and models the noise from recreational boating in the Archipelago Sea; vessel slowdown and MPAs are considered within the scope of the project. RIB boats should be considered to be covered by this action and other actions that address recreational craft, even though they are often used for commercial purposes. Sweden has launched a tender to support the implementation of this action (April 2025). This two-year initiative aims to advance efforts on recreational craft, both within the framework of the national programme of measures and at the regional level in support of Action 25 of the RAP Noise.
26 | Development of HELCOM indicators suitable for monitoring noise sources identified under measure 23. | Existing indicators cover impulsive noise under 10 kHz and continuous low-frequency noise, but does not include echosounders, most sonars and sub-bottom profilers, net pingers, etc. | To be considered at a later stage, once action 23 is implemented.
27 | Development of common guidelines for assessing impact from echosounders, sonars and other sources not covered by 2.1 and 2.2 | Such as to apply to environmental impact assessments (EIAs) and assessment of environmental status (GES). | Contracting Parties and observers are invited to provide information regarding projects and studies of relevance for this action, to future sessions of EG Noise or to the Secretariat directly.
28 | Support for research on pressure and impact from echosounders and other low-level, but abundant noise sources. | As detailed in the HELCOM science agenda | Action related to action S57c) in the BSAP. Denmark contributes to this task through a specific research pilot project aiming to quantify the pressure from echosounders as measured at Danish noise monitoring stations. The pilot project has been initiated and scheduled to be finalized by the end of 2022. The preliminary results of a pilot study on echosounders and sonars as a pressure factor contributes to the implementation of this action. The pilot project, by Aarhus University and the Danish Ministry of the Environment, aimed to quantify the contribution of echo sounders to underwater noise by analyzing data collected near shipping routes. The project report of is available in Danish and an English translation will be provided as soon as possible. | The pilot project is scheduled finalize by the end of 2022.
29 | Reduce the impact from acoustic deterrent devices by developing and agreeing on common guidelines and regulation of the design and use of deterrent devices | Action proposed for BSAP update | The progress made and way forward agreed by IC WS on BSAP action S61 on 30 October 2024 is expected to contribute to the implementation of this action.
30 | Strengthen coordination with IMO on the development of actions, as appropriate, to reduce underwater noise from commercial shipping and cooperate with other relevant actors as needed in the development of technical and operational solutions to reduce such noise in line with the aforementioned IMO actions. | Includes, but it is not limited to, discussions on current and future quiet ship design as well as on shipping's contribution to underwater noise and the impact of underwater noise on marine species. Initiate discussions on feasibility of reducing or otherwise regulate the emissions from echosounders (in general or restricted to sensitive areas) without compromising navigational safety. Discuss feasibility of systems providing real-time feedback to bridge about noise emissions from the ship. | Possible cooperation with the GEF on Capacity Building in the IMO framework. Contracting Parties are encouraged to inform the MEPC sessions 82-85 on lessons learned/best practices in the implementation of the revised IMO Guidelines, noting that extension of the experience building phase beyond MEPC 85 would not be ideal. IC WG SEA-BASED PRESSURES 5-2025 took note that on behalf of the OSPAR Contracting Parties, Germany will prepare a submission to IMO in relation to the experience-building phase. The Session took note of CCB’s announcement that it has applied to host a side event at the upcoming UNOC in Nice, focusing on underwater noise from shipping and its links to decarbonisation.
31 | Establish platforms to share best practices on policy options within member states and between authorities, the private sector and NGO’s. Improve public awareness, so that political decision makers, local administrations and civil society are adequately informed about the underwater noise challenges. | For example, issuing a bulletin on best practices and policy options in the region and in the world. | Maritime Working Group to be involved, active and informed on activities related to this action. Consider the findings of the Informal consultation workshop on underwater noise by shipping organised online by BSH and CCB on 8-9 Septemper 2022 (https://www.ccb.se/event/2022-workshop-underwater-noise-shipping). CCB has coordinated the submission of an application for LIFE funding for the QuietWaters Project related to underwater noise from recreational craft, which is expected to be able to contribute to the development of an online platform, if funded. IC WG SEA-BASED PRESSURES 4-2024 considered the possibilities of hosting an online platform to share best practices on policy options related to underwater noise on the HELCOM website, or other options such as DOSITS, as well as related budgetary implications. The Session recognized the need for such an online platform and invited EG Noise to consider the envisaged contents as well as options for hosting such a platform (HELCOM website, DOSITS, ICES etc.) at their next session, before a recommendation can be made on where to host the platform.
32 | Strengthen the cooperation with OSPAR on development of common and/or compatible indicators, databases and assessment methodologies | As agreed on an overall level in the 2018 HELCOM Brussels declaration | It is a continuous activity. The Second Informal Consultation Session of the HELCOM EG on Underwater Noise and the OSPAR ICG on Underwater Noise (IC EG NOISE and ICG NOISE 2-2024) was held on 17 September 2024 in Helsinki, Finland.
33 | Maintain and strengthen cooperation with the European Union expert group TG-Noise on issues of mutual interest | In particular to assure consistency in development of indicators and criteria and methods for establishing thresholds and targets
34 | Reduce the impact from leisure boats by establishing a discussion with producers of echosounders and fishfinders with the goal of introducing standards for noise emission from echosounders, fishfinders and engines of leisure boats. | This aims for example at installing on/relates to the ability to turn off and adjust source level and frequency of echosounders and fish-finders, as well as developing industry standards for underwater noise emissions for boat engines. | Action related to actions S56 and S57b) in the BSAP. Maritime Working Group to be involved, active and informed on activities related to this action. Possible input from CCB in connection with a pilot project on mitigation measures. The action, according to its implementation plan, has not been initiated yet. However, IC EG NOISE and ICG NOISE 2-2024 recognized that standards for noise emission from echosounders, fishfinders and engines of leisure boats could potentially be developed jointly with OSPAR. The Session took note that CCB is in the process on putting together a project in relation to this action (Memo of IC EG NOISE and ICG NOISE 2-2024 para. 2.13). IC WG MARITIME 3-2024 took note of the information provided by CCB on the Red Noise Baltship Project and QuietWaters Project application (document 11-6), including upcoming events as well as the planned development of a Digital Baltic Sea Platform for Recreational Craft, which could potentially be hosted by HELCOM if agreed by Contracting Parties.
35 | Reduce the impact from underwater explosions in connection to munition clearance, by developing international guidelines for the safe removal and detonation of ammunition. The guidelines should be established through consultation with the Ministry of Defence of the Russian Federation and NATO and lead actions for use of noise mitigation technologies and operating practices in the Baltic Sea. | Initiate discussions on the use of noise mitigation measures, as well as informing nature protection institutions about planned detonations and mitigation methods. | Maritime Working Group to follow this action in relation to safety of navigation, and be consulted if needed. CCB to contribute to the implementation of this action. EG Submerged to support EG Noise on the implementation of the action, noting the strong link between the action and BSAP action S34.

## Leadership by country
LEADERSHIP
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden | CCB | Joint contact group of HELCOM and OSPAR representatives and Secretariat | HELCOM Secretariat
1 |  | To contribute to parts of the action |  |  | Lead. Responsible of implementing Task 1 |  |  |  |  | To contribute to parts of the action
2 | [7 empty] | To contribute with overlaying data on noise sensitive species and noise input on maps |  |  | To take the lead of Task 1
3 | Co-lead |  |  |  | Co-lead
4
5 |  | To support | [7 empty] | To support work on other relevant species groups different from marine mammals
6 |  |  |  |  | Lead |  |  |  |  | To support | To support
7 |  |  |  |  | Lead
8 | Considering co-leading |  |  | Considering co-leading if the Aurora Interreg project is granted | Considering co-leading |  |  |  |  | Co-lead
9 |  |  |  | To contribute
10 | Lead |  |  |  | Co-lead
11 | [11 empty] | To lead
12
13
14 | [10 empty] | CCB to take the lead of Task 1
15
16
17 | Co-lead | To contribute | [7 empty] | To contribute
18 |  | To support |  | May be able to contribute | [5 empty] | To support work on other relevant species groups different from marine mammals
19 |  |  |  |  | Lead
20 |  |  |  | Can very likely contribute. | [6 empty] | Possible input in connection with a pilot project on mitigation measures
21 |  |  |  | Can very likely contribute. | [6 empty] | CCB taking the lead of Task 1 in connection with a pilot project on mitigation measures as well as on material towards raising awareness, depending on funding available.
22
23
24 |  |  |  | Can very likely contribute | [6 empty] | To take the lead of Task 1.
25 |  |  |  | Can very likely contribute | [5 empty] | Lead | Possible input in connection with a pilot project on mitigation measures.
26
27
28 | Co-Lead
29
30 |  |  |  |  | To assist | [7 empty] | To lead
31 |  |  |  |  | To contribute | [5 empty] | Co-lead
32*
33**
34 |  |  |  | May be able to contribute. | [6 empty] | Possible input in connection with a pilot project on mitigation measures
35 |  |  |  | Can very likely contribute if the Aurora Interreg project is granted | [6 empty] | To contribute
*No lead needed (Secretariats and Chair to lead).
**No lead needed

## National actions
ACTIVITIES
CODE OF ACTION | Denmark | Estonia | EU | Finland | Germany | Latvia | Lithuania | Poland | Russia | Sweden
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17